## PERIODIC
DEPARTMENT OF FEEDER ROADS
CENTRAL REGION
MONTHLY PROGRESS REPORT FOR JUNE 2014
NO. | AGENCY | REGION | PROJECT LOCATION (DISTRICT) | CONTRACT NUMBER | ACTIVITY | CONTRACT NAME | ROAD LENGTH (KM) | CONTRACTOR | FUNDING & SOURCES | WORK PERIOD |  |  |  |  | REVISED COMPLETION DATE | NO. OF CULVERTS | CONTRACT SUM (GH¢) | REVISED CONTRACT SUM | TOTAL AMOUNT CERTIFIED | OUTSTANDING | % ACHIEVEMENT |  | REMARKS | WORK DONE | ACTUAL COMPLETION DATE | ROAD NUMBER | CERT. NO | % TIME SPENT
[10 empty] | AWARD | DATE OF | TIME DAYS | DATE OF | TIME DAYS | [6 empty] | FINANCIAL | PHYSICAL
[10 empty] | DATE | COMM. | AWARD - START | COMP. | START - COMP.
COCOBOD/CRIP
1 | DFR | CENTRAL | UDW | DFR/CR/SURF/CRIP/PH3/08/5 | Surf. | Nkwantanum-Asaman F/R PH 1 | 5 | Saitama Ent. Ltd. | COCOBOD/CRIP | 2008-10-07 | - | - | - | - | - | - | 778153.2 | 778153.2 | 0 | 778153.2 | 0 | - | Project terminated on 15/03/11 |  |  |  |  | CR-UED-C-014
2 | DFR | CENTRAL | UDW | DFR/CR/SURF/CRIP/PH3/08/6 | Surf. | Nkwantanum-Asaman F/R PH 3 | 5 | Nins Dev. Ltd. | COCOBOD/CRIP | 2012-01-18 | - | - | - | - | - | 7№ 700X900mm,1№ 900X1200mm ,1№ 2/900X1200mm U-Culvert,160m of 450x450x120mm,200m of 600x600x150mm Conc. U-drain completed | 1022583.05 | 1022583.05 | 475476.75 | 547106.3 | 46.4976 | 50 | Work in progress | Clearing , 7No 700x900mm, 1No 900x1200mm, 1No 2/900x1200mm U culvert, 160m of 450x450x120mm, 200m of 600x600x150mm Conc. U-drain completed, 2.5km sub-base completed. |  |  |  | CR-UED-C-014 |  | #VALUE! | 2014-07-07
3 | DFR | CENTRAL | Assin North | DFR/CR/SURF/COCOA/01/2007 | Surf. | Akropong-Odumase F/R PH 1 | 6 | Johaze Ltd. | COCOBOD/CRIP | 2008-01-29 | 2008-03-11 | 42 | 2009-03-11 | 365 | 2009-03-11 | 500m of 450x450x120mm Conc. U-drain and 4No 700x900mm U-culvert completed. | 560493.3 | 560493.3 | 137250.54 | 423242.76 | 24.4875 | 52 | Project Terminated on 3/11/09. | Clearing,formation, 500m of 450x450x120mm Conc. U-drain, 4No 700x900mm U-culvert ,3.0km of base & sub-base completed |  |  |  | CR-ASN-C-026 | 3
4 | DFR | CENTRAL | Assin North | DFR/CR/SURF/CRIP/PH3/08/2 | Surf. | Akropong-Odumase F/R PH 2 | 4 | Asuowam Complex Ltd. | COCOBOD/CRIP | 2008-12-24 | 2009-04-13 | 110 | 2010-04-13 | 365 | 2010-04-13 | 3№ 700x900mm U-culvert,2,371m 450x450mm U-drain completed | 897044.72 | 897044.72 | 713220.67 | 183824.05 | 79.5078 | 85 | Slow progress.Fourth Warning letter issued on 12/03/10 | Clearing,3No 700x900mm U-culvert, 2,371m 450x450mm U-drain completed |  |  |  | CR-ASN-C-026 | 6 | 523.5616 | 2014-07-07
5 | DFR | CENTRAL | Agona West | DFR/CR/SUR/COCOA/4/2007 | Surf. | Agona Nyarkrom-Otenkorang-Bosompa | 15 | Saraswate Civil & Building Const. Ltd | COCOBOD/CRIP | 2007-11-29 | 2008-03-18 | 110 | 2010-03-18 | 730 | 2010-03-18 | 4,238m 450x450x120mm Concrete U drains completed | 2140458.46 | 2140458.46 | 588921.8 | 1551536.66 | 27.5138 | 41 | Project Terminated on 21/7/10. | Clearing, 4,238m 450x450x120mm Concrete U drains completed |  |  |  | CR-AGO-I-039 | 5
6 | DFR | CENTRAL | Assin North | DFR/CR/SURF/COCOA/02/2007 | Surf. | Akonfudi-Camp-Appolinningo F/R PH 1 | 6.5 | Kingsman Ltd. | COCOBOD/CRIP | 2008-01-30 | 2008-05-30 | 121 | 2009-05-30 | 365 | 2009-05-30 | 4№ 700X900mm U-culvert completed. | 700060.7 | 700060.7 | 92246.42 | 607814.28 | 13.1769 | 50 | Project Terminated on 3/11/09.Refund GH¢ 87,299.08 MOB Loan | Clearing, 4No 700x900mm U-culvert completed |  |  |  | CR-ASN-I-017 | 2
7 | DFR | CENTRAL | Assin North | DFR/CR/SURF/COCOA/03/2007 | Surf. | Akonfudi-Camp-Appolinningo F/R PH 2 | 6 | Tatop Company Ltd. | COCOBOD/CRIP | 2008-01-29 | 2008-03-21 | 52 | 2009-03-21 | 365 | 2009-03-21 | Clearing, 6No 700x900mm,2No 900x1200mm U-culvert completed | 642582.88 | 642582.88 | 211031.75 | 431551.13 | 32.8412 | 30 | Project Terminated on 4/02/11. | Clearing, 6No 700x900mm,2No 900x1200mm U-culvert completed |  |  |  | CR-ASN-I-017 | 3
8 | DFR | CENTRAL | UDE | DFR/CR/SURF/CRIP/PH3/08/1 | Surf. | Kyekyewere-Kumakrom F/R PH 1 | 6 | Siltek Const. Ltd. | COCOBOD/CRIP | 2008-12-23 | 2009-02-05 | 44 | 2010-02-05 | 1075 | 2012-01-16 | 4№ 700x900mm,3№ 900x1200mm,1№ 2/700x900mm | 1338767.14 | 1338767.14 |  | 1338767.14 | 66.1 | 51.67 | Clearing,4№ 700x900mm,3№ 900x1200mm,1№ 2/700x900mm, 1,318m 600x600mm, 405m 450x450mm Concrete 'U' Drain Completed | Clearing, 4No 700x900mm,3No 900x1200mm, 1No 2/700x900mm U-culvert completed |  |  |  | CR-UED-A-060 | 1
9 | DFR | CENTRAL | UDE | DFR/CR/SURF/CRIP/PH3/08/4 | Surf. | Kyekyewere-Kumakrom F/R PH 2 | 5.8 | Nins Dev. Ltd. | COCOBOD/CRIP | 2008-12-24 | 2009-01-22 | 29 | 2010-01-22 | 813 | 2011-04-15 | 3№ 700X900mm,1№ 900X1200mm U-Culvert completed. | 857461.16 | 2153994.64 | 1512456.29 | 0 | 70.2163 | 100 | Project completed | Clearing,3№ 700x900mm, 1No 900x1200mm U-culverts completed, 5.0 sub-base, base and primer completed |  |  |  | CR-UED-A-060 | 8
10 | DFR | CENTRAL | UDW | DFR/CR/SURF/CRIP/PH3/08/1 | Surf. | Nkwantanum-Asaman F/R PH 2 | 5 | Effasco Ltd. | COCOBOD/CRIP | 2008-12-24 | 2009-02-04 | 42 | 2010-02-04 | 1217 | 2012-06-05 | 7№ 700X900mm U-Culvert completed | 787239 | 787239 | 167054.45 | 620184.55 | 26 | 12.76 | Work in progress | 7№ 700X900mm U-Culvert completed |  |  |  | CR-UED-C-014 | _ | 162.613 | 2014-07-07
11 | DFR | CENTRAL | THLD | DFR/CR/SURF/CRIP/PH3/08/3 | Surf. | Anyinase-Kayireku-Osenagya F/R PH 1 | 4.5 | Siltek Const. Ltd. | COCOBOD/CRIP | 2008-12-23 | 2009-02-05 | 44 | 2010-02-05 | 2096 | 2014-11-02 | 8№ 700x900mm,1№ 900x1200mm,2№ 1250x1800mm U-culvert,280m 450x450x120mm,208m 600x600x150mm Conc. 'U' drain,455.9m of kerbs completed. | 731733.88 | 2462238.56 | 1627442.47 | 834796.09 | 66.0961 | 51.67 | Project is behind schedule | Clearing, 8№ 700x900mm,1№ 900x1200mm,2№ 1250x1800mm U-culvert,280m 450x450x120mm,208m 600x600x150mm Conc. 'U' drain,455.9m of kerbs completed. |  |  |  | CR-LDE-I-022 | 3 | 94.3702 | 2014-07-07
12 | DFR | CENTRAL | THLD | DFR/CR/SURF/CRIP/PH3/08/8 | Surf. | Anyinase-Kayireku-Osenagya F/R PH 2 | 4.7 | Big Tanko Ltd. | COCOBOD/CRIP | 2008-10-03 | 2008-12-01 | 59 | 2009-12-01 | 1530 | 2013-02-08 | 5№ 700X900mm U-culvert,500m of 450x450x120mm Conc. U-drain completed. | 935290.86 | 935290.86 | 388582.49 | 546708.37 | 41.5467 | 65 | Slow progress.Project Terminated reversed on 2012. | 5№ 700X900mm U-culvert,500m of 450x450x120mm Conc. U-drain completed, Clearing in progress |  |  |  | CR-LDE-I-022 | 1 | 133.5948 | 2014-07-07
COCOBOD/CFRIP
13 | DFR | CENTRAL | Mfantsiman | DFR/CR/MF/SURF/GOG/2011 | Surf. | Essuehia Akra & Others | 18.91 | Gen. Const. & Dev. Ltd. | COCOBOD/CFRIP | 2011-01-04 | 2011-03-18 | 73 | 2013-03-18 | 731 | 2013-03-18 | 3№ 900x1200mm,3№ 2/900x1200mm,14№ 700x900mm U-culvert and 6,956m 450x450x120mm,2,623m 600x600x150mm,220m 900x900x150mm Conc U-drain,679m of kerbs completed | 7069530.64 | 9537373.01 | 12842104.67 | 0 | 134.6503 | 100 | Final retention released on 24/06/2014 | 3№ 900x1200mm,3№ 2/900x1200mm,14№ 700x900mm U-culvert and 6,956m 450x450x120mm,2,623m 600x600x150mm,220m 900x900x150mm Conc U-drain,679m of kerbs completed |  |  |  | CR-MFA-A-015 CR-MFA-C-018 |  | 165.1163 | 2014-07-07
14 | DFR | CENTRAL | AEE | DFR/CR/AEE/CFRIP PHI/SURF/1A/11 | Surf. | Besease - Anyinasu F/R (A) | 3.5 | Lartan Ltd. | COCOBOD/CFRIP | 2011-07-05 | 2011-08-23 | 49 | 2012-08-23 | 366 | 2012-08-23 | 3No 700x900mm,2No 900x1200mm U- culvert completed | 781550.75 | 781550.75 | 94864.87 | 686685.88 | 21.05 | 35 | Slow progress. Third warning letter given on 20/7/12 | Clearing,3No 700x900mm,2No 900x1200mm U-culvert completed |  |  |  | CR-AJU-C-001 | 2 | 286.612 | 2014-07-07
15 | DFR | CENTRAL | AEE | DFR/CR/AEE/CFRIP PHI/SURF/1B/11 | Surf. | Besease - Anyinasu F/R (B) | 2.5 | Gluck Fides Ent. | COCOBOD/CFRIP | 2011-07-12 | 2011-08-23 | 42 | 2012-08-23 | 366 | 2012-08-23 | 3No 700x900mm,1No 900x1200mm U- culvert,272m 450x450x120mm Conc U-drains completed | 748466.66 | 748466.66 | 112475.45 | 635991.21 | 15.0274 | 25 | Slow progress. Second warning letter given on 11/6/12 | Clearing completed, 3No 700x900mm,1No 900x1200mm U- culvert,272m 450x450x120mm Conc U-drains completed |  |  |  | CR-AJU-C-001 |  | 286.612 | 2014-07-07
16 | DFR | CENTRAL | THLD |  | Spot Imp. | Agona Mirekukrom - Ayaase F/R (A) | 7 | Jamas Co. Ltd. | COCOBOD/CFRIP | 2011-07-06 | 2011-08-26 | 51 | 2012-08-26 | 366 | 2012-08-26 | 16No 700x900mm,4No 900x1200mm,1No 2/900x1200mm,1No 1250x1800mm U- culvert ,160m 600x600x150mm Conc U-drainscompleted. | 791815.55 | 791815.55 | 318835.89 | 472979.66 | 40.2664 | 85 | Work in progress | Clearing and formation completed, 16No 700x900mm,4No 900x1200mm,1No 2/900x1200mm,1No 1250x1800mm U- culvert ,160m 600x600x150mm Conc U-drainscompleted, 6.0km of sub-base and base completed. |  |  |  | CR-LDE-C-037 |  | 285.7923 | 2014-07-07
17 | DFR | CENTRAL | THLD | DFR/CR/THLD/CFRIP PHI/REH/2B/11 | Spot Imp. | Agona Mirekukrom - Ayaase F/R (B) | 10 | Nataco Beach Resort & Const. Ltd. | COCOBOD/CFRIP | 2011-07-06 | 2011-08-26 | 51 | 2012-08-26 | 366 | 2012-08-26 | 18No 700x900mm U- culvert,220m 600x600x150mm,212m 900x900x150mm Conc U-drains completed | 827334.26 | 827334.26 | 527949.72 | 299384.54 | 63.8134 | 58.7 | Works in progress | 18No 700x900mm U- culvert,220m 600x600x150mm,212m 900x900x150mm Conc U-drains completed |  |  |  | CR-LDE-C-037 |  | 285.7923 | 2014-07-07
18 | DFR | CENTRAL | THLD | DFR/CR/THLD/CFRIP PHI/SURF/3A/11 | Surf. | Praso-Bimponagya - Bimponso F/R (A) | 4.5 | Opakoh Ent. | COCOBOD/CFRIP | 2011-07-06 | 2011-08-23 | 48 | 2012-08-23 | 442 | 2012-11-07 | 3No 700x900mm,1No 1800x1800mm ,1No 2/1800x1800mm U- culvert,384m 450x450x120mm Conc U-drains | 1199066.95 | 1199066.95 | 312651.72 | 886415.23 | 26.0746 | 35 | Work in progress | 3No 700x900mm,1No 1800x1800mm ,1No 2/1800x1800mm U- culvert,384m 450x450x120mm Conc U-drains |  |  |  | CR-LDE-I-001 |  | 237.3303 | 2014-07-07
19 | DFR | CENTRAL | THLD | DFR/CR/THLD/CFRIP PHI/SURF/3B/11 | Surf. | Praso-Bimponagya - Bimponso F/R (B) | 3 | Stafco Ltd. | COCOBOD/CFRIP | 2011-07-05 | 2011-08-26 | 52 | 2012-08-26 | 644 | 2013-05-31 | 4No 700x900mm,1No 900x1200mm,1No 1200x1200mm U-culvert, 1,045m 450x450x120mm Conc U-drains,390m kerbs completed, 3.0KM sub-base, base, primer and seal completed | 922627.64 | 922627.64 | 1224436.98 | 0 | 158.95 | 100 | Work completed | 4No 700x900mm,1No 900x1200mm,1No 1200x1200mm U-culvert, 1,045m 450x450x120mm Conc U-drains,390m kerbs completed, 3.0KM sub-base, base, primer and seal completed |  |  |  | CR-LDE-I-001 |  | 162.4224 | 2014-07-07
20 | DFR | CENTRAL | Assin South | DFR/CR/AS/CFRIP PHI/SURF/4A/11 | Surf. | Assin Manso - Anyinasu F/R (A) | 5 | Konasah Ent Ltd. | COCOBOD/CFRIP | 2011-07-06 | 2011-08-09 | 34 | 2012-10-23 | 511 | 2013-01-01 | 5No 700x900mm,3No 900x1200mm,1No 1250x1800mm U-culvert, 1,200m of 450x450x120mm,410m of 600x600x150mm,102m of 900x900x150mm Conc U-drains completed. | 1449949.11 | 1554996.71 | 875095.76 | 679900.95 | 56.2764 | 100 | Work completed | 5No 700x900mm,3No 900x1200mm,1No 1250x1800mm U-culvert, 1,200m of 450x450x120mm,410m of 600x600x150mm,102m of 900x900x150mm Conc U-drains completed, sub-base, base, primer and seal completed. |  |  |  | CR-AJU-I-002 |  | 208.0235 | 2014-07-07
21 | DFR | CENTRAL | Assin South | DFR/CR/AEE/CFRIP PHI/SURF/4B/11 | Surf. | Assin Manso - Anyinasu F/R (B) | 5 | Joe Azar Co. Ltd. | COCOBOD/CFRIP | 2011-07-05 | 2011-08-23 | 49 | 2012-10-23 | 427 | 2012-10-23 | 1,100m of 450x450x120mm Conc U-drains,108m Kerbs completed. | 1307389.3 | 1307389.3 | 161423.66 | 1145965.64 | 12.347 | 80 | Work in progress | 1,100m of 450x450x120mm Conc U-drains, 108m Kerbs,2.18 Ha clearing and 2376 Cu.m cutting, sub base, base and primer seal completed |  |  |  | CR-AJU-I-002 |  | 245.6674 | 2014-07-07
22 | DFR | CENTRAL | AOB | DFR/CR/AS/CFRIP PHI/SURF/5A/11 | Surf. | Breman Baako -Anyinabrim F/R (A) | 2.5 | Pee-Wuud Const. Ltd. | COCOBOD/CFRIP | 2011-07-16 | 2011-10-12 | 88 | 2012-10-12 | 701 | 2013-09-12 | 1No 900x1200mm,1No 700x900mm U- culvert,400m of 450x450x120mm Conc U-drains,190m Kerbs completed | 561716.82 | 561716.82 | 172178.64 | 389538.18 | 30.6522 | 50 | Slow progress. Third warning letter given on 6/9/12 | 1No 900x1200mm,1No 700x900mm U- culvert,400m of 450x450x120mm Conc U-drains,190m Kerbs completed |  |  |  | CR-ASS-I-044 |  | 142.5107 | 2014-07-07
23 | DFR | CENTRAL | AOB | DFR/CR/AS/CFRIP PHI/SURF/5B/11 | Surf. | Breman Baako -Anyinabrim F/R (B) | 3 | Alt Const. Ltd. | COCOBOD/CFRIP | 2011-07-06 | 2011-10-12 | 98 | 2012-10-12 | 366 | 2012-10-12 | 1No 900x1200mm,2No 700x900mm U- culvert,509m of 450x450x120mm Conc U-drains,100m Kerbs completed. | 776866.57 | 776866.57 | 345582.52 | 431284.05 | 41.45 | 55 | Work in progress | 1No 900x1200mm,2No 700x900mm U- culvert,509m of 450x450x120mm Conc U-drains,100m Kerbs completed. |  |  |  | CR-ASS-I-044 |  | 272.9508 | 2014-07-07
24 | DFR | CENTRAL | AEE | DFR/CR/AEE/CFRIP PHII/SURF/6/11 | Surf. | Dominase - Assin Subinso Var No. 4 | 16.2 | Bildex Farms Ltd. | COCOBOD/CFRIP | 2011-08-29 | 2011-11-11 | 74 | 2013-06-28 | 642 | 2013-08-14 | 2No 900x1200mm,3No 700x900mm U- culvert,1,763m of 450x450x120mm Conc U-drains completed. After V.O, 6No 900mm pipe, 1777m of 450x450x120mm, 632m of 600x600x150mm Conc U-drains completed | 1764145.8 | 7147177.12 | 2877685.05 | 0 | 0 | 15 | Work in progress | 2No 900x1200mm,3No 700x900mm U- culvert,1,763m of 450x450x120mm Conc U-drains completed, 6.20km of sub-base, base and primer completed. After V.O, 6No 900x1200mm, 1777m of 450x450x120mm, 632m of 600x600x150mm Conc U-drains completed
25 | DFR | CENTRAL | THLD | DFR/CR/THLD/CFRIP PHII/SURF/7/11 | Surf. | Praso-Bimponagya - Bimponso F/R | 3.5 | Mode Ent. Ltd. | COCOBOD/CFRIP | 2011-06-06 | 2011-11-02 | 149 | 2012-11-02 | 520 | 2013-04-05 | 5No 700x900mm,1No 1250x1800mm U-culvert,300m 450x450x120mm,690m 600x600x150mm Conc U-drains completed. | 1172355.5 | 1172355.5 | 416724.17 | 755631.33 | 35.5459 | 40 | Work in progress | Clearing, 5No 700x900mm,1No 1250x1800mm U-culvert,300m 450x450x120mm,690m 600x600x150mm Conc U-drains completed. |  |  |  | CR-AJU-C-001 |  | 188.0769 | 2014-07-07
26 | DFR | CENTRAL | THLD | DFR/CR/THLD/CFRIP PHII/SURF/8/11 | Surf. | Praso-Bimponagya - Bimponso F/R | 4 | Sunlu (Gh) Ltd. | COCOBOD/CFRIP | 2011-08-24 | 2011-11-29 | 97 | 2012-11-29 | 366 | 2012-11-29 | 500m of 450x450x120mm & 80m of 600x600x150mm Conc U-drains,1№ 900x1200mm U-culverts completed | 1221576.08 | 1221576.08 | 121537.26 | 1100038.82 | 11.4 | 20 | Work in progress | Clearing, 500m of 450x450x120mm & 80m of 600x600x150mm Conc U-drains,1№ 900x1200mm U-culverts completed |  |  |  | CR-LDE-I-001 |  | 259.8361 | 2014-07-07
27 | DFR | CENTRAL | UDE | DFR/CR/THLD/CFRIP PHII/SURF/9/11 | Surf. | Dunkwa - Buabin - Mbrayaim F/R | 20 | Ussuya (Gh) Ltd. | COCOBOD/CFRIP | 2011-08-24 | 2011-12-06 | 104 | 2013-06-06 | 548 | 2013-06-06 | 12No 700x900mm completed | 4989270.16 | 4989270.16 | 314101.98 | 4675168.18 | 6.2955 | 30 | Work in progress | 3No 700x900mm,9No 900x1200mm U-culvert completed |  |  |  | CR-LDE-I-001 |  | 172.2628 | 2014-07-07
28 | DFR | CENTRAL | AOB | DFR/CR/AOB/CFRIP PHII/SURF/10/11 | Surf. | Breman Baako -Anyinabrim F/R | 5.5 | K.E. & Sons Ltd. | COCOBOD/CFRIP | 2011-08-29 | 2011-10-28 | 60 | 2013-01-28 | 504 | 2013-03-15 | 5No 700x900mm,2No 900x1200mm U-culvert,583m of 450x450x120mm Conc U-drains completed | 1396431.2 | 1396431.2 | 313255.17 | 1083176.03 | 22.4326 | 40 | Work in progress | Clearing, 2No 700x900mm,7No 900x1200mm, 2No 1200x1200mm and 1No 2/1800x1800mm U-culvert and 5.50km of sub-base completed |  |  |  | CR-UED-A-025/ CR-UED-A-043 |  | 195.0397 | 2014-07-07
29 | DFR | CENTRAL | AAK | DFR/CR/AAK/CFRIP PHII/SURF/11/11 | Surf. | Eguase - Amosima F/R | 3.8 | Sambrain Tricosal Co. Ltd. | COCOBOD/CFRIP | 2011-08-24 | 2011-12-05 | 103 | 2013-03-05 | 456 | 2013-03-05 | 2No 900x1200mm,10No 700x900mm U-culvert completed | 1396431.2 | 1396431.2 |  | 1396431.2 |  | 35 | Slow progress. First warning letter given on 13/4/12 | 2No 900x1200mm,10No 700x900mm U-culvert completed |  |  |  | CR-ASS-I-044 |  | 207.2368 | 2014-07-07
30 | DFR | CENTRAL | Gomoa West | DFR/CR/GW/CFRIP/SURF/12/11 | Surf. | Mankoadze Jn - Mankoadze F/R | 6.25 | O.D.B. Const. Ltd. | COCOBOD/CFRIP | 2011-08-29 | 2011-11-01 | 64 | 2013-02-01 | 458 | 2013-02-01 | 5№ 700x900mm U-culverts, 1№ 1250x1800mm U-culvert, 870m of 450x450x120mm,200m of 600x600x150mm Conc U-drains completed | 1422405.26 | 1422405.26 | 290309.4 | 1132095.86 | 24.58 | 30 | Slow progress. Third warning letter given on 22/10/12 | 5№ 700x900mm U-culverts, 1№ 1250x1800mm U-culvert, 870m of 450x450x120mm,200m of 600x600x150mm Conc U-drains completed |  |  |  | CR-AAK-C-017 |  | 213.7555 | 2014-07-07
31 | DFR | CENTRAL | Agona West | DFR/CR/AW/CFRIP/SI/1A/11 | Spot Imp. | Wawase - Amponsa F/R | 4 | Mohamsah Ltd. | COCOBOD/CFRIP | 2012-08-08 | 2012-10-09 | 62 | 2013-10-09 | 365 | 2013-10-09 | 4No 700x900mm,3No 900x1200mm U-culvert completed | 200182.3 | 200182.3 | 78646.39 | 121535.91 | 44.83 | 60 | Work in progress | 4No 700x900mm,3No 900x1200mm U-culvert completed |  |  |  | CR-GOM-A-003 |  | 174.2466 | 2014-07-07
32 | DFR | CENTRAL | Agona West | DFR/CR/AW/CFRIP/SI/1B/11 | Spot Imp. | Jacob - Nkwanfo | 3.5 | E. Speedway Const. Ltd. | COCOBOD/CFRIP | 2012-06-05 | 2012-10-10 | 127 | 2013-10-10 | 365 | 2013-10-10 | 6No 700x900mm,2No 900x1200mm U-culvert completed | 215574.42 | 215574.42 | 79077.25 | 136497.17 | 41.34 | 50 | Work in progress | Clearing , 6№ 700X900mm, 2No 900x1200mm U-Culvert,Sub-base & base completed |  |  |  | CR-AGO-A-030 |  | 173.9726 | 2014-07-07
33 | DFR | CENTRAL | Agona West | DFR/CR/AW/CFRIP/SI/2A/11 | Spot Imp. | Swedru - Otepro F/R | 4 | Blessedfield Ltd. | COCOBOD/CFRIP | 2012-06-05 | 2012-12-19 | 197 | 2013-12-19 | 365 | 2013-12-19 | 5No 700x900mm,2No 900x1200mm U-culvert completed | 162004.15 | 162004.15 |  | 162004.15 | 0 | 35 | Work in progress | 5No 700x900mm,2No 900x1200mm U-culvert completed |  |  |  | CR-AGO-A-020 |  | 154.7945 | 2014-07-07
34 | DFR | CENTRAL | Assin North | DFR/CR/AN/CFRIP/SI/2B/11 | Spot Imp. | Amoakrom Jn - Amoakrom | 3 | Akakyere Ventures | COCOBOD/CFRIP | 2012-06-05 | 2012-11-26 | 174 | 2013-11-26 | 365 | 2013-11-26 | 2№ 700x900mm U-culverts completed | 196278.23 | 196278.23 |  | 196278.23 | 0 | 50 | Work in progress | 2№ 700x900mm U-culverts completed |  |  |  | CR-AGO-A-001 |  | 161.0959 | 2014-07-07
35 | DFR | CENTRAL | AEE | DFR/CR/AEE/CFRIP/SI/3A/11 | Spot Imp. | Nyamebekyere - Amoanda | 5 | Karins Gh Ltd. | COCOBOD/CFRIP | 2012-06-05 | 2012-11-02 | 150 | 2013-11-02 | 365 | 2013-11-02 |  | 263003.6 | 263003.6 |  | 263003.6 | 0 |  | Possesion of site given |  |  |  |  | CR-ASN-A-034 |  | 167.6712 | 2014-07-07
36 | DFR | CENTRAL | AEE | DFR/CR/AEE/CFRIP/SI/3B/11 | Spot Imp. | Nyemebekyere - Ekwamase | 4 | Josh Yank Ent. Ltd. | COCOBOD/CFRIP | 2012-08-08 | 2012-10-11 | 64 | 2013-10-11 | 365 | 2013-10-11 | 1No 700x900mm,2No 900x1200mm U-culvert completed | 208432.12 | 208432.12 | 63073.4 | 145358.72 | 30.2609 | 29.07 | Work in progress | Clearing, formation 1No 700x900mm,2No 900x1200mm U- culvert and sub-base completed |  |  |  | Not Available |  | 173.6986 | 2014-07-07
37 | DFR | CENTRAL | AOB | DFR/CR/AOB/CFRIP/REH/4A/11 | Rehab. | Anhwiam - Kwaanankwaa | 3 | Kobnasah Inv. Ltd. | COCOBOD/CFRIP | 2012-08-08 | 2012-11-13 | 97 | 2013-11-12 | 358 | 2013-11-06 | 4No 900x1200mm,2No 2/900x1200mm U-culvert completed. | 482930.23 | 482930.23 | 157809.38 | 325120.85 | 32.6775 | 40 | Work in progress | 4No 900x1200mm,2No 2/900x1200mm U-culvert completed. |  |  |  | CR-AJU-C-022 |  | 167.8771 | 2014-07-07
38 | DFR | CENTRAL | AOB | DFR/CR/AOB/CFRIP/SI/4B/11 | Spot Imp. | Bibianiha - Yeboa F/R | 3.5 | Ebko-V Ltd. | COCOBOD/CFRIP | 2012-07-08 | 2012-09-27 | 81 | 2013-09-27 | 365 | 2013-09-27 | 6No 700x900mm,2No 900x1200mm,1No 2/1800x1800mm U-culvert completed | 224738.08 | 224738.08 | 170052.7 | 54685.38 | 75.6671 | 73 | Work in progress | Clearing and formation,6No 700x900mm,2No 900x1200mm U- culvert, 1No 2/1800x1800mm completed |  |  |  | Not Available |  | 177.5342 | 2014-07-07
39 | DFR | CENTRAL | Agona East | DFR/CR/AE/CFRIP/SI/5A/11 | Spot Imp. | Duoto - Kwasi Dadzie - Paintsil F/R | 5 | Walterduam Ent. Ltd. | COCOBOD/CFRIP | 2012-06-05 | 2012-10-18 | 135 | 2013-10-18 | 365 | 2013-10-18 | 7No 700x900mm,1No 900x1200mm U-culvert completed | 218000 | 218000 |  | 218000 | 0 | 50 | Work in progress | Clearing, formation, 7No 700x900mm,1No 900x1200mm U-culvert completed |  |  |  | CR-AJU-A-033 |  | 171.7808 | 2014-07-07
40 | DFR | CENTRAL | Assin North | DFR/CR/AS/CFRIP/SI/5B/11 | Spot Imp. | Odumasi - Wurakese Station | 4.7 | Hanimart Ventures | COCOBOD/CFRIP | 2012-06-05 | 2012-12-06 | 184 | 2013-12-06 | 365 | 2013-12-06 |  | 277513.29 | 277513.29 |  | 277513.29 | 0 | 10 | Work in progress | Clearing and formation completed. |  |  |  | CR-AGO-C-028/CR-AGO-A-027 |  | 158.3562 | 2014-07-07
41 | DFR | CENTRAL | AEE | DFR/CR/AEE/CFRIP/REH/6A/11 | Rehab. | Ofabil - Dominase F/R | 7.2 | Unkar Ltd | COCOBOD/CFRIP | 2012-06-05 | 2012-10-11 | 128 | 2013-10-11 | 365 | 2013-10-11 |  | 633393.26 | 633393.26 |  | 633393.26 | 0 | 2 | Work in progress | Clearing and formation completed. |  |  |  | CR-ASN-C-046 |  | 173.6986 | 2014-07-07
42 | DFR | CENTRAL | UDE | DFR/CR/UDE/CFRIP/SI/6B/11 | Spot Imp. | Praprababida - Buabin Camp F/R | 5.2 | Alt Const. Ltd. | COCOBOD/CFRIP | 2012-06-05 | 2012-10-03 | 120 | 2013-10-03 | 365 | 2013-10-03 | 2No 700x900mm, U-culvert completed | 271201.84 | 271201.84 |  | 271201.84 | 0 | 25 | Work in progress | Clearing, 2No 700x900mm completed. |  |  |  | CR-MFA-I-027 |  | 175.8904 | 2014-07-07
43 | DFR | CENTRAL | UDE | DFR/CR/UDE/CFRIP/SI/7A/11 | Spot Imp. | Amoafo - Akyenekrom - Zion № 2 | 8.2 | Tiboura-Taa Ent. Ltd. | COCOBOD/CFRIP | 2012-06-07 | 2012-10-03 | 118 | 2013-10-03 | 365 | 2013-10-03 |  | 247191.18 | 247191.18 | 28092.65 | 219098.53 | 11.3647 |  | Work in progress | Clearing and formation completed |  |  |  | CR-UED-A-063 |  | 175.8904 | 2014-07-07
44 | DFR | CENTRAL | UDE | DFR/CR/UDE/CFRIP/REH/7B/11 | Rehab. | Buabin - Adjoma F/R | 4.2 | Ariyan Ltd. | COCOBOD/CFRIP | 2012-08-08 | 2012-10-03 | 56 | 2013-10-03 | 365 | 2013-10-03 |  | 473041.15 | 473041.15 | 36639.17 | 436401.98 | 9 | 9 | Work in progress | Clearing and formation completed |  |  |  | CR-UED-A-054 |  | 175.8904 | 2014-07-07
45 | DFR | CENTRAL | Assin South | DFR/CR/AS/CFRIP/REH/8A/11 | Rehab. | Adiembra - Gyahadze F/R | 5.1 | Property Dev. /Bus. Inv. Ltd. | COCOBOD/CFRIP | 2012-08-08 | 2012-11-29 | 113 | 2013-11-28 | 321 | 2013-10-16 | 1No 700x900mm,3No 900x1200mm U-culvert ,300m of 450x450x120mm Conc U-drains completed | 453322.83 | 453322.83 | 136786.59 | 316536.24 | 33.59 | 50 | Work in progress | Clearing ,shaping & V-shaped drain,1№ 700x900mm, 3No 900x1200mm U-culvert, 300m 450x450x120mm U-drain,sub-base ,base and primerseal completed |  |  |  | CR-UED-A-026 |  | 182.243 | 2014-07-07
46 | DFR | CENTRAL | AOB | DFR/CR/AOB/CFRIP/SI/8B/11 | Spot Imp. | Odoben - Nsutem F/R | 13.5 | Francobex Co. Ltd. | COCOBOD/CFRIP | 2012-08-08 | 2012-09-27 | 50 | 2013-09-27 | 365 | 2013-09-27 | 2No 700x900mm,1No 1200x1800mm U-culvert completed | 333155.02 | 333155.02 | 98966.98 | 234188.04 | 35.17 | 15.99 | Work in progress | Clearing, 2No 700x900mm,1No 1200x1800mm U-culvert completed. |  |  |  | CR-ASS-A-043 |  | 177.5342 | 2014-07-07
47 | DFR | CENTRAL | UDE | DFR/CR/UDE/CFRIP/SI/9A/11 | Spot Imp. | Kona - Adadekofi | 4.75 | Osei Apeani Co. Ltd. | COCOBOD/CFRIP | 2012-06-05 | [6 empty] | 294382.9 | 294382.9 | 33871.54 | 260511.36 | 11.5059 | 10 | Work in progress | Clearing and formation completed |  |  |  | CR-ASI-A-024 |  | #DIV/0! | 2014-07-07
48 | DFR | CENTRAL | Assin North | DFR/CR/AN/CFRIP/SI/9B/11 | Spot Imp. | Gold Coast Camp - Wawase F/R | 9.2 | Ruthra Const. Ltd. | COCOBOD/CFRIP | 2012-08-08 | 2012-10-12 | 65 | 2013-10-14 | 367 | 2013-10-14 | 8No 700x900mm,1No 900x1200mm,1No 1250x1800mm U-culvert completed | 398414.08 | 398414.08 | 141139.74 | 257274.34 | 39.37 | 35.38 | Work in progress | Clearing and formation,8No 700x900mm,1No 900x1200mm, 1No 1250x1800mm U- culvert completed |  |  |  | CR-UED-I-046 |  | 172.4796 | 2014-07-07
49 | DFR | CENTRAL | AOB | DFR/CR/AOB/CFRIP/SI/10A/11 | Rehab. | Tumsiase Jn - Tumsiase | 2.4 | Nanahene Inv. Ltd, | COCOBOD/CFRIP | 2012-08-08 | 2012-12-14 | 128 | 2013-12-13 | 364 | 2013-12-13 | 6No 700x900mm,3No 900x1200mm,1No 1800x1800mm U-culvert completed | 378253.18 | 378253.18 | 341174.04 | 37079.14 | 90.1973 | 85 | Work in progress | Clearing and formation, 6No 700x900mm, 3No 900x1200mm, 1No 1800x1800mm U culvert,238m of 450x450x120mm Concrete U drains,10,901cu.m cutting and 6.5km of sub-base and 0.8km of base completed |  |  |  | CR-ASN-C-020/19 | 1 | 156.5934 | 2014-07-07
50 | DFR | CENTRAL | THLD | DFR/CR/THLD/CFRIP/SI/10B/11 | Spot Imp. | Apenkro - Asensoho-Shed | 6.5 | Insaan Gh Ltd. | COCOBOD/CFRIP | 2012-08-08 | 2012-10-10 | 63 | 2013-10-10 | 365 | 2013-10-10 | 3No 700x900mm,9No 900x1200mm U-culvert completed | 339778.6 | 339778.6 | 112563.18 | 227215.42 | 33.1284 | 40 | Work in progress | Clearing ,formation,3No 700x900mm, 9No 900x1200mm U- culvert completed. |  |  |  | Not Available |  | 173.9726 | 2014-07-07
51 | DFR | CENTRAL | THLD | DFR/CR/THLD/CFRIP/SI/11A/11 | Spot Imp. | Paaso - Nyamebekyere F/R | 6.6 | Teranisa Co. Ltd. | COCOBOD/CFRIP | 2012-08-08 | 2012-10-10 | 63 | 2013-10-10 | 365 | 2013-10-10 | 2No 700x900mm,7No 900x1200mm, 2No 1200x1200mm and 1No 2/1800x1800mm U-culvert completed | 384825.58 | 384825.58 | 224511.63 | 160313.95 | 60 | 54 | Work in progress | Clearing and formation completed, 2No 700x900mm, 7No 900x1200mm, 2No 1200x1200mm and 1No 2/1800x1800mm U culvert, Clearing, 150m of 450x450x120mm Conc U-drains & 100m of 600x600x150mm Conc U-drains completed |  |  |  | CR-LDE-A-059 |  | 173.9726 | 2014-07-07
52 | DFR | CENTRAL | AEE | DFR/CR/AEE/CFRIP/REH/11B/11 | Rehab. | Badukrom - Ofabil F/R | 4.2 | Abdul-Rahman & Sons Ltd. | COCOBOD/CFRIP | 2012-08-08 | 2012-10-11 | 64 | 2013-10-11 | 365 | 2013-10-11 | 1445m of 450x450x150mm Conc U-drains completed, 24m of 600x600x150mm Conc U-drains completed | 672477.15 | 672477.15 | 431483.91 | 240993.24 | 66.3 | 80 | Work in progress | Clearing and formation completed, 1445m of 450x450x150mm Conc U-drains completed, 24m of 600x600x150mm Conc U-drains completed |  |  |  | CR-LDE-C-053 |  | 173.6986 | 2014-07-07
53 | DFR | CENTRAL | Assin South | DFR/CR/AS/CFRIP/SI/12B/11 | Spot Imp. | Adiembra - Nuanua F/R | 13.6 | Gudmann Int. Ltd. | COCOBOD/CFRIP | 2012-06-05 | 2012-10-03 | 120 | 2013-10-03 | 365 | 2013-10-03 |  | 373746.28 | 373746.28 | 43912.04 | 329834.24 | 11.7492 | 10 | Possesion of site given | Clearing and formation completed. |  |  |  | CR-AJU-C-017 | 2 | 175.8904 | 2014-07-07
54 | DFR | CENTRAL | Agona East | DFR/CR/AE/CFRIP/SI/12A/11 | Spot Imp. | Nantifa - Tawora | 4 | Balmoral Co. Ltd. | COCOBOD/CFRIP | 2012-06-05 | [6 empty] | 197510.08 | 197510.08 |  | 197510.08 | 0 |  | Possesion of site given |  |  |  |  | CR-ASS-I-036 |  | #DIV/0! | 2014-07-07
DUTCH/GOG
55 | DFR | CENTRAL | Gomoa West | DFR/CR/BRG/GOG/2006/50 | Bridge Construction | Steel Bridge on River Naakwa-Otchi on Ajumako-Abeadzi-Gomoa | _ | Comfort Plaza Ltd. | DUTCH/GOG | 2007-03-01 | 2007-06-01 | 92 | 2008-05-31 | 365 | 2008-05-31 | _ | 457656.61 | 457656.61 | 108901.12 | 348755.49 | 23.7954 | 63.54 | Project Terminated on 20/04/11. Final account on 11/03/13 | _ |  | _ | 2
56 | DFR | CENTRAL | Assin North | DFR/CR/BRG/DUTCH/2005/32 | Bridge Construction | Steel Bridge on River Asunsu on Krofofordo Jn-Krofofordo and River Nuanua on Nuanua-Bunso | _ | David Walter Ltd. | DUTCH/GOG | 2005-11-16 | 2006-01-09 | 54 | 2007-05-08 | 484 | 2007-05-08 | Steel Components lunched. | 612511.672 | 612511.672 | 327373.74 | 285137.932 | 53.4478 | 95 | Project Terminated on 13/03/12 | Abutment walls complete.Road approaches partially filled.Steel Components lunched. |  | CR-ASS-A-025 | 5 | 640.7025 | 2014-07-07
57 | DFR | CENTRAL | Assin South | DFR/CR/BRG/DUTCH/2005/02 | Bridge Construction | Steel Bridge on River Ochi on Assin Dawumako Jn-Assin Dawumako | _ | G.K. Appiah & Sons Ltd. | DUTCH/GOG | 2005-03-16 | 2006-04-13 | 393 | 2006-12-04 | 1782 | 2011-02-28 | Steel members lunched | 343552.21 | 343552.21 | 276965.56 | 0 | 80.6182 | 100 | Work completed. 50% of retention released on 14/12/11 | Steel members lunched |  | _ | 5 |  | 2014-07-07
58 | DFR | CENTRAL | THLD | DFR/CR/BRG/DUTCH/08/83 | Bridge Construction | Steel Bridge on Dorkodoko-Otukrom F/R | _ | M. Isumail Ltd. | DUTCH/GOG | 2008-12-22 | 2009-04-01 | 100 | 2010-03-31 | 927 | 2011-10-15 | Abutment walls completed and bridge lunched | 794487.36 | 794487.36 | 595830.19 | 0 | 74.9956 | 100 | Final Retention Released on 20/03/14 | Abutment walls,Road approaches completed and bridge lunched |  | _ | 6 |  | 2014-07-07
59 | DFR | CENTRAL | Assin South | DFR/CR/BRG/DUTCH/08/80 | Bridge Construction | Steel Bridge on Tehente-Tehente Jn F/R | _ | M.W. Co Ltd. | DUTCH/GOG | 2008-12-22 | 2009-03-18 | 86 | 2010-03-17 | 865 | 2011-07-31 | Steel members lunched,3№ 700x900mm,1№ 900x1200mm U-culvert completed | 922224 | 1779154.6 | 719432.59 | 1059722.01 | 40.74 | 40.48 | Work in progress | Steel members lunched,3№ 700x900mm,1№ 900x1200mm U-culvert completed |  | _ | 7 |  | 2014-07-07
60 | DFR | CENTRAL | UDE | DFR/CR/BRG/DUTCH/08/81 | Bridge Construction | Steel Bridge on Dunkwa-Nkottomso Jn F/R | _ | Dangiba Co. Ltd. | DUTCH/GOG | 2008-12-22 | 2009-03-19 | 87 | 2010-03-18 | 553 | 2010-09-23 | 1№ 900X1200mm U-Culvert,abutment wall and lynching completed. | 788725.5 | 788725.5 | 620694.82 | 0 | 78.6959 | 100 | Project completed on 16/05/11 | Main structure of the site office,1№ 900X1200mm U-Culvert,abutment wall and lynching completed. |  | CR-UED-C-001 | 2 | 350.0904 | 2014-07-07
61 | DFR | CENTRAL | Agona East | DFR/DUTCH/CR/LOT.82/08 | Bridge Construction | Steel Bridge on Agona Nsaba-Agona Nkran Jn F/R | _ | Old Days Co. Ltd. | DUTCH/GOG | 2008-12-22 | 2009-09-18 | 270 | 2010-09-17 | 1383 | 2013-07-02 | 2№ Relief Culverts,2№ 1800x1800mm U-culvert and lynching completed. | 977334.6 | 1695020.06 | 1125886.74 | 24433.12 | 66.4232 | 70.98 | Work in progress | Clearing,demolition,2№ Abuttment to launching level and 2№ Relief Culverts,2№ 1800x1800mm U-culvert and lynching completed. |  | _ | 2 | 126.7534 | 2014-07-07
CONSOLIDATED FUND
62 | DFR | CENTRAL | Assin North | DFR/CR/SURF/HIPC/08/1 | Surfacing | Asempaneye-Kushea PH 1 | 5 | Joe Azar Co. Ltd. | Consolidated Fund | 2008-11-28 | 2009-01-19 | 52 | 2010-01-19 | 1045 | 2011-11-30 | 1,120m 450x450x120mm U-drain completed | 758413.24 | 758413.24 | 790986.42 | 0 | 104.2949 | 100 | Work completed. 50% of Retention released on 25/06/12 | Clearing,1,120m 450x450x120mm U-drain,5.0km sub-base ,base,primerseal & seal completed |  | CR-ASN-A-001 | 2 |  | 2014-07-07
63 | DFR | CENTRAL | Assin North | DFR/CR/SURF/HIPC/08/2 | Surfacing | Asempaneye-Kushea PH 2 | 5 | Honia - As Gh. Ltd. | Consolidated Fund | 2008-11-28 | 2009-03-05 | 97 | 2010-03-05 | 365 | 2010-03-05 | 444m of 450x450x120mm U-drain,2№ 1250x1800mm U-culvert,100m Conc. Kerbs completed | 710968.82 | 710968.82 | 367497.37 | 343471.45 | 51.6897 | 60 | Project Terminated on 12/07/11. | Clearing,444m of 450x450x120mm U-drain,2№ 1250x1800mm U-culvert,100m Conc. Kerbs,5.0km of sub-base,4.5km base and 2.0km primer seal completed. |  | CR-ASN-A-001 | 1 |  | 2014-07-07
64 | DFR | CENTRAL | Assin North | DFR/CR/SURF/HIPC/08/3 | Surfacing | Asempaneye-Kushea PH 3 | 6.5 | Memphis Metro. Ltd. | Consolidated Fund | 2008-11-28 | 2009-06-02 | 186 | 2010-06-02 | 779 | 2011-07-21 | 8№ 700x900mm,1№ 900x1200mm U-culvert,90m 600x600x150mm and 3857m 450x450x120mm U-drain,42m 1200x200mm Retaining Wall completed | 1170783.4 | 1345348.63 | 2802428.87 | 0 | 208.305 | 100 | Final Retension released on 1st November, 2013 | 8№ 700x900mm,1№ 900x1200mm U-culvert,90m 600x600x150mm and 3857m 450x450x120mm U-drain,42m 1200x200mm Retaining Wall,6.5km sub-base,base,primer seal & seal completed. |  | CR-ASN-A-001 | 1 | 238.896 | 2014-07-07
65 | DFR | CENTRAL | Gomoa West | DFR/CR/GW/SURF/GOG/1/12 | Surfacing | Kyiren Nkwanta Jn - Mando | 15 | GKL Ltd. | Consolidated Fund | 2012-11-22 | 2013-01-23 | 62 | 2014-01-23 | 546 | 2014-07-23 |  | 4967358.12 | 4967358.12 | 621294.77 | 4346063.35 | 12.5075 |  | Possesion of site given |  |  | CR-GOM-I-035 |  | 97.0696 | 2014-07-07
66 | DFR | CENTRAL | Agona East | DFR/CR/AE/SURF/GOG/2/12 | Surfacing | Duakwa - Akwakwa | 10 | Gen. Const. & Dev. Ltd. | Consolidated Fund | 2012-11-22 | 2013-02-13 | 83 | 2014-03-13 | 393 | 2014-03-13 | 3№ 700x900mm,14№ 900x1200mm,1№ 1250x1800mm U-culvert and 3,100m 450x450x120mm U-drain completed | 4265673.8 | 4265673.8 | 885318.55 | 3380355.25 | 20.7545 | 40 | work in progress | Clearing,3№ 700x900mm,14№ 900x1200mm,1№ 1250x1800mm U-culvert and 3,100m 450x450x120mm U-drain, sub base and base, 4.5km of primer seal completed |  | CR-AGO-I-007 |  | 129.5165 | 2014-07-07
IDA/TSP
66 | DFR | CENTRAL | THLD | DFR/CR/THLD/IDA/TSP/NCB/W-4/SI/LOT 2/2011 | Rehabilitation | Wamaso - Aquakrom | 0.6 | Asmariate Ent. Ltd. | IDA/TSP | 2011-03-16 | 2011-05-18 | 63 | 2011-11-18 | 352 | 2012-05-04 | 1№ 900X1200mm,3№ 700X900mm completed. | 120001.7 | 120001.7 | 105694.99 | 0 | 88.0779 | 100 | Work completed. Final of retention released on 24/5/13 | Clearing,formation,1№ 900X1200mm,3№ 700X900mm and sub-base completed. |  | CR-LDE-A-040 |  | 325.5682 | 2014-07-07
67 | DFR | CENTRAL | THLD | DFR/CR/THLD/IDA/TSP/NCB/W-4/SI/LOT 3/2011 | Spot Improvement | Kwame Alert Jn - Kwame Alert - Amuza | 3.7 | Asti Agencies Ltd. | IDA/TSP | 2011-03-16 | 2011-05-26 | 71 | 2011-11-26 | 228 | 2012-01-09 | 7№ 700X900mm completed. | 172987.32 | 172987.32 | 153928.62 | 0 | 88.9826 | 100 | Work completed | Clearing,Formation, 7№ 700X900mm and sub-base completed. |  | CR-LDE-A-050 |  | 499.1228 | 2014-07-07
68 | DFR | CENTRAL | Gomoa West | DFR/CR/GW/IDA/TSP/NCB/W-4/SI/LOT 6/2011 | Spot Improvement | Simpa - Ohuam | 4.2 | Bo Const. Ent. Ltd. | IDA/TSP | 2011-03-16 | 2011-04-19 | 34 | 2011-10-19 | 257 | 2012-01-01 | 7№ 700x900mm completed. | 148733.77 | 148733.77 | 130164.08 | 0 | 87.5148 | 100 | Work completed. Final of retention released on 18/12/13 | Clearing , formation,7№ 700x900mm completed. |  | CR-GOM-C-031 |  | 457.1984 | 2014-07-07
69 | DFR | CENTRAL | Agona East | DFR/CR/AE/IDA/TSP/NCB/W-4/SI/LOT 7/2011 | Spot Improvement | Kwanyako - Namawora | 4 | T&A Everest Co. Ltd. | IDA/TSP | 2011-03-16 | 2011-05-24 | 69 | 2011-11-24 | 184 | 2011-11-24 | 2№ 700X900mm,1№ 900X1200mm,2№ 1250X1800mm completed. | 161225.26 | 161225.26 | 142716.57 | 0 | 100 | 100 | Works completed. Half retention released on 17/12/13 | Clearing,formation,2№ 700X900mm,1№ 900X1200mm,2№ 1250X1800mm completed. |  | CR-GOM-I-047 |  | 619.5652 | 2014-07-07
70 | DFR | CENTRAL | AEE | DFR/CR/AEE/IDA/TSP/NCB/W-4/SI/LOT 8/2011 | Spot Improvement | Abowinim - Nkodwo | 4 | Abdul-Rahman & Sons Ltd. | IDA/TSP | 2011-03-16 | 2011-05-19 | 64 | 2011-11-21 | 384 | 2012-06-06 | 7№ 700x900mm completed. | 181648.04 | 181648.04 | 150855.62 | 0 | 83.0483 | 100 | Work completed. Final of retention released on 26/7/13 | Clearing,formation & 7№ 700x900mm completed. |  | CR-AJU-A-032 |  | 298.1771 | 2014-07-07
71 | DFR | CENTRAL | Awutu Senya | DFR/CR/AWS/IDA/TSP/NCB/W-4/SI/LOT 9/2011 | Spot Improvement | Mayenda - Obodakaba | 3.2 | Tamlana-Tega Ent. | IDA/TSP | 2011-03-16 | 2011-05-18 | 63 | 2011-11-18 | 276 | 2012-02-18 | 2№ 700x900mm,600m 450x450x120mm Concrete U drains completed. | 150531.58 | 150531.58 | 161334.97 | 0 | 107.1768 | 100 | Work completed. 50% of retention released on 14/05/13 | Clearing,2№ 700x900mm,600m 450x450x120mm Concrete U drains,0.22km sub-base completed. |  | CR-AES-A-019 |  | 415.2174 | 2014-07-07
72 | DFR | CENTRAL | Mfantsiman | DFR/CR/MFA/IDA/TSP/NCB/W-4/SI/LOT 11/2011 | Spot Improvement | Akotsi - Ekroful | 5 | Jonokie Ltd. | IDA/TSP | 2011-03-16 | 2011-07-22 | 128 | 2012-02-22 | 215 | 2012-02-22 | 2№ 700x900mm, 1№ 900x1200mm, 1.8km sub-base completed. | 196767.51 | 196767.51 | 152036.77 | 0 | 77.2672 | 100 | Work completed | Clearing,formation,2№ 700x900mm, 1№ 900x1200mm, 1.8km sub-base completed. |  | CR-MFA-C-009 |  | 502.7907 | 2014-07-07
73 | DFR | CENTRAL | THLD | DFR/CR/THLD/IDA/TSP/NCB/W-4/SI/LOT 1/2011 | Spot Improvement | Mfuom - Apokwaa - Onomakwa | 6 | Cindsarrah Ltd. | IDA/TSP | 2011-03-16 | 2011-04-26 | 41 | 2011-11-28 | 337 | 2012-03-28 | 6№ 700x900mm,3№ 900X1200mm,2№ 1800X1800mm completed. | 223162.64 | 223162.64 | 208919.21 | 0 | 93.6175 | 100 | Works completed. Final retention released on 20/02/14 | Clearing, formation,6№ 700x900mm,3№ 900X1200mm,2№ 1800X1800mm completed. |  | CR-LDE-A-063 |  | 346.5875 | 2014-07-07
74 | DFR | CENTRAL | UDE | DFR/CR/UDE/IDA/TSP/NCB/W-4/SI/LOT 10/2011 | Spot Improvement | Ntonton - Kona | 5 | Awally Complex Ltd. | IDA/TSP | 2011-03-16 | 2011-04-26 | 41 | 2011-11-28 | 275 | 2012-01-26 | 4№ 700X900mm,1№ 900X1200mm,1№ 1200X1200mm,1№ 1250X1800mm completed. | 210514.14 | 210514.14 | 190991.12 | 0 | 90.726 | 100 | Final Retension released on 31st October, 2013 | Clearing and formation,4№ 700X900mm,1№ 900X1200mm,1№ 1200X1200mm,1№ 1250X1800mm completed. |  | CR-UED-C-062 |  | 424.7273 | 2014-07-07
75 | DFR | CENTRAL | Assin North | DFR/CR/AN/IDA/TSP/NCB/W-4/SI/LOT 13/2011 | Spot Improvement | Senchiem - Agave | 4 | J. O. Awuah & Brothers Ltd. | IDA/TSP | 2011-03-16 | 2011-04-28 | 43 | 2011-11-28 | 335 | 2012-03-28 | 7№ 700X900mm & 6№ 900X1200mm completed. | 224861.99 | 224861.99 | 198586.54 | 0 | 84.62 | 100 | Works completed | Clearing, Formation ,7№ 700X900mm & 6№ 900X1200mm completed. |  | Not Available | 3 | 348.0597 | 2014-07-07
76 | DFR | CENTRAL | Assin South | DFR/CR/AS/IDA/TSP/NCB/W-4/SI/LOT 12/2011 | Spot Improvement | Nsuta - Bepokokoo | 6.7 | Pee-Wuud Const. Ltd. | IDA/TSP | 2011-03-16 | 2011-05-30 | 75 | 2011-12-30 | 214 | 2011-12-30 | 2№ 700X900mm and 8№ 900X1200mm completed. | 217558.04 | 217558.04 | 198471.69 | 0 | 91.227 | 100 | Work completed. Final of retention released on 28/7/13 | Clearing,formation,2№ 700X900mm and 8№ 900X1200mm completed. |  | CR-ASS-C-050 |  | 529.9065 | 2014-07-07
77 | DFR | CENTRAL | AAK | DFR/CR/AAK/IDA/TSP/NCB/W-4/SI/LOT 4/2011 | Spot Improvement | Tayedo - Afonakrom - Dadagua | 9.3 | Samwilco Const. Ltd. | IDA/TSP | 2011-03-16 | 2011-05-11 | 56 | 2011-11-28 | 201 | 2011-11-28 | 2№ 700X900mm,595m 450x450x120mm Concrete U drains completed | 230074.83 | 230074.83 | 175973.74 | 0 | 76.4854 | 100 | Final Retention Released on 25/03/14 | Clearing and formation,2№ 700X900mm,595m 450x450x120mm Concrete U drains,2.2km sub-base completed |  | CR-MFA-I-037 |  | 573.6318 | 2014-07-07
78 | DFR | CENTRAL | THLD | DFR/CR/THLD/IDA/TSP/NCB/W-4/SI/LOT 4/2011 | Rehabilitation | Jukwa - Krobo | 7 | Ceco Eng. Ltd. | IDA/TSP | 2011-03-16 | 2011-05-19 | 64 | 2011-12-19 | 305 | 2012-03-19 | 13№ 700X900mm and 2№ 900X1200mm completed. | 247006.92 | 247006.92 | 216880.54 | 0 | 87.8034 | 100 | Final Retention Released on 23/06/2014 | Clearing,formation,13№ 700X900mm and 2№ 900X1200mm completed. |  | CR-LDE-A-074 |  | 375.4098 | 2014-07-07
79 | DFR | CENTRAL | Awutu Senya | DFR/CR/IDA/TSP/NCB/W-4/SURF/LOT 1/2013 | Surfacing | Sankor-Kweikrom-Ojobi-Akoti | 5 | Soro Const. Ltd. | IDA/TSP | 2012-11-22 | [6 empty] | 2147734.2 | 2147734.2 |  |  |  |  | Possesion of site given. Advanced Mobilization Loan Guaranteed
80 | DFR | CENTRAL | Awutu Senya | DFR/CR/IDA/TSP/NCB/W-4/REH/LOT 2/2012 | Rehabilitation | Bawjiase-Aponkye Akura | 6.9 | Shamma Rohi Ltd. | IDA/TSP | 2013-02-12 | [6 empty] | 550994.9 | 550994.9 |  |  |  |  | Possesion of site given. Advanced Mobilization Loan Guaranteed
81 | DFR | CENTRAL | Awutu Senya | DFR/CR/IDA/TSP/NCB/W-4/REH/LOT 3/2012 | Rehabilitation | Bawjiase-Ayensu Ako | 5.3 | Taboura-Taa Ent. Ltd. | IDA/TSP | 2013-02-12 | [6 empty] | 564624.09 | 564624.09 |  |  |  |  | Possesion of site given
82 | DFR | CENTRAL | Awutu Senya | DFR/CR/IDA/TSP/NCB/W-4/REH/LOT 4/2012 | Rehabilitation | Bawjiase-Amontrom (Congo)-Tetteykura | 3.25 | Skarom Eng. Ltd. | IDA/TSP | 2013-02-12 | [6 empty] | 381696.2 | 381696.2 |  |  |  |  | Possesion of site given
83 | DFR | CENTRAL | Awutu Senya | DFR/CR/IDA/TSP/NCB/W-4/REH/LOT 5/2012 | Rehabilitation | Ahentia-Busumabra Jtn-Kweikrom | 6 | Abdul-Rahman & Sons Ltd. | IDA/TSP | 2013-02-12 | [6 empty] | 515720.22 | 515720.22 |  |  |  |  | Possesion of site given. Advanced Mobilization Loan Guaranteed
84 | DFR | CENTRAL | Awutu Senya | DFR/CR/IDA/TSP/NCB/W-4/SI/LOT 6/2012 | Spot Improvement | Adawukwa-Ofadjator-Honi | 3.45 | Paabadu Const. Ltd. | IDA/TSP | 2013-02-12 | [6 empty] | 456254.91 | 456254.91 |  |  |  |  | Possesion of site given
85 | DFR | CENTRAL | Awutu Senya | DFR/CR/IDA/TSP/NCB/W-4/REH/LOT 7/2012 | Rehabilitation | Bewuanum-Adawukwa | 9.95 | Minak Investment Ltd. | IDA/TSP | 2013-02-12 | [6 empty] | 620525.89 | 620525.89 |  |  |  | 20 | Work in progress | Clearing completed, Formation works underway
86 | DFR | CENTRAL | Awutu Senya | DFR/CR/IDA/TSP/NCB/W-4/SURF/LOT 8/2012 | Surfacing | Bontrase-Desum | 4.7 | Memphis Metro. Ltd. | IDA/TSP | 2013-02-12 | [6 empty] | 1273569.82 | 1273569.82 |  |  |  |  | Possesion of site given
87 | DFR | CENTRAL | Awutu Senya | DFR/CR/IDA/TSP/NCB/W-4/REH/LOT 9/2012 | Rehabilitation | Papaase No.1-Odotom | 9.4 | Alt Const. Ltd. | IDA/TSP | 2013-02-12 | [6 empty] | 477155.5 | 477155.5 |  |  |  |  | Possesion of site given
88 | DFR | CENTRAL | Awutu Senya | DFR/CR/IDA/TSP/NCB/W-4/REH/LOT 10/2012 | Rehabilitation | Kwao Bondze-Larbie-Jei Krodua | 3.55 | Lovemak Ventures Ltd. | IDA/TSP | 2013-02-12 | [6 empty] | 562912.67 | 562912.67 |  |  |  |  | Possesion of site given
ROAD FUND/LABOUR BASED
89 | DFR | CENTRAL | Assin South | DFR/CR/AS/RF/LB/LOT 14/10 | Rehabilitation | Mankata Jn. - Mankata | 10.7 | Johaze Ltd. | Road Fund | 2011-02-10 | 2011-03-18 | 36 | 2012-03-18 | 580 | 2012-10-18 |  | 635630.44 | 635630.44 | 132463.5 | 503166.94 | 20.8397 | 25 | Slow progress. Third Warning letter given on 2/10/12 | Clearing,formation Completed |  | CR-ASS-A-037 |  | 208.1034 | 2014-07-07
90 | DFR | CENTRAL | AEE | DFR/CR/AEE/RF/LB/LOT 15/10 | Spot Improvement | Abaasa – Onyandze – Kokodo – Engo | 7.1 | Antelli Agricon Ltd. | Road Fund | 2011-02-10 | 2011-03-09 | 27 | 2012-01-09 | 306 | 2012-01-09 | 10№ 700x900mm 'U' culverts completed. | 516703.36 | 516703.36 | 122149.9 | 394553.46 | 23.6402 | 40 | Slow progress.Final Warning letter given on 17/7/12 | Clearing, 2.0km of ditching and camber,10№ 700x900mm 'U' culverts completed. |  | CR-AJU-C-029 CR-MFA-C-016 |  | 397.3856 | 2014-07-07
91 | DFR | CENTRAL | Assin North | DFR/CR/AN/RF/LB/LOT 17/10 | Spot Improvement | Essiam – Kyeikrom – Adukweku | 6.7 | Yadovic Ltd. | Road Fund | 2011-02-10 | 2011-05-23 | 102 | 2012-01-23 | 245 | 2012-01-23 | 9№ 700X900mm,3№ 900X1200mm completed | 395917.16 | 395917.16 | 350579.87 | 0 | 80.07 | 100 | Work completed. 50% of retention released on 22/04/14 | Clearing, formation, 9№ 700X900mm,3№ 900X1200mm completed . |  | CR-ASN-A-011 |  | 465.7143 | 2014-07-07
ROAD FUND
92 | DFR | CENTRAL | Assin North | DFR/CR/SURF/IDA/2005/1 | Surfacing | Anwiasu-Abaase-Wawase | 6 | Abdelco Ltd. | Road Fund | 2006-12-18 | 2007-03-05 | 77 | 2008-02-20 | 352 | 2008-02-20 | 5№ 700x900mm,6№ 900x1200mm,2№ 2/900x1200mm,1№ 3/2x2m and 1№ 2/3x2m R.B.C. completed. | 516682.7 | 516682.7 | 285232.67 | 231450.03 | 55.2046 | 45 | Slow progress.Third Warning letter given on 22/5/09 | Clearing, 5№ 700x900mm,6№ 900x1200mm,2№ 2/900x1200mm,1№ 3/2x2m and 1№ 2/3x2m R.B.C. completed. |  | CR-ASN-C-004 | 3 | 761.6477 | 2014-07-07
93 | DFR | CENTRAL | Mfantsiman | DFR/CR/SUR/GOG/07/1 | Surfacing | Mankessim Town Roads | 4.6 | Konadu Yiadom Construction Ltd. | Road Fund | 2007-10-16 | 2007-12-11 | 56 | 2011-10-11 | 1400 | 2011-10-11 | 2,931m Conc. 0.3x0.3x0.1m "U" Drains, 6,048 m Conc. 0.45x0.45x0.12m "U" Drains, 1№ 2/900X1200mm,4№ 900X1200mm,6№ 700X900mm U-Culvert Completed. | 1114698.12 | 1114698.12 | 903915.83 | 210782.29 | 81.0906 | 95 | Substantially completed | 2,931m Conc. 0.3x0.3x0.1m "U" Drains, 6,048 m Conc. 0.45x0.45x0.12m "U" Drains, 1№ 2/900X1200mm,4№ 900X1200mm,6№ 700X900mm U-Culvert,4.8km sub-base and base,4.8km of primer seal & seal Completed. |  | Not Available | 7 | 171.4286 | 2014-07-07
94 | DFR | CENTRAL | AAK | DFR/CR/SP IMP/PQ/2007/11 | Spot Improvement | Nenyimaaye Jn-Nenyimaaye | 1.45 | Alhaji Dauda & Sons Const. | Road Fund | 2007-07-19 | 2008-03-10 | 235 | 2008-09-10 | 184 | 2008-09-10 | _ | 49627 | 49627 | 0 | 49627 | 0 | 0 | Recommended for termination to Head office on 10/5/08 | _ |  | _ | _ | 1255.4348 | 2014-07-07
95 | DFR | CENTRAL | Mfantsiman | DFR/CR/SURF/GOG/07/2 | Surfacing | Saltpond Town Roads PH 2 & Mfantsiman Sec School | 7.67 | Joe Azar Co. Ltd. | Road Fund | 2007-10-29 | 2008-01-24 | 87 | 2009-07-24 | 1356 | 2011-10-11 | 7,537m of 0.45x0.45x0.12m Conc. "U" Drains,1№ 2/900x1200mm & 9No culverts and 3,949.9m of Conc. In-situ kerbs, 59.3m of Retaining wall Completed. | 1752683.59 | 2637390.54 | 2637390.54 | 0 | 100 | 100 | Work completed with interest on delayed payment. Rectangular storm drain under construction | 7,537m of 0.45x0.45x0.12m Conc. "U" Drains,1№ 2/900x1200mm & 9No culverts and 3,949.9m of Conc. In-situ kerbs, 59.3m of Retaining wall, 5.65km of sub-base and base,5.65km of primer seal &seal Completed. |  | Not Available | 5 | 173.7463 | 2014-07-07
96 | DFR | CENTRAL | THLD | DFR/CR/GOG/SI/PQ/08/10 | Spot Improvement | Twifo Praso – Bimponso (PhIV) | 3.75 | Batwack Ent. Ltd. | Road Fund | 2008-11-19 | 2008-12-10 | 21 | 2009-06-03 | 175 | 2009-06-03 | _ | 37923.5 | 37923.5 | 26523.16 | 11400.34 | 69.9386 | 83.37 | Recommended to RETC on Nov,10 | Clearing and Blading completed |  | _ | 1 | 1162.8571 | 2014-07-07
97 | DFR | CENTRAL | Agona East | DFR/CR/SI/GOG/PQ/08/2 | Spot Improvement | Seth Okai - Nsaba F/R PH 2 | 2.1 | Excelcon Ltd. | Road Fund | 2008-12-01 | 2009-01-28 | 58 | 2009-05-27 | 119 | 2009-05-27 | 1No 700x900 U-culverts completed | 46557.09 | 46557.09 | 0 | 46557.09 | 0 | 15 | Slow progress.Final Warning letter given on 19/11/09 | Clearing,1No 700x900 U-culverts completed |  | _ | _ | 1668.9076 | 2014-07-07
98 | DFR | CENTRAL | Agona East | DFR/CR/SI/GOG/PQ/08/3 | Spot Improvement | Seth Okai - Nsaba F/R PH 3 | 1.8 | Samoswag Ltd. | Road Fund | 2008-12-04 | 2009-02-09 | 67 | 2009-07-15 | 156 | 2009-07-15 | 4№700X900mm and 1№900X1200mm completed | 49523.31 | 49523.31 | 39070.37 | 10452.94 | 78.8929 | 98 | Substantially completed | Clearing,Formation,4№700X900mm and 1№900X1200mm completed |  | _ | 1 | 1265.3846 | 2014-07-07
99 | DFR | CENTRAL | Agona East | DFR/CR/SI/GOG/PQ/08/4 | Spot Improvement | Seth Okai - Nsaba F/R PH 4 | 2.4 | Pea - Ka Ltd. | Road Fund | 2008-12-01 | 2009-01-28 | 58 | 2009-05-27 | 119 | 2009-05-27 | _ | 47761.66 | 47761.66 | 0 | 47761.66 | 0 | 5 | Slow progress.Final Warning letter given on 19/11/09 | Clearing completed |  | _ | _ | 1668.9076 | 2014-07-07
100 | DFR | CENTRAL | Agona East | DFR/CR/SI/GOG/PQ/08/6 | Spot Improvement | Kwame Agyei - Ebamu - Nyakokwaa PH 2 | 3.95 | Joe Azar Co. Ltd. | Road Fund | 2008-12-01 | 2009-02-03 | 64 | 2009-06-09 | 126 | 2009-06-09 | _ | 49587.75 | 49587.75 | 0 | 49587.75 | 0 | 0 | Recommended for termination to Head office on 9/11/09 | _ |  | _ | _ | 1571.4286 | 2014-07-07
101 | DFR | CENTRAL | Agona East | DFR/CR/SI/GOG/PQ/08/7 | Spot Improvement | Kwame Agyei - Ebamu - Nyakokwaa PH 3 | 2.2 | Ewudzi Ventures | Road Fund | 2008-12-01 | 2009-02-03 | 64 | 2009-06-09 | 126 | 2009-06-09 | _ | 47897.24 | 47897.24 | 0 | 47897.24 | 0 | 0 | Recommended to DTC for termination of project on 28/7/10 | _ |  | _ | _ | 1571.4286 | 2014-07-07
102 | DFR | CENTRAL | Agona East | DFR/CR/SI/GOG/PQ/08/11 | Spot Improvement | Boferase - Kwesi Paintsil PH 4 | 1.2 | Rabin Ent. | Road Fund | 2008-12-01 | 2009-01-26 | 56 | 2009-05-25 | 119 | 2009-05-25 | 3No.700mm x900mm completed. | 48799.1 | 48799.1 | 28593.3 | 20205.8 | 58.5939 | 87.62 | Recommended for termination to Head Office on 8/02/11 | Clearing,formation and 3No.700mm x900mm completed. |  | _ | 1 | 1670.5882 | 2014-07-07
103 | DFR | CENTRAL | Awutu Senya | DFR/CR/REH./GOG/06/6 | Rehabilitation | Chapess-Mampong | 6.9 | Asabea Eng. Wks. Ltd. | Road Fund | 2006-12-18 | 2007-02-28 | 72 | 2007-12-28 | 303 | 2007-12-28 | 8No. 7x9 U-culvert,1No1.2x1.2 U-culvert ,2/1.2x1.2 U-culvert and 1No.1.25x1.8 U-culvert completed | 291598.5 | 291598.5 | 294817.72 | _ | 101.104 | 96 | Project substantially completed on 5/5/2008. | 5.31Ha cleared 8No. 7x9 U-culvert 1No1.2x1.2 U-culvert Double 1.2x1.2 U-culvert 1No.1.25x1.8 U-culvert |  | CR-GOM-A-037 | 3
104 | DFR | CENTRAL | Gomoa West | DFR/CR/MTCE/GOG/01 | Box Culvert Construction | Mumford-Whida | 5 | Sung Yeurang Ltd. | Road Fund | 2005-12-23 | 2006-04-11 | 109 | 2006-10-17 | 189 | 2006-10-17 | _ | 40029 | 40029 | 5458.5 | 34570.5 | 13.6364 | 10 | Recommended for termination to Head office on 4/2/08 | _ |  | CR-GOM-C-011 | 1 | 1592.0635 | 2014-07-07
105 | DFR | CENTRAL | THLD |  | Spot Improvement | Kwame Alert Jn - Kwame Alert - Amuza | 4 | Kobota Ent. | Road Fund | 2011-09-27 | 2011-12-01 | 65 | 2012-04-01 | 122 | 2012-04-01 |  | 32329.2 | 32329.2 |  | 32329.2 | 0 | 95 | Subtantially completed | 1№ 1800mm x1800mm completed. |  |  |  | 777.8689 | 2014-07-07
106 | DFR | CENTRAL | THLD |  | Spot Improvement | Paaso - Nyamebekyere | 3.5 | Insaan Gh Ltd. | Road Fund | 2012-12-21 | 2013-03-27 | 96 | 2013-07-27 | 122 | 2013-07-27 | 1№ 2/1800mm x1800mm completed. | 47591.64 | 47591.64 | 41924 | 5667.64 | 88.0911 | 88 | work in progress | 1№ 2/1800mm x1800mm completed. |  |  |  | 382.7869 | 2014-07-07
JICA/DCRIP
105 | DFR | CENTRAL | Agona East | DFR/CR/SURF/DCRIP/PH/08/34 | Surfacing | Agona Nsaba Town Roads | 2 | Gak Eng. Ltd. | JICA/DCRIP | 2008-12-24 | 2009-05-18 | 145 | 2010-05-17 | 592 | 2010-12-31 | 1592m of 450x450x120mm U-drain,2№ 700x900mm U-Culvert completed | 523193.85 | 523193.85 | 466855.75 | 0 | 89.2319 | 100 | Subtantially Completed | 1592m of 450x450x120mm U-drain,2№ 700x900mm U-Culvert, 2.0km of sub-base, base,primer seal & seal completed. |  | Not Available | 3
106 | DFR | CENTRAL | Assin North | DFR/CR/SURF/DCRIP/PH2/08/33 | Surfacing | Assin Fosu Town Roads | 2 | Core Const. Ltd. | JICA/DCRIP | 2008-12-29 | 2009-04-15 | 107 | 2010-03-15 | 334 | 2010-03-15 | 2565m of 450x450x120mm of U-drain,2№ 700x900mm U-Culvert completed. | 552834.62 | 552834.62 | 523736.57 | 0 | 94.7366 | 100 | Work completed.50% of Retention released | 2565m of 450x450x120mm of U-drain,2№ 700x900mm U-Culvert and 2.0km sub-base and base,2.0km primer seal and seal completed. |  | Not Available | 3
107 | DFR | CENTRAL | UDW | DFR/CR/SURF/DCRIP/PH2/08/33 | Surfacing | Diaso Town Roads | 2 | Core Const. Ltd. | JICA/DCRIP | 2008-12-29 | [5 empty] | 878m 450x450mm U-drain,4№ 900x1200mm U-Culvert Completed | 911213.1 | 911213.1 | 667207.81 | 244005.29 | 73.2219 | 40 | Work in Progress | 878m 450x450mm U-drain,4№ 900x1200mm U-Culvert completed. |  | Not Available | _ | #DIV/0! | 2014-07-07
108 | DFR | CENTRAL | THLD | DFR/CR/SURF/DCRIP/PH2/08/35 | Surfacing | Twifo Praso Town Roads PH 2 | 2 | Caks Ltd. | JICA/DCRIP | 2008-12-29 | 2009-05-18 | 140 | 2010-05-17 | 1326 | 2013-01-03 | 1142№ conc. Slabs,1№ 2/900x1200mm and 6№ 700x900mm U-culvert,1,533.9m 450x450x120 U-drain,640m of kerbs,258m of stone line drain completed. | 506872.94 | 506872.94 | 715440.35 | 0 | 141.1479 | 100 | Works completed. Final retention released on 27/01/14 | Clearing,1142№ conc. Slabs,1№ 2/900x1200mm and 6№ 700x900mm U-culvert,1,533.9m 450x450x120 U-drain,640m of kerbs,258m of stone line drain,sub-base,base and primer seal & seal completed. |  | Not Available | 7 | 141.4781 | 2014-07-07
109 | DFR | CENTRAL | Agona East | DFR/CR/SURF/DCRIP/09/09 | Surfacing | Swedru Town Roads | 2 | Pee-Wuud Const. Ltd. | JICA/DCRIP | 2010-06-25 | 2010-08-27 | 63 | 2011-08-27 | 365 | 2011-08-27 | 1,992m 450x450x120mm,128m 600x600x150mm,46m 900x900x150mm Conc U-drain,402m of kerbs completed. | 509308.35 | 509308.35 | 394877.21 | 114431.14 | 77.5321 | 85 | Slow progress.Second Warning letter given on 30/04/12 | Clearing,formation and 1,992m 450x450x120mm,128m 600x600x150mm,46m 900x900x150mm Conc U-drain,402m of kerbs,2.0km of sub-base, 1.6km of base & 2.0km primer seal completed. |  | Not Available | 4 | 386.3014 | 2014-07-07
ACROW/GOG
110 | DFR | CENTRAL | THLD | DFR/CR/ACROW/09/12 | Bridge Construction | Steel Bridge over River Aklakpa on Adugyaa - Kotokrom F/R | 20M | Jonokie Ltd. | ACROW/GOG | 2010-05-06 | 2011-04-28 | 357 | 2012-12-31 | 613 | 2012-12-31 | 4№ 900x1200mm U-culvert,2№ abutment completed. | 632419.04 | 632419.04 | 268119.72 | 364299.32 | 42.3959 | 36 | Work in Progress | Clearing,4№ 900x1200mm U-culvert ,2№ abutment completed. |  | - |  | 190.2121 | 2014-07-07
111 | DFR | CENTRAL | Cape Coast | DFR/CR/ACROW/09/13 | Bridge Construction | Steel Bridge over River Kakum on Anyinase - Dahia - Tsetsekasum F/R | 30M | Rinacand Co. Ltd. | ACROW/GOG | 2010-05-06 | 2010-07-30 | 85 | 2011-08-01 | 885 | 2012-12-31 | 2№ abutment completed. | 623982.56 | 623982.56 | 357205.06 | 266777.5 | 57.246 | 60 | Work in Progress | Clearing ,2№ abutment completed. |  | - |  | 162.4859 | 2014-07-07
112 | DFR | CENTRAL | Mfantsiman | DFR/CR/ACROW/09/14 | Bridge Construction | Steel Bridge over River Okyi on Eshiro Jn - Eshiro - Kwesigyan F/R | 20M | Memphis Metro. Ltd. | ACROW/GOG | 2010-05-06 | 2010-08-19 | 105 | 2012-10-04 | 865 | 2012-12-31 | 1№ 1800x2500mm,4№ 1250x1800mm,2№ 900x1200mm,1№ 700x900mm U-culvert,2№ abutment completed and bridge lunched | 659257.92 | 2202359.67 | 2202359.67 | 0 | 100 | 100 | Works completed with interest on delayed payment | 1№ 1800x2500mm,4№ 1250x1800mm,2№ 900x1200mm,1№ 700x900mm U-culvert,2№ abutment completed and bridge lunched |  | - | 3 | 163.9306 | 2014-07-07
113 | DFR | CENTRAL | UDW | DFR/CR/ACROW/09/15 | Bridge Construction | Steel Bridge over River Hurine on Nkwantanum - Asaman F/R | 20M | J. O. Awuah & Brothers Ltd. | ACROW/GOG | 2010-05-06 | 2011-04-28 | 357 | 2012-12-31 | 613 | 2012-12-31 | - | 556969.59 | 556969.59 | 239305 | 317664.59 | 42.9655 | 43 | Slow Progress | Clearing completed, Bridge foundation on-going |  | - | 1 | 190.2121 | 2014-07-07
SPANISH/GOG
114 | DFR | CENTRAL | Cape Coast | DFR/CR/SPANISH/09/09 | Bridge Construction | Steel Bridges over River Amunam and River Kakum on Kwaprow - Ankaful Jn F/R | 40M | Gen. Const. & Dev. Ltd. | SPANISH/GOG | 2010-05-06 | 2010-08-19 | 105 | 2011-08-19 | 865 | 2012-12-31 | 3№ 700x900mm,9№ 900x1200mm,1№ 1200x1200mm U-culvert,4№ Abutments completed and bridge lunched. | 1352858.78 | 1617419.1 | 1617419.1 | 0 | 100 | 100 | Work completed. | 3№ 700x900mm,9№ 900x1200mm,1№ 1200x1200mm U-culvert,4№ Abutments completed and bridge lunched. |  | - |  | 163.9306 | 2014-07-07
115 |  | CENTRAL | THLD | DFR/CR/SPANISH/09/10 | Bridge Construction | Steel Bridge over River Bonsa on Atieku - Bonsaho F/R | 20M | Bo Const. Ent. Ltd. | SPANISH/GOG | 2010-05-06 | 2011-04-28 | 357 | 2012-12-31 | 613 | 2012-12-31 | - | 562982.9 | 562982.9 | 66897.86 | 496085.04 | 11.8828 | 5 | Work in progress | Clearing completed |  | - | 1 | 190.2121 | 2014-07-07
116 | DFR | CENTRAL | UDW | DFR/CR/SPANISH/09/11 | Bridge Construction | Steel Bridge over River Ntateasu on Nkwantanum - Asaman F/R | 20M | Little Light Ent. | SPANISH/GOG | 2010-05-06 | 2011-04-28 | 357 | 2012-12-31 | 613 | 2012-12-31 | 6№ 700X900mm,3№ 900x1200mm,1№ 2/3,000X3,000mm RBC completed | 715324.12 | 715324.12 | 357889.87 | 357434.25 | 50.0318 | 52 | Work in progress | Clearing ,6№ 700X900mm,3№ 900x1200mm,1№ 2/3,000X3,000mm RBC completed, Completed with approach filling of all culverts |  | - | 1 | 190.2121 | 2014-07-07
AfDB/EMQAP
117 | DFR | CENTRAL | Awutu Senya | EMQAP/DFR/CR/AWS/10/NCB/LOT 1 | Surfacing | Bawjiase - Akufokrodua - Adawuka | 6.4 | Catrol (GH) Ltd. | AfDB/EMQAP | 2011-02-07 | 2011-05-19 | 101 | 2012-05-21 | 368 | 2012-05-21 | 7№ 700X900mm,2№ 900X1200mm U-culverts and 1№ 1800mm Pipe Culvert,236m 600x600x150mm Conc U-drain completed. | 1085513.11 | 1085513.11 | 985861.91 | 25286.32 | 90.8199 | 100 | Works completed. Final retention released on 3/2/14 | Clearing, formation,7№ 700X900mm,2№ 900X1200mm U-culverts and 1№ 1800mm Pipe Culvert,236m 600x600x150mm Conc U-drain,6.1km sub-base & base, primer seal & seal completed |  | CR-AES-C-023 | 1 | 311.1413 | 2014-07-07
118 | DFR | CENTRAL | Awutu Senya | EMQAP/DFR/CR/AWS/10/NCB/LOT 2 | Surfacing | Jeikrodua - Osaekrodua | 1.8 | Memphis Metro. Ltd. | AfDB/EMQAP | 2011-02-07 | 2011-05-05 | 87 | 2011-11-07 | 543 | 2012-10-29 | 1No 2/1800x1800mm,1№ 900X1200mm,4№ 700X900mm U-culvert,700m 450x450x150mm block drain completed. | 454625.2 | 454625.2 | 454028.75 | 0 | 99.8688 | 100 | Works completed. Final retention released on 18/7/13 | Clearing, formation and 1No 2/1800x1800mm,1№ 900X1200mm,4№ 700X900mm U-culvert,700m 450x450x150mm block drain,sub-base,base,primerseal & seal completed. |  | CR-AES-C-026 |  | 213.4438 | 2014-07-07
119 | DFR | CENTRAL | Awutu Senya | EMQAP/DFR/CR/AWS/10/NCB/LOT 14 | Spot Improvement | Kwame Kwei - Akweiku - Anaman Akura | 7.7 | B. K. Nsiah Co. Ltd. | AfDB/EMQAP | 2011-02-07 | 2011-05-05 | 87 | 2012-01-05 | 573 | 2012-11-28 | 15№ 700X900mm,8№ 900X1200mm completed | 409515.08 | 409515.08 | 307111.1 | 0 | 74.9938 | 100 | Works completed. Final retention released on 25/7/13 | Clearing,formation,15№ 700X900mm,8№ 900X1200mm and 6.7km sub-base completed. |  | CR-AES-A-054 |  | 202.2688 | 2014-07-07
120 | DFR | CENTRAL | Awutu Senya | EMQAP/DFR/CR/AWS/10/NCB/LOT 4 | Rehabilitation | Chochoe - Abonasah | 3.6 | Askku Ent. Ltd. | AfDB/EMQAP | 2011-02-07 | 2011-05-19 | 101 | 2011-11-21 | 186 | 2011-11-21 | 4№ 700X900mm,2№ 600X700mm U-culverts completed | 173030.04 | 173030.04 | 98466.16 | 74563.88 | 56.907 | 90 | Project terminated on 6/2/13 | Clearing, formation,4№ 700X900mm,2№ 600X700mm U-culverts and 3.6km sub-base completed |  | CR-AES-C-053 |  | 615.5914 | 2014-07-07
121 | DFR | CENTRAL | Gomoa East | EMQAP/DFR/CR/AWS/10/NCB/LOT 13 | Spot Improvement | Okyereko - Demonstration Centre | 4.5 | Abdul-Rahman & Sons Ltd. | AfDB/EMQAP | 2011-02-07 | 2011-05-05 | 87 | 2011-11-07 | 186 | 2011-11-07 | 6№ 700x900mm and 1№ 1200x1200mm U culvert,250m 450x450x150mm U- drain,200m of stone line drain completed | 134880.48 | 134880.48 | 123358.5 | 0 | 91.4576 | 100 | Works completed. Final retention released on 23/7/13 | Clearing,6№ 700x900mm and 1№ 1200x1200mm U culvert,250m 450x450x150mm U- drain,200m of stone line drain & sub-base completed |  | CR-AES-A-046 |  | 623.1183 | 2014-07-07
122 | DFR | CENTRAL | Awutu Senya | DFR/CR/EMQAP/12/NCB/LOT 5 | Spot Improvement | Osaekrodua - George Farms | 1.3 | Abdul-Rahman & Sons Ltd. | AfDB/EMQAP | 2012-05-15 | 2012-06-28 | 44 | 2012-12-28 | 183 | 2012-12-28 | 6№ 700X900mm U-culvert,316m 450x450x150mm U- drain completed. | 233685.08 | 233685.08 | 204214.65 | 0 | 87.3888 | 100 | Work completed. Final retention released on 30/01/14 | Clearing and 6№ 700X900mm U-culvert,316m 450x450x150mm U- drain,1.2km of sub-base completed. |  | CR-AES-A-056 |  | 403.8251 | 2014-07-07
123 | DFR | CENTRAL | Awutu Senya | DFR/CR/AWS/EMQAP/12/NCB/LOT 6 | Spot Improvement | Opembo - Peelco Farms | 1.6 | Sweet City Ent. | AfDB/EMQAP | 2012-06-26 | 2012-06-28 | 2 | 2012-12-28 | 183 | 2012-12-28 | 3№ 700X900mm U-culvert,150m 450x450x150mm U- drain,200m kerb & extention of 1No 600mm pipe culvert completed. | 156346.52 | 156346.52 | 118562.38 | 0 | 75.8331 | 100 | Works completed. 50% of retention released on 20/03/13 | Clearing, formation and 5№ 700X900mm U-culvert,150m 450x450x150mm U- drain,200m kerb,extention of 1No 600mm pipe culvert & 1.0km sub-base completed. |  |  |  | 403.8251 | 2014-07-07
Note on H5: CR3:

## ROUTINE
DEPARTMENT OF FEEDER ROADS
CENTRAL REGION
MONTHLY PROGRESS REPORT FOR DECEMBER 2012
NO. | PROJECT NAME |  | ROAD LENGTH (KM) | PROJECT LOCATION (DISTRICT) | ACTIVITY | ROAD NUMBER | CONTRACTOR | WORK PERIOD |  |  | CONTRACT SUM (GH¢) | TOTAL AMOUNT CERTIFIED | % COMPLETED | LENGTH COMPLETED | REMARKS | CONTRACT NUMBER | FUNDING & SOURCES | CERT. NO
[8 empty] | AWARD | DATE OF | DATE OF
[8 empty] | DATE | COMM. | COMP.
ROAD FUND
1 | Abor-Techiman-Eyisam & Others | Abor-Techiman-Eyisam | 3.1 | MFA | Reshaping | CR-MFA-C-069 | E. Speedway Construct | 2010-03-12 | 2010-03-30 | 2010-06-30 | 14582.15 | 14446.75 | 100 | 8.6km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/MF/RESH/GOG/10/1 | GOG | 1
| Abor-Techiman-Eyisam & Others | Ekumfi Nanabin - Narkwa | 5.5 |  |  | CR-MFA-C-018 | Super Technology Ent. | [9 empty] | COCOA
8.6
2 | Boadukrom Jn Boadukrom-Gomoa Amanful & Others | Boadukrom Jn - Gomoa Amanful | 2.8 | MFA | Reshaping | CR-MFA-I-072 | Kopp Civil Eng Building And Roads Co Ltd | 2010-03-12 | 2010-04-08 | 2010-08-08 | 22864.8 | 15886.82 | 100 | 11.9km of Grass Cutting and Reshaping completed |  | DFR/CR/MF/RESH/GOG/10/2 | GOG
|  | Otuam - Aboano - Srafa | 4.7 |  |  | CR-MFA-C-003
|  | Adansi - Akra | 6.5 |  |  | CR-MFA-A-001
|  | Etsebedu Jn - Etsebedu | 1.3 |  |  | CR-MFA-A-004
15.3
3 | Egyanka-Immuna & Others | Egyanka-Immuna | 8 | MFA | Reshaping | CR-MFA-C-005 | Asti Agencies Ltd. | 2010-03-12 | 2010-04-15 | 2010-07-15 | 25686.8 | 24647.52 | 100 | 18.80km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/MF/RESH/GOG/10/3 | GOG | 1
|  | Adansi - Immuna - Srafa Kokodo | 8 |  |  | CR-MFA-C-003
|  | Ekumpoano Jn - Ekumpoano | 1.6 |  |  | CR-MFA-A-002
|  | Ekumfi Potwabeng Jn - Potwabeng | 1.2 |  |  | CR-MFA-A-024 | [10 empty] | COCOA
18.8
4 | Gyinakuma Jn-Gyinakuma & Others | Gyinakuma Jn-Gyinakuma | 1.4 | MFA | Reshaping | CR-MFA-A-008 | Zulpha Construction Ltd | 2010-03-12 | 2010-04-21 | 2010-07-21 | 13848 | 13765.28 | 100 | 10.3km of Grass Cutting and Reshaping completed | Work in Progress | DFR/CR/MF/RESH/GOG/10/4 | GOG
|  | Egyanka - Srafa Kokodo | 6 |  |  | CR-MFA-C-005
|  | Gyinankuma - Aduasa Kokodo | 2.1 |  |  | CR-MFA-C-010
9.5
5 | Enum Jn-Donkorkrom & Others | Enum Jn - Donkorkrom | 9 | ASN | Reshaping | CR-ASN-A-012 | Lar-Tan Ltd | 2010-03-12 | 2010-05-19 | 2010-09-19 | 39491 | 38185.21 | 100 | 26.6km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/ASN/RESH/GOG/10/5 | GOG | 1
|  | Donkorkrom - Besedriase | 6 |  |  | CR-ASN-A-013
|  | Assin Swedru - Adukwaku | 6.4 |  |  | CR-ASN-A-011
|  | Samankrom Jn - Samankrom | 2.5 |  |  | Not Available | [10 empty] | COCOA
|  | Amoakrom Jn - Amoakrom | 3 |  |  | CR-ASN-A-034 | [10 empty] | COCOA
26.9
6 | Affaw Jn-affaw & Others | Affaw Jn-affaw | 5.8 | ASS | Reshaping | CR-ASS-A-022 | Pe-Wuud Const Ltd | 2010-03-12 | 2010-03-31 | 2010-07-31 | 39242.15 | 32784.73 | 100 | 26.3km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/ASS/RESH/GOG/10/6 | GOG | 1
|  | Jakai - Kruwa Jn | 13 |  |  | CR-ASS-I-018 | [10 empty] | COCOA
|  | Jakai - Asano-Aben | 7.5 |  |  | CR-ASS-A-017 | [10 empty] | COCOA
26.3
7 | Gyinabodie Jn-Nyankomase & Others & Others | Gyinabodie Jn-Nyankomase | 18 | ASS | Reshaping | CR-ASS-C-011 | All In One Co. Ltd | 2010-03-12 | 2010-05-19 | 2010-09-19 | 28240 | 26367.7 | 100 | 15.40km of Grass Cutting and Reshaping completed. |  | DFR/CR/ASS/RESH/GOG/10/7 | GOG | 1
|  | Fanti Nyankomase - Obosomase | 2 |  |  | CR-ASS-I-023 | [10 empty] | COCOA
20
8 | Ebukrom Jn-Hemang & Others | Ebukrom Jn-Hemang Jn | 5.2 | KEEA | Reshaping | CR-KEE-A-038 | Alt Const. Ltd. | 2010-03-12 | 2010-05-04 | 2010-08-04 | 21522 | 21385.7 | 100 | 15.40km of Grass Cutting and Reshaping completed. |  | DFR/CR/KEEA/RESH/GOG/10/8 | GOG | 1
|  | Kissi - Atekyem | 10.2 |  |  | CR-KEE-C-036 | [10 empty] | COCOA
15.4
9 | Osubonpanyin Jn.-Asubonpanyin & Others | Osubonpanyin Jn.-Asubonpanyin | 4.2 | EF | Reshaping | CR-AES-C-049 | Ernma Venture | 2010-03-12 | 2010-05-26 | 2010-08-26 | 17368 | 17244.8 | 100 | 11.80km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/EF/RESH/GOG/10/9 | GOG | 1
|  | Atieku - Okyireko | 4.4 |  |  | Not Available | Jen & Vince Co. Ltd. | [9 empty] | COCOA
|  | Sankor - Nsuakyir | 6.5 |  |  | CR-AES-C-036
|  | Nsuakyir - Warabeba | 1.6 |  |  | CR-AES-A-038 | Jen & Vince Co. Ltd. | [9 empty] | COCOA
16.7
10 | Manford-Wheda & Others | Manford-Wheda | 4.65 | GW | Reshaping | CR-GOM-C-011 | West Sunrise Comp. Ltd. | 2010-03-12 | 2010-05-06 | 2010-09-06 | 30005.5 | 29401.07 | 100 | 17.20km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/GW/RESH/GOG/10/10 | GOG | 1
|  | Gomoa Abostia Jn - Abostia | 0.8 |  |  | CR-GOM-A-017 | [10 empty] | COCOA
|  | Gomoa Assin - Brofoyedur | 2.5 |  |  | CR-GOM-C-016 | [10 empty] | COCOA
|  | Apan - Brofoyedur | 12.5 |  |  | CR-GOM-C-018 | [10 empty] | COCOA
20.45
12 | Gomoa Kirenkwanta-Mando & Others | Gomoa Kirenkwanta-Mando | 15 | GW | Reshaping | CR-GOM-I-035 | Katoll (Gh) Ltd. | 2010-03-12 | 2010-04-29 | 2010-07-29 | 23497.2 | 17515.56 | 100 | 12.90km of Grass Cutting and Reshaping completed |  | DFR/CR/GW/RESH/GOG/10/12 | GOG | 1
|  | Sampa Jn - Akropong | 4.5 |  |  | CR-GOM-A-032
|  | Asempanaye Jn - Asempanaye | 0.6 |  |  | Not Available | [10 empty] | COCOA
20.1
13 | Swedru-Oteipiro-Domokyi & Others | Swedru-Oteipiro-Domokyi | 5.2 | AW | Reshaping | CR-AGO-A-001 | O.D.B. Const. Ltd. | 2010-03-12 | 2010-04-05 | 2010-08-05 | 46556 | 45754.3 | 100 | 30.30km of Grass Cutting and Reshaping completed. | Work is satisfactory | DFR/CR/AW/RESH/GOG/10/13 | GOG | 1
|  | Afranse - Nyarkrom | 12.4 |  |  | CR-AGO-I-004
|  | Jacobs - Nkranfo | 4.1 |  |  | CR-AGO-A-020
|  | Jacobs - Akwakwa | 1.3 |  |  | CR-AGO-A-021
|  | Wawase - Amponsah - Samuel | 4.5 |  |  | Not Available
|  | Wawase - Nyamedam | 2.8 |  |  | CR-AGO-A-018 | [10 empty] | COCOA
30.3
14 | Amanfor-Namanwor & Others | Amanfor - Namanwor | 8.4 | AW | Reshaping | CR-AGO-C-010/11/12 | Saint Gallen Ent. | 2010-03-12 | 2010-04-07 | 2010-08-07 | 33170 | 29190.6 | 100 | 20.0km of Grass Cutting and Reshaping completed. |  | DFR/CR/AW/RESH/GOG/10/14 | GOG | 1
|  | Bobikuma - Kuntenase | 10.4 |  |  | CR-AGO-I-050
|  | Bosompa - Nkwantanando | 3 |  |  | Not Available | [10 empty] | COCOA
21.8
15 | Mfadwen Jn-Bonrase & Others | Mfadwen Jn-Bonrase | 4.6 | AS | Reshaping | CR-AES-C-025 | Sosthenes Comp. Ltd | 2010-03-12 | 2010-04-13 | 2010-07-13 | 17985.55 | 17138.02 | 100 | 13.10km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/AS/RESH/GOG/10/15 | GOG | 1
|  | Akubufar Jn - Gyekrodua | 8.5 |  |  | CR-AES-C-026 | [10 empty] | COCOA
13.1
16 | Kwamewatey-Bosomaben & Others | Kwamewatey-Bosomaben | 2.5 | AS | Reshaping | CR-AES-C-032 | Zulpha Construction Ltd | 2010-03-12 | 2010-04-21 | 2010-07-21 | 26281.2 | 25679.04 | 100 | 19.8km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/AS/RESH/GOG/10/16 | GOG | 1
|  | Ahintia - Kasoa | 13 |  |  | CR-AES-C-035
|  | Osimpo - Akraman | 4.3 |  |  | CR-AES-I-031 | [10 empty] | COCOA
19.8
17 | Fianko-Asuetene & Others | Fianko-Asuetene | 11 | AS | Reshaping | CR-AES-I-008 | Roquartco Const. Works | 2010-03-12 | 2010-04-20 | 2010-08-20 | 32914 | 30963.86 | 100 | 20.85km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/AS/RESH/GOG/10/17 | GOG | 1
|  | Okwabena - Ofaso | 2.6 |  |  | CR-AES-C-012 | [10 empty] | COCOA
|  | Adawukwa - Fianko | 5.8 |  |  | Not Available | [10 empty] | COCOA
|  | Papaye Jn - Papaye | 1 |  |  | CR-AES-C-009
|  | Mofrakrom Jn - Mofrakrom | 1.3 |  |  | CR-AES-A-010 | [10 empty] | COCOA
21.7
18 | New Ansaful-Ntakofam | New Ansaful-Ntakofam | 4 | EF | Reshaping | Not Available | Tecson Comp. Ltd. | 2010-03-12 | 2010-04-05 | 2010-11-05 | 49546.08 | 23236.45 | 94 | 2.7km of Grass Cutting and Reshaping,1№ 700x900mm,1№ 900x1200mm U-culvert,36m of 450x450x120mm,52.6m of 600x600x150mm Conc. U-drain completed | Work is satisfactory | DFR/CR/EF/RESH/GOG/10/18 | GOG | 1
4
19 | Afrangua-Ayeldo-Kwadeogya & Others | Afrangua-Ayeldo-Kwadeogya | 17.8 | AAK | Reshaping | CR-MFA-I-044 | Boabbsons Co Ltd. | 2010-03-12 | 2010-04-07 | 2010-08-07 | 36101 | 30494.4 | 100 | 20.10km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/AAK/RESH/GOG/10/19 | GOG | 1
|  | Gyabankrom - Kwamankese | 2.8 |  |  | CR-AAK-C-050 | [10 empty] | COCOA
|  | Kwamankese - Nkwanta | 4.1 |  |  | CR-AAK-C-051 | [10 empty] | COCOA
24.7
20 | Nyamedom-Asomdwee & Others | Nyamedom-Asomdwee | 7 | AAK | Reshaping | CR-AAK-C-054 | Altep Ent. Ltd. | 2010-03-12 | 2010-05-26 | 2010-08-26 | 23481 | 23463.49 | 100 | 13.0km of Grass Cutting and Reshaping completed | Work in Progress | DFR/CR/AAK/RESH/GOG/10/20 | GOG | 1
|  | Asomdwee - Badukrom | 2.8 |  |  | CR-AAK-A-013
|  | Abakrampa - Nyamedom | 6.1 |  |  | CR-AAK-C-025 | [10 empty] | COCOA
15.9
21 | Nkwantanum-Assin Manso | Nkwantanum-Assin Manso | 30 | AEE | Reshaping | CR-ASS-I-027 | Sosthenes Comp. Ltd | 2010-03-12 | 2010-04-13 | 2010-08-13 | 38458 |  |  |  | Second Warning letter given on 17/01/11. | DFR/CR/AEE/RESH/GOG/10/21 | GOG
30
22 | Nkodjo-Abaasa & Others | Nkodjo-Abaasa | 3.1 | AEE | Reshaping | CR-AJU-A-032 | West Sunrise Comp. Ltd. | 2010-03-12 | 2010-05-06 | 2010-09-06 | 36462 | 36438.3 | 100 | 21.85km of Grass Cutting and Reshaping completed |  | DFR/CR/AEE/RESH/GOG/10/22 | GOG | 1
|  | Nkwantanum-Kromaim-Mando | 6.2 |  |  | CR-AJU-C-036
|  | Ampia Ajumako - Adwumam | 3 |  |  | CR-AJU-I-034
|  | Denkyira - Kromaim | 3 |  |  | CR-AJU-C-026
|  | Nsawadze - Atakwa - Nkodjo | 4 |  |  | Not Available
|  | Kromaim - Abaasa | 3 |  |  | CR-AJU-C-037 | [10 empty] | GOG
22.3
23 | Abaasa-Enyan Abor & Others | Abaasa-Enyan Abor | 13.5 | AEE | Reshaping | Not Available | Asmariate Ent. Ltd. | 2010-03-12 | 2010-04-13 | 2010-08-13 | 50136 | 50134 | 100 | 29.8km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/AEE/RESH/GOG/10/23 | GOG | 1
|  | Osedzi - Essaman - Opropro | 3.9 |  |  | CR-AJU-A-006
|  | Kyebi Jn - Osedzi | 3 |  |  | CR-AJU-C-004
|  | Eshiem - Afransi | 3.5 |  |  | CR-AJU-A-008
|  | Kwesi Gyan - Opesease | 2.6 |  |  | CR-AJU-A-015
|  | Baa-Amia - Osedzi | 3 |  |  | CR-AJU-C-005
29.5
| Ongua - Sergentkrom | Ongua - Sergentkrom | 14.5 | ASS | Reshaping | CR-ASS-A-039 | Jaysem Co Ltd. | 2010-10-05 | 2010-12-06 | 2011-04-06 | 30127.2 | 26203.78 | 100 | 14.1km of Grass Cutting and Reshaping completed |  |  | GOG
14.5
| Amoakrom Jn - Amoakrom | Tweapease Jn - Tweapease | 2.8 | ASN | Reshaping | CR-ASN-A-016 | Samwilco Const. Ltd. | 2010-10-05 | 2010-11-12 | 2011-03-12 | 45846.24 | 43041.82 | 100 | 21.3km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Amoakrom Jn - Amoakrom | 3 |  |  | CR-ASN-A-034
|  | Benuye Camp C - Atakwaa | 5.7 |  |  | CR-ASN-A-005
|  | Nyamebekyere - Subrisu | 4.2 |  |  | Not Available
|  | Akyianu - Anlofuom | 8 |  |  | CR-ASN-C-003
23.7
| Bawjiase - Aponkyikwa | Bawjiase - Aponkyikwa | 7.2 | AS | Reshaping | CR-AES-A-013 | Thomlako Ltd. | 2010-10-05 | 2011-02-07 | 2011-06-07 | 45820.4 | 42959.3 | 100 | 25.25km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Hasowodze Jn - Hasowodze | 1
|  | Aburi Jn - Aburi | 2.1
|  | Kwesidadzie Jn - Kwesidadzie | 0.5
|  | Bawjiase - Ayensuakwa | 7.5 |  |  | CR-AES-C-018
|  | Bewinum Jn - Adawukwa | 9.5 |  |  | CR-AES-C-005
27.8
| Duakwa-Akwakwaa | Duakwa-Akwakwaa | 16 | AE | Reshaping | CR-AGO-I-007 | Opakoh Ent. | 2010-10-05 | 2010-11-06 | 2011-03-05 | 31855.2 | 28037.35 | 100 | 16.0km of Grass Cutting and Reshaping completed | Work is satisfactory | DFR/CR/AE/RESH/GOG/4/10 | GOG | 1
16
| Baifikrom - Dominase | Baifikrom - Dominase | 12.6 | MFA | Reshaping | CR-MFA-C-025 | Acquah & Sons Ltd. | 2010-10-05 | 2010-12-07 | 2011-04-07 | 40663.44 | 33250.39 | 100 | 18.65km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Duadze - Kwesil Ansah | 4.05 |  |  | CR-MFA-C-075
|  | Eshirow Jn - Eshirow | 2 |  |  | CR-MFA-A-026
18.65
| Nsanfo - Nsaadze | Nsanfo - Nsaadze | 4.4 | MFA | Reshaping | CR-MFA-C-057 | Alt Const. Ltd. | 2010-10-05 | 2011-01-17 | 2011-04-16 | 26312.88 | 17776.82 | 100 | 12.6km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Nsanfo - Amissahkrom | 3.5 |  |  | CR-MFA-A-063
|  | Waakrom Jn -Waakrom | 1.5 |  |  | CR-MFA-A-059
|  | Egyirefa Jn - Eeyirefa | 3 |  |  | CR-MFA-A-062
12.4
| Akwakwaa - Ankama | Akwakwaa - Ankama | 2.1 | AE | Reshaping | CR-AGO-I-054 | Jackson & Sons Ltd. | 2010-10-05 | 2010-11-11 | 2011-02-11 | 21746.4 | 14085.88 | 100 | 8.10km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Duoto - Obereburu | 2.2 |  |  | CR-AGO-A-027
|  | Kokwado - Asarekwa | 2 |  |  | CR-AGO-A-014
|  | Nantifa - Tawora - Kokwado | 4 |  |  | CR-AGO-C-016
10.3
| Manso Jn - Gomoa Oguaa | Manso Jn - Gomoa Oguaa | 13 | GW | Reshaping | CR-GOM-C-020 | Anafo Const Works | 2010-10-05 | 2010-11-22 | 2011-02-22 | 24945.6 | 17087.4 | 100 | 11.10km of Grass Cutting and Reshaping completed |  |  | GOG | 1
13
| Atekyem - Besease Jn | Atekyem - Besease Jn | 8.3 | KEEA | Reshaping | CR-KEE-C-037 | Sweet City Ent. | 2010-10-05 | 2010-11-11 | 2011-02-11 | 26397.36 | 25519.35 | 100 | 12.30km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Atekyem- Mprakokrom | 2.3 |  |  | CR-KEE-A-039
|  | Komfokrom Jn - Komfokrom | 2 |  |  | Not Available
12.6
| Egya № 2 - Oboadze | Egya № 2 - Oboadze | 9.5 | MFA | Reshaping | CR-MFA-A-032 | Ruthra Const. Co. | 2010-10-05 | 2010-11-23 | 2011-03-23 | 44825.04 | 33482.13 | 100 | 21.4km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Anomabo - Pomase | 9 |  |  | CR-MFA-I-036
|  | Pomaadze - Oboadze | 2.9 |  |  | Not Available
21.4
| Gyankobo - Abaka Nkwanta | Gyankobo - Abaka Nkwanta | 19.2 | THLD | Reshaping | CR-LDE-I-052 | Nataco Beach Resort | 2010-10-05 | 2010-12-07 | 2011-04-07 | 36543.36 | 33620.54 | 100 | 17.9km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Antwikwa Jn - Antwikwa | 2.3 |  |  | CR-LDE-A-057
21.5
| Kotokye - Atiaso | Kotokye - Atiaso | 4.4 | THLD | Reshaping | CR-LDE-A-033 | Pee-Wuud Const. Ltd. | 2010-10-05 | 2010-12-08 | 2011-03-08 | 26190.72 | 20709.7 | 100 | 15.8km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Kyirenkum - Boninsuma | 7 |  |  | CR-LDE-C-035
|  | Akatakyi Jn - Akatakyi | 2.1 |  |  | Not Available
|  | Attorkrom Jn- Attorkrom | 2.2 |  |  | CR-LDE-A-036
15.7
| Fianko - Openbo | Fianko - Openbo | 7.8 | AS | Reshaping | Not Available | Enh Eng. | 2010-10-05 | 2010-12-10 | 2011-03-10 | 27528 | 19828.84 | 100 | 12.7km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Bukokrom Jn - Ayisikrom | 1.2 |  |  | Not Available
|  | Nkura Akyire Jn - Nkura Akyire | 1.8 |  |  | Not Available
|  | Dankwa Jn - Dankwa | 1 |  |  | CR-AES-A-011
|  | Ofaso - Konkokura | 3 |  |  | CR-AES-C-058
14.8
| Nsueam Jn - Nsueam | Nsueam Jn - Nsueam | 4 | GE | Reshaping | CR-GOM-A-039 | Pot Systems Ltd. | 2010-10-05 | 2010-12-02 | 2011-03-02 | 20400.59 | 12910.14 | 100 | 8.8km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Paaso - Paaso Farm | 2.6 |  |  | CR-GOM-A-043
|  | Asiwukwaa Jn - Asiwukwaa | 3.2 |  |  | CR-GOM-C-049
|  | Otweikrom - Okotokwaa | 2 |  |  | CR-GOM-C-051
|  | Odombo Jn - Odombo | 1.1 |  |  | CR-GOM-A-050
12.9
| Anomabu - Nkramofuokrom | Nsanfo Jn - Nkramofuokrom | 10.6 | MFA | Reshaping | CR-MFA-C-055 | Ark Const Works Ltd. | 2010-10-05 | 2010-11-05 | 2011-03-05 | 31104 | 30284.9 | 100 | 15.2km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Oguanamua Jn - Akoa | 2.1 |  |  | CR-MFA-A-056
|  | Wankam Jn - Wankam | 1 |  |  | CR-MFA-A-058
|  | Komantse - Otsir | 1.5 |  |  | CR-MFA-A-054
|  | Lower Komantse - Upper Komantse | 1 |  |  | CR-MFA-A-053
16.2
| Anokye - Kuntu | Anokye - Kuntu | 4 | MFA | Reshaping | CR-MFA-A-051 | Teranisa Com. Ltd. | 2010-10-05 | 2010-11-05 | 2011-02-05 | 22835.28 | 20729.58 | 100 | 10.75km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Kankanbom - Oboadze | 1 |  |  | CR-MFA-C-034
|  | Traveco Jn - Traveco | 0.7 |  |  | CR-MFA-A-052
|  | Biriwa - Asfora Jn | 5.8 |  |  | CR-MFA-C-064
11.5
| Oduman - Akropong | Oduman - Akropong | 5.35 | MFA | Reshaping | CR-MFA-A-030 | Thureve Ltd. | 2010-10-05 | 2010-11-29 | 2011-03-01 | 25632 | 20271.08 | 100 | 12.7km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Essiamotan Jn - Essimotan | 1.6 |  |  | CR-MFA-A-042
|  | Korado - Obosomdze | 1.2 |  |  | CR-MFA-C-041
|  | Akobima Jn - Achiase | 2.7 |  |  | CR-MFA-A-040
|  | Akobima - Bosomadze | 2.5 |  |  | CR-MFA-C-076
13.35
| Anwiom Jn - Beposo | Anwiom Jn - Beposo | 6.6 | KEEA | Reshaping | CR-KEE-C-044 | Zee Dok Ltd. | 2010-10-05 | 2010-11-11 | 2011-03-10 | 35888.48 | 32744.45 | 100 | 17.5km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Komenda Ssfwi - Krofofrodo | 6.6 |  |  | CR-KEE-C-034
|  | Domenase - Duakyimase | 4.3 |  |  | CR-KEE-A-033
17.5
| Obosomase - Asankwa | Obosomase - Asankwa | 3 | AE | Reshaping | CR-AGO-A-025 | Rochfords Co. Ltd. | 2010-10-05 | 2010-12-15 | 2011-03-15 | 22924.8 | 20896.91 | 100 | 10.25km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Kokroko Jn - Kokroko | 1.05 |  |  | Not Available
|  | Asafo - Kwesitwekwa - Fawomanye | 8 |  |  | CR-AGO-I-015
12.05
| Oguaa Jn - Abeadze | Oguaa Jn - Abeadze | 8 | GW | Reshaping | CR-GOM-I-021 | Deidenz Co Ltd. | 2010-10-05 | 2010-12-01 | 2011-04-01 | 38480.4 | 36399.9 | 100 | 19.0km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Gomoa Tarkwa - Abeadze | 7.5 |  |  | CR-GOM-I-021
|  | Gomoa Dabiso - Ayanfuri | 2 |  |  | CR-GOM-I-022
|  | Akyease - Mankesim | 3.5 |  |  | CR-GOM-C-033
21
| Simbrofo Jn - Denkyira | Simbrofo Jn - Denkyira | 11 | GW | Reshaping | CR-GOM-C-007 | Tamlana-Tega Ent. | 2010-10-05 | 2010-12-13 | 2011-04-13 | 49889.52 | 47981 | 100 | 25.7km of Grass Cutting and Reshaping completed | Work in progress |  | GOG
|  | Oguan Jn - Nduem | 9.2 |  |  | CR-GOM-C-006
|  | Essaakyire - Gomoa Maim | 1.7
|  | Gomoa Adam Jn - Gomoa Adam | 0.4
|  | Oguan Jn - Ajumako | 4.5 |  |  | CR-GOM-C-014
26.8
| Akropong - Kwaakrom | Akropong - Kwaakrom | 2.9 | MFA | Reshaping | Not Available | Tescon Ltd. | 2010-10-05 | 2011-01-27 | 2011-04-27 | 27199.44 | 22631.62 | 100 | 12.9km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Kyeakor - Akropong | 4 |  |  | Not Available
|  | Dominase - Bewura | 6 |  |  | CR-MFA-I-028
12.9
| Bankyiase - Kyinso | Bankyiase - Kyinso | 12 | ASS | Reshaping | CR-ASS-A-008 | Tiboura-Taa Ltd. | 2010-10-05 | 2010-12-02 | 2011-03-02 | 24945.2 | 22844 | 100 | 12.9km of Grass Cutting and Reshaping completed |  |  | GOG | 1
12
| Papase - Olutum | Papase - Olutum | 9.2 | AS | Reshaping | CR-AES-C-029 | Johaze Ltd. | 2010-10-05 | 2011-03-16 | 2011-06-16 | 27145.92 | [5 empty] | GOG
|  | Bontrase - Dasum | 4.4 |  |  | CR-AES-I-030
13.6
| Hemang - Paaso- Nsutem | Hemang - Paaso- Nsutem | 12.5 | THLD | Reshaping | CR-LDE-C-058 | Nataco Beach Resort | 2010-10-05 | 2010-10-22 | 2011-02-22 | 45168 | 43282.9 | 100 | 24.0km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Betimor-Nyameyeadom | 6.7 |  |  | CR-LDE-A-049
|  | Baakondzidzi - Oppongso | 4 |  |  | CR-LDE-A-051
|  | Brukusu-Nyamebekyere | 2.8 |  |  | CR-LDE-A-048
26
| Abrekum Jn - Abrekum | Abrekum Jn - Abrekum | 6 | GW | Reshaping | CR-GOM-A-004 | Tescon Ltd. | 2010-10-05 | 2011-01-27 | 2011-05-27 | 41864.64 | 34022.18 | 100 | 19.0km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Otsewew - Gomoa Lome | 8.4 |  |  | CR-GOM-C-005
|  | Mprumaim Jn - Mprumaim | 1 |  |  | CR-GOM-A-009
|  | Djankrom Jn - Djankrom | 4.5 |  |  | CR-GOM-A-008
19.9
| Akwakrom Jn - Akwakrom | Akwakrom Jn - Akwakrom | 4.1 | KEEA | Reshaping | CR-KEE-A-021 | Fikus Const. Ltd. | 2010-10-05 | 2010-12-13 | 2011-04-13 | 39282.24 |  | 40 | 17.0km of Grass Cutting completed |  |  | GOG
|  | Abrem Agona - Adama | 9.3 |  |  | CR-KEE-I-017
|  | Warebeba Jn - Warebeba | 1.5 |  |  | CR-KEE-A-023
|  | Antem Jn - Antem | 0.5 |  |  | CR-KEE-A-022
|  | Ntontonso Jn - Ntontonso | 2.6 |  |  | CR-KEE-A-018
18
| Odina - Kokofu | Odina - Kokofu | 9.9 | GW | Reshaping | CR-GOM-C-023 | Amana Supply & Const. Works | 2010-10-05 | 2010-11-21 | 2011-04-21 | 43337.28 | 39133.72 | 100 | 20.9km of Grass Cutting and Reshaping completed | Work is satisfactory |  | GOG | 1
|  | Dawurampong - Fomena | 11 |  |  | CR-GOM-I-026
20.9
| Anyinase Jn - Dutch Komenda | Anyinase Jn - Dutch Komenda | 5.2 | KEEA | Reshaping | CR-KEE-A-025 | Ceebag Co. Ltd. | 2010-10-05 | 2011-01-10 | 2011-05-10 | 33933.6 | 26813.31 | 100 | 13.95km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Ankaful Prison - Simiw | 3.1 |  |  | CR-KEE-A-002
|  | Anlo Jn.-Anlo Beach | 1.5 |  |  | CR-KEE-A-027
|  | Dompoase Jn.-Dompoase | 1.6 |  |  | CR-KEE-A-012
|  | Eguafo - Pongkromu | 3 |  |  | Not Available
|  | Eguafo - Bremang | 1.9 |  |  | CR-KEE-A-010
|  | Dompoase-Kokwado - Benyadze | 4.8 |  |  | Not Available
|  | Nswadwir - School | 0.6 |  |  | Not Available
|  | Amoanda Jn - Amoanda | 2 |  |  | CR-KEE-A-005
23.7
| Asomdwee - Okyeriku | Asomdwee - Okyeriku | 3.2 | AAK | Reshaping | CR-AAK-C-056 | Yamabek Const | 2010-10-05 |  |  | 29992.32 |  |  | - | Terminated and re-awarded |  | GOG
|  | Asuansi - Okyeriku | 3.9 |  |  | CR-AAK-C-043
|  | Framase - Kruwaa | 7 |  |  | Not Available
14.1
| Apenkwakrom - Obokrom Jn | Apenkwakrom - Obokrom Jn | 3.7 | AAK | Reshaping | CR-AAK-C-003 | Yamabek Const | 2010-10-05 |  |  | 29376 |  |  | - | Terminated and re-awarded |  | GOG
|  | Asuansi - Obokrom | 2.7 |  |  | CR-AAK-A-041
|  | Odumano - Akropong | 5.3 |  |  | CR-MFA-A-030
|  | Akropong - Kwaakron | 3.6 |  |  | Not Available
15.3
| Nkwantanum-Akokokrom | Nkwantanum-Akokokrom | 3.7 | AAK | Reshaping | CR-AAK-A-033 | Walker Ent | 2010-10-05 | 2010-11-05 | 2011-02-05 | 22272 | 18143.8 | 100 | 11.5km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Nyamebekyere Jn - Nyamebekyere Bush | 2.5 |  |  | CR-AAK-A-034
|  | Essandohkrom Jn - Essandohkrom | 1.4 |  |  | CR-AAK-A-045
|  | Old Ebu - Abuenu | 3.8 |  |  | CR-AAK-A-024
|  | Kokwado Jn-Odumase | 2 |  |  | CR-AAK-C-010
|  | Nyamedom - Kokwado | 0.9 |  |  | CR-AAK-A-009
|  | Nsien Jn - Nsien | 1.1 |  |  | CR-AAK-A-008
15.4
| Eguase-Asebu Ekroful Jn. | Eguase-Asebu Ekroful Jn. | 9 | AAK | Reshaping | CR-AAK-C-017 | Asaff Const | 2010-10-05 | 2010-11-04 | 2011-02-04 | 35661.6 | 24084.39 | 100 | 14.1km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Moree Jn-Moree | 2.1 |  |  | CR-AAK-A-016
|  | Amosima - Mensah | 2.3 |  |  | CR-AAK-A-018
|  | Wiamoa - Ekroful | 3.5 |  |  | Not Available
|  | Edukrom-Amosima | 1.6 |  |  | CR-AAK-C-015
18.5
| Abakrampa-Abura Denkyira | Abakrampa-Abura Denkyira | 6.2 | AAK | Reshaping | CR-AAK-C-027 | Asaff Const | 2010-10-05 | 2010-11-03 | 2011-03-02 | 26743.2 | 25850.2 | 100 | 14.4km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Abakrampa-Batanyia | 4.1 |  |  | CR-AAK-A-031
|  | Pra Ewusi - Ekroful | 1.1 |  |  | CR-AAK-A-028
|  | Taido-Ekroful | 0.7 |  |  | CR-AAK-A-029
|  | Nkramofokrom - Amoanda | 0.9 |  |  | CR-AAK-A-030
13
| Dominase - Badukrom | Dominase - Badukrom | 12.6 | MFA | Reshaping | CR-MFA-I-027 | Gluck Fides Gh Ltd | 2010-10-05 | 2010-12-30 | 2011-03-30 | 26277.36 | 26277.03 | 100 | 12.6km of Grass Cutting and Reshaping completed | Work is satisfactory |  | GOG
|  | Assin Akrofrom - Asabeim | 13.4 |  |  | CR-ASS-I-031
|  | Nkubemu Jn - Larter Amanbete | 3.6 |  |  | CR-ASS-C-032
12.6
| Nyinasin - Tsetsekasum | Nyinasin - Tsetsekasum | 6 | CC | Reshaping | CR-CCP-I-006 | Legna Const. Wks. | 2010-10-05 | 2010-12-27 | 2011-04-27 | 40240.2 | 32215.04 | 100 | 18.8km of Grass Cutting and Reshaping completed |  | DFR/CR/CC/RESH/GOG/36/10 | GOG | 1
|  | Ankaful - Ebu | 2 |  |  | CR-CCP-A-002
|  | Efutu - Srodofo | 4 |  |  | CR-AAK-I-014
|  | Ebubonko - Warabeba | 4.5 |  |  | CR-CCP-A-001
|  | Ebubonko - Dankwakrom | 2.7 |  |  | Not Available
|  | Abura-Adwengofom - Harris Hostel | 0.7 |  |  | Not Available
|  | Hans Cottage - Ebu | 2.4 |  |  | CR-CCP-A-002
|  | Kokwado Jn - Nkokonsa | 3.2 |  |  | CR-CCP-A-008
25.5
| Mankessim - Ewoyaa Jn | Mankessim - Ewoyaa Jn | 10.3 | MFA | Reshaping | CR-MFA-C-046 | Jins Co. Ltd. | 2010-10-05 | 2010-11-14 | 2011-02-14 | 40785.84 | 33919.86 | 100 | 17.6km of Grass Cutting and Reshaping completed |  |  | GOG | 1
|  | Krofu - Mpeseadadze | 3 |  |  | CR-MFA-C-048
|  | Krofu - Krampakrom Jn | 1.7 |  |  | CR-MFA-C-049
|  | Antaadze Jn - Antaadze | 1.4 |  |  | CR-MFA-C-047
|  | Nkwanta - Kwabadukwaa | 2.2 |  |  | CR-MFA-C-067
|  | Gyedu - Eduafo | 1.1 |  |  | CR-MFA-C-043
19.7
| Acquahkrom - Amissahkrom | Acquahkrom - Amissahkrom | 14.1 | MFA | Reshaping | CR-MFA-C-021 | Agri-Bisa Ventures | 2010-10-05 |  |  | 32021.4 |  | 30 | 6.5km of Grass Cutting and Reshaping completed | Terminated and re-awarded |  | GOG
|  | Mankessim - Suprudo | 5.1 |  |  | CR-MFA-C-022
19.2
| Tuakwa Jn-Betsingua | Tuakwa Jn-Betsingua | 8.1 | AAK | Reshaping | CR-AAK-C-046 | Knapo Const. Ltd. | 2010-10-05 | 2010-11-10 | 2011-03-10 | 35493.36 | 35459.76 | 100 | 20.4km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Bando - Pomase | 3.4 |  |  | CR-MFA-I-036
|  | Bando - Abura Abuase | 3.1 |  |  | CR-AAK-C-048
|  | Old Odonase - Kankanase Jn | 2 |  |  | CR-AAK-C-052
|  | Obohen - Ekroful | 1.6 |  |  | CR-AAK-C-049
|  | Obohen - Oboka | 1.4 |  |  | CR-AAK-C-057
|  | Tuakwa-Odonkwa | 1.3 |  |  | CR-AAK-A-047
20.9
| Kwabiako Jn - Kofikwaa | Kwabiako Jn - Kofikwaa | 4 | AS | Reshaping | CR-AES-A-017 | Afua Amanquah | 2010-10-05 | 2010-11-22 | 2011-02-22 | 23218.08 | 18171.05 | 100 | 11.1km of Grass Cutting and Reshaping completed |  |  | GOG
|  | Esusu - Akwakwa | 2.1 |  |  | CR-AGO-C-026
|  | Obrakyire - Kwakwabi | 4.2 |  |  | CR-AES-A-002
|  | Amowi Jn - Amowi | 1 |  |  | CR-AES-A-004
11.3
| WINNEBA - OJOBI PH 1 | WINNEBA - OJOBI PH 1 | 5.535 | EF | Reshaping | CR-AES-I-039 | J. K. BONNEY CONT WKS. | 2010-12-13 | 2011-01-04 | 2011-04-04 | 30676.7 | 14508.4 | 100 | 5.54km of Grass Cutting and Reshaping completed | Work in Progress |  | GOG
5.535
| WINNEBA - OJOBI PH 2 | WINNEBA - OJOBI PH 2 | 4.365 | EF | Reshaping | CR-AES-I-039 | SALAMBA AGENCIES | 2010-12-13 | 2011-02-04 | 2011-05-04 | 25708.27 | 16740.2 | 100 | 4.8km of Grass Cutting and Reshaping completed |  |  | GOG
4.365
| WINNEBA - OJOBI PH 3 | WINNEBA - OJOBI PH 3 | 9.2 | EF | Reshaping | CR-AES-I-039 | STRATEGIC HERITAGE SERVICES LTD | 2010-12-13 | 2011-01-03 | 2011-04-03 | 42235.6 | 31515.74 | 100 | 8.7km of Grass Cutting and Reshaping completed |  |  | GOG
9.2
| Odoben - Brakwaa Ph 1 | Odoben - Brakwaa | 8 | AOB | Grasscutting | CR-ASI-C-023 | Desapcon Co. Ltd. |  |  |  | 4956 | [5 empty] | GOG
8
| Odoben - Brakwaa Ph 2 | Odoben - Brakwaa | 7.7 | AOB | Grasscutting | CR-ASI-C-023 | Francotouch Services Ltd. |  |  |  | 4710.8 | [5 empty] | GOG
7.7
| Atonsu - Dominase - Nyameyenam | Atonsu - Nyameyenam | 12 | ASN | Grasscutting | CR-ASN-A-041 | Lesse Co. Ltd. | 2010-09-20 | 2010-10-28 | 2010-12-27 | 7170 | 6350.95 | 100 | 10.5km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/03/10 | GOG | 1
12
| Dwenuama Jn - Dwenuama | Dwenuama Jn - Dwenuama |  | ASN | Grasscutting | CR-ASN-A-030 | Caks Ltd. | 2010-09-02 |  |  | 3660 | [5 empty] | GOG
|  | Kwesi Adu - Wawase |  |  |  | CR-ASN-C-026
| Aworabo Jn- Aworabo | Aworabo Jn- Aworabo | 8 | ASN | Grasscutting | CR-ASN-C-022 | Hanimart Ventures | 2010-09-07 | 2010-10-28 | 2010-12-27 | 4892 | 4770.05 | 100 | 7.25km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/05/10 | GOG | 1
8
| Fosu - Ghana Telecom | Fosu - Ghana Telecom | 1.5 | ASN | Grasscutting | CR-ASN-A-043 | Will Joan Ent. | 2010-09-02 | 2010-11-02 | 2011-01-02 | 8500 | 6109 | 100 | 11.35km of Grass Cutting completed |  |  | GOG
|  | Fosu - Odumase | 4 |  |  | CR-ASN-A-040
|  | Gangan - Ankaa | 3.2
|  | Samankrom Jn - Samankrom | 2.2
|  | Sikanbodua Jn - Sikanbodua | 2.5
13.4
| Odumase - Asibrim | Odumase - Asibrim | 15 | ASN | Grasscutting | CR-ASN-C-026 | Bobsteps Ventures | 2010-09-07 | 2010-10-20 | 2010-12-19 | 7800 | 6629.3 | 100 | 12.0km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/08/10 | GOG | 1
15
| Japan Bridge - Appoliningo | Japan Bridge - Appoliningo | 15 | ASN | Grasscutting | CR-ASN-I-017 | Little Light Ent. | 2010-09-07 | 2010-11-01 | 2011-01-31 | 9140 | 8766.8 | 100 | 14.0km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/09/10 | GOG | 1
15
| Akyianu - Armah Camp | Akyianu - Armah Camp | 6 | ASN | Grasscutting | CR-ASN-C-003 | Bo Const. | 2010-09-07 | 2010-11-01 | 2011-01-31 | 3840 | 3800.45 | 100 | 5.7km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/10/10 | GOG | 1
6
| Adiembra - Nuanua | Adiembra - Nuanua | 14 | ASSIN SOUTH | Grasscutting | CR-ASS-I-036 | NKY Const. Ltd. | 2010-06-09 | 2010-10-12 | 2010-12-11 | 8516 | 8331.1 | 100 | 14.0km of Grass Cutting completed |  | DFR/CR/AS/GC/GOG/11/10 | GOG | 1
14
| Ando Adadientem -Adubiase | Ando-Adadientem-Adubiase | 14 | ASSIN SOUTH | Grasscutting | CR-ASS-C-001 | Forstwum Venturs | 2010-06-09 | 2010-10-12 | 2010-12-11 | 8516 | 6932 | 100 | 12.0km of Grass Cutting completed |  | DFR/CR/AS/GC/GOG/12/10 | GOG | 1
14
| FRAMASE JN - TUMFUKOR | FRAMASE JN - TUMFUKOR | 6.4 | ASSIN SOUTH | Grasscutting | CR-ASS-A-009 | Lilyboat Ltd. | 2010-06-09 | 2010-10-28 | 2010-12-27 | 3925.6 | 3902 | 100 | 7.9km of Grass Cutting completed |  | DFR/CR/AS/GC/GOG/13/10 | GOG | 1
6.4
| POTSIN - AMOANDA | POTSIN - AMOANDA | 14 | GOMOA EAST | Grasscutting | CR-GOM-I-046 | Kpanyaraga Gh. Ltd. | 2010-09-16 | 2010-10-21 | 2010-12-20 | 8516 | 8424 | 100 | 14.0km of Grass Cutting completed |  | DFR/CR/GE/GC/GOG/14/10 | GOG | 1
14
| POTSIN JN - AWOREMBEREW | POTSIN JN - AWOREMBEREW | 10.2 | GOMOA EAST | Grasscutting | CR-GOM-C-042 | Joseph S. Y. Ent. | 2010-10-08 | 2010-11-29 | 2011-01-29 | 6057.6 | 4902 | 100 | 8.6km of Grass Cutting completed |  | DFR/CR/GE/GC/GOG/15/10 | GOG
10.2
| OKUSHIBIADZE - FETTEH | OKUSHIBIADZE - FETTEH | 5.8 | GOMOA EAST | Grasscutting | CR-AES-C-040 | Tecson Co. Ltd. |  |  |  | 4584 |  | 100 | 5.8km of Grass Cutting completed |  |  | GOG
5.8
| ATAABADZE -ABREM AGONA | ATAABADZE -ABREM AGONA | 12 | KEEA | Grasscutting | CR-KEE-I-015 | Hanimart Ventures | 2010-09-14 | 2010-11-26 | 2011-01-25 | 7444 | 7100.65 | 100 | 18.1km of Grass Cutting completed |  | DFR/CR/KEEA/GC/GOG/16/10 | GOG | 1
12
| EGYINKUMA - AKWEIKROM | EGYINKUMA - AKWEIKROM | 2 | THLD | Grasscutting | CR-LDE-A-007 | Dewuboa Ent. | 2011-01-13 | 2011-03-17 | 2011-05-17 | 4018 | 3422.6 | 100 | 6.1km of Grass Cutting completed |  |  | GOG
|  | EKURAKESE JN - EKURAKESE | 4.4 |  |  | CR-LDE-A-042
6.4
| PRASO - BIMPONSO | PRASO - BIMPONSO | 10 | THLD | Grasscutting | CR-LDE-I-001 | Debrasko Co. Ltd. |  |  |  | 9500 | 6895.25 | 100 |  |  |  | GOG
10
| MINTASO - ADADEKOFI | MINTASO - ADADEKOFI | 12 | THLD | Grasscutting | CR-LDE-I-032 | Theokalma Ent. | 2011-01-13 | 2011-02-03 | 2011-04-03 | 7490 | 6708.3 | 100 | 11.9km of Grass Cutting completed |  |  | GOG
12
| NUAMAKROM - MINTA | NUAMAKROM - MINTA | 6.7 | THLD | Grasscutting | CR-LDE-C-003 | Sosotek Ltd. |  |  |  | 4204 | [5 empty] | GOG
6.7
| HEMANG - BRUKUSU | HEMANG - BRUKUSU | 8.6 | THLD | Grasscutting | CR-LDE-A-048 | Ancomec Co. Ltd. |  |  |  | 5382 | [5 empty] | GOG
8.6
| AKROMAIN JN - NYAMEKYEMASO | AKROMAIN JN - NYAMEKYEMASO | 7 | THLD | Grasscutting | CR-LDE-C-005 | Akakyere Ventures Ltd. | 2011-01-13 | 2011-04-12 | 2011-06-12 | 4390 | 3167.2 | 100 | 6.3km of Grass Cutting completed |  |  | GOG
7
| HEMANG - BAAKONDZIDZI | HEMANG - BAAKONDZIDZI | 8.2 | THLD | Grasscutting | CR-LDE-A-051 | Tecson Co. Ltd. |  |  |  | 5098 | 7572.69 |  |  |  |  | GOG
8.2
| ANTWIKWAA JN - ANTWIKWAA | ANTWIKWAA JN - ANTWIKWAA | 2.1 | THLD | Grasscutting | CR-LDE-A-057 | Joyous-Bee Ent. | 2011-01-13 | 2011-02-04 | 2011-04-04 | 4884.8 | 4117.3 | 100 | 6.1km of Grass Cutting completed |  |  | GOG
|  | Brukusu-Nyamebekyere | 2.8 |  |  | CR-LDE-A-048
|  | BERTIMOR - ALERT - AGO | 4 |  |  | CR-LDE-A-050
8.9
| KUMAKROM - KENKUASE | KUMAKROM - KENKUASE | 5.6 | THLD | Grasscutting |  | Afua Afeiduwa Works |  |  |  | 3572 | [5 empty] | GOG
5.6
| PRASO - BIMPONSO PH 2 | PRASO - BIMPONSO PH 2 | 15 | THLD | Grasscutting | CR-LDE-I-001 | Will Joan Ent. |  |  |  | 9420 | 8245 | 100 | 15.0km of Grass Cutting completed |  |  | GOG
15
| AMOAFO - AKYENEKROM | AMOAFO - AKYENEKROM | 8 | UDE | Grasscutting | CR-UED-C-015 | Build Trust Const. Ltd. | 2010-09-23 | 2010-10-07 | 2010-12-07 | 8337.6 | 7837.85 | 100 | 10.85km of Grass Cutting completed |  | DFR/CR/UDE/GC/GOG/25/10 | GOG | 1
|  | ZION NO2 - ZION CAMP | 2.7
10.7
| ADEADE JN - ADEADE | ADEADE JN - ADEADE | 3.5 | UDW | Grasscutting | CR-UED-A-012 | Coky Ent. | 2010-09-14 | 2011-01-13 | 2011-03-13 | 4962 | 4805.26 | 100 | 8.0km of Grass Cutting completed |  |  | GOG
|  | BETHLEHEM - OTOMKROM | 4.5 |  |  | CR-UED-A-011
8
| ASIKUMA - BESEASE | ASIKUMA - BESEASE | 15 | AOB | Grasscutting | CR-ASI-I-005 | Francotouch Services Ltd. |  |  |  | 8628 | [5 empty] | GOG
15
| BESEASE - ESHIEM | BESEASE - ESHIEM | 5 | AOB | Grasscutting | CR-AJU-C-001 | Dygate Gh Ltd. |  |  |  | 3080 | [5 empty] | GOG
5
| ASSIN SWEDRU - BISIDUASE | ASSIN SWEDRU - BISIDUASE | 8.7 | ASN | Grasscutting |  | Felko Ent. | 2010-07-09 | 2010-11-01 | 2011-01-31 | 5334.8 | 5252.1 | 100 | 8.1km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/29/10 | GOG | 1
8.7
| ODUMASE - OBOBAKOKROWA | ODUMASE - OBOBAKOKROWA | 8.7 | ASN | Grasscutting |  | NKY Const. Ltd. | 2010-09-02 | 2010-09-27 | 2010-11-27 | 4150 | 3988 | 100 | 4.8km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/30/10 | GOG | 1
8.7
| ODUMASE - KWESI ADU | ODUMASE - KWESI ADU | 12 | ASN | Grasscutting | CR-ASN-C-023 | Lamanasa Ent. | 2010-07-09 | 2010-10-25 | 2010-12-24 | 7424 | 7366.6 | 100 | 12.0km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/31/10 | GOG | 1
12
| JUASO COCOA STATION - OTABIL NKWANTA | JUASO COCOA STATION - OTABIL NKWANTA | 6 | ASN | Grasscutting | CR-ASN-A-038 | Benyark Ltd. | 2010-09-02 | 2010-09-16 | 2010-11-12 | 3636 | 3561.2 | 100 | 6.7km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/32/10 | GOG | 1
6
| ABOTAREYE - DIADOKONO | ABOTAREYE - DIADOKONO | 7.4 | ASN | Grasscutting |  | Ebisanso Co. Ltd. | 2010-09-02 | 2011-03-21 | 2011-05-21 | 4560 | 4443.96 | 100 | 7.2km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/33/10 | GOG | 1
7.4
| ANUM JN - DONKORKROM | ANUM JN - DONKORKROM | 9 | ASN | Grasscutting | CR-ASN-A-012 | Lilyboat Ltd. | 2010-09-02 | 2010-09-27 | 2010-11-27 | 5238 | 5222.4 | 100 | 9.0km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/34/10 | GOG | 1
9
| AKONFUDI - ASUANKUMASU CAMP | AKONFUDI - ASUANKUMASU CAMP | 4 | ASN | Grasscutting |  | Nu-Skin Ltd. | 2010-09-02 | 2010-09-27 | 2010-11-27 | 3844 | 3705.29 | 100 | 6.3km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/35/10 | GOG | 1
|  | ODUMASE - NKUKUASA | 2.5
6.5
| BEREKU - NINKYISU | BEREKU - NINKYISU | 11 | ASN | Grasscutting | CR-ASN-A-014 | B-Kham Co. Ltd. | 2010-07-09 | 2010-10-28 | 2010-12-27 | 6630 | 6455.3 | 100 | 10.0km of Grass Cutting completed |  | DFR/CR/AN/GC/GOG/37/10 | GOG | 1
11
| ANYINABRIM - BAAKO | ANYINABRIM - BAAKO | 13.4 | ASSIN SOUTH | Grasscutting | CR-ASS-I-044 | Lesse Co. Ltd. | 2010-06-09 | 2010-10-28 | 2010-12-27 | 8772 | 6554.1 | 100 | 6.9km of Grass Cutting completed |  | DFR/CR/AS/GC/GOG/38/10 | GOG | 1
13.4
| ASSIN NYANKUMASE - JAKAI | ASSIN NYANKUMASE - JAKAI | 13.4 | ASSIN SOUTH | Grasscutting | CR-ASS-C-011 | Yadovic Ltd. | 2010-06-09 | 2010-10-28 | 2010-12-27 | 8772 | 6554.1 | 100 | 6.9km of Grass Cutting completed |  | DFR/CR/AS/GC/GOG/40/10 | GOG | 1
13.4
| AKOTI JN - DESUM | AKOTI JN - DESUM | 10 | GOMOA EAST | Grasscutting | CR-GOM-C-048 | Voroma Complex Ltd. | 2010-09-16 | 2010-10-07 | 2010-12-07 | 6100 | 6100 | 100 | 10.0km of Grass Cutting completed |  | DFR/CR/GE/GC/GOG/42/10 | GOG | 1
10
| FETTEH - KROBOAKYIR | FETTEH - KROBOAKYIR | 4.3 | GOMOA EAST | Grasscutting | CR-AES-C-042 | Masagri Co. Ltd. | 2010-09-16 | 2010-10-21 | 2010-12-20 | 3310.8 | 3226.3 | 100 | 4.3km of Grass Cutting completed |  | DFR/CR/GE/GC/GOG/43/10 | GOG | 1
4.3
| BUADUATTA JN - FAWOMANYE | BUADUATTA JN - FAWOMANYE | 15 | GOMOA EAST | Grasscutting | CR-GOM-I-047 | Amoh Mensah Co. Ltd. | 2010-09-16 | 2010-10-21 | 2010-12-20 | 9120 | 9032 | 100 | 15.0km of Grass Cutting completed |  | DFR/CR/GE/GC/GOG/44/10 | GOG | 1
15
| ESSAMAN - ANQUANDA | ESSAMAN - ANQUANDA | 4.1 | KEEA | Grasscutting | CR-KEE-C-014 | Appiafo Works Ltd. | 2010-09-20 | 2010-10-26 | 2010-12-25 | 5789 | 5784.5 | 100 | 9.5km of Grass Cutting completed |  | DFR/CR/KEEA/GC/GOG/45/10 | GOG
|  | ANTADO JN - ANTADO | 0.8 |  |  | CR-KEE-A-035
|  | ABROBEANO JN - ABROBEANO | 1.7 |  |  | CR-KEE-A-031
|  | Dompoase-Kokoado – Kissi | 3.4 |  |  | Not Available
|  | DOMPOASE JN - DOMPOASE | 1.6 |  |  | CR-KEE-A-012
11.6
| KUMAKROM - KENKUASE | KUMAKROM - KENKUASE | 5.6 | THLD | Grasscutting |  | Afua Afeiduwa Wks | 2011-01-13 | 2011-03-04 | 2011-05-04 | 3572 | 3487.2 | 100 | 5.6km of Grass Cutting completed |  | DFR/CR/THLD/GC/GOG/50/10 | GOG
5.6
| ASIKUMA - AKWABOA PH 1 | ASIKUMA - AKWABOA | 17.1 | UDE | Grasscutting | CR-UED-I-030 | Coky Ent. | 2010-09-20 | 2011-01-13 | 2011-03-13 | 10412.6 | 8204 | 100 | 17.0km of Grass Cutting completed |  |  | GOG
17.1
| AMPENYI JN - AMPENYI | AMPENYI JN - AMPENYI | 3.6 | KEEA | Grasscutting | CR-KEE-A-024 | Skills & Sirgaul Ltd. | 2010-09-20 | 2010-10-26 | 2010-12-25 | 5696.8 | 5552.8 | 100 | 8.0km of Grass Cutting completed |  | DFR/CR/KEEA/GC/GOG/53/10 | GOG | 1
|  | ABURANSA - KAFODZIDZI | 5.6 |  |  | CR-KEE-A-032
9.2
| ANDO- ADADIENTEM- ADUBIASE PH 2 | ANDO- ADADIENTEM- ADUBIASE PH 2 | 14 | ASSIN SOUTH | Grasscutting | CR-ASS-C-001 | Sybil-Princ Ltd. | 2010-07-09 | 2010-11-14 | 2011-01-05 | 8486 | 7252.9 | 100 | 14.0km of Grass Cutting completed |  | DFR/CR/AS/GC/GOG/54/10 | GOG | 1
14
| ESSAMAN - BANTAMA | ESSAMAN - BANTAMA | 4.5 | KEEA | Grasscutting | Not Available | Speedway Const. Ltd. | 2010-09-20 | 2010-10-28 | 2010-12-27 | 3536 | 3513.8 | 100 | 4.0km of Grass Cutting completed |  | DFR/CR/KEEA/GC/GOG/56/10 | GOG | 1
4.5
| AYENSUDU JN - BRENU AKYINIM | AYENSUDU JN - BRENU AKYINIM | 5.1 | KEEA | Grasscutting | CR-KEE-A-019 | Gracious Lawrence Ltd. | 2010-09-14 | 2010-12-16 | 2011-02-16 | 3935.6 | 3910 | 100 | 7.65km of Grass Cutting completed |  | DFR/CR/KEEA/GC/GOG/57/10 | GOG
|  | KISSI - AKYEASE JN | 1.35 |  |  | Not Available
|  | KISSI JN - KISSI | 0.8 |  |  | Not Available
7.25
Note on D5: CR3:

## ROUTINE 2011
DEPARTMENT OF FEEDER ROADS
CENTRAL REGION
MONTHLY PROGRESS REPORT FOR AUGUST 2013
NO. | PROJECT NAME |  | ROAD LENGTH (KM) | PROJECT LOCATION (DISTRICT) | ACTIVITY | ROAD NUMBER | CONTRACTOR | WORK PERIOD |  |  | CONTRACT SUM (GH¢) | TOTAL AMOUNT CERTIFIED | % COMPLETED | LENGTH COMPLETED | REMARKS | CONTRACT NUMBER | FUNDING & SOURCES | CERT. NO
[8 empty] | AWARD | DATE OF | DATE OF
[8 empty] | DATE | COMM. | COMP.
ROAD FUND
5 | ADIANOM JN - ADIANOM & OTHER | ADIANOM JN - ADIANOM | 3.4 | ASS | Reshaping | CR-ASS-A-042 | Annointed Star & Trd. Ltd. | 2011-09-25 |  |  | 18974.8 |  |  |  |  | DFR/CR/AS/RESH/GOG/1/11 | GOG
|  | ABOABO CAMP - AKOTEY | 4.7 |  |  | CR-ASS-A-040
8.1
5 | NGRESI - OTABILKROM & OTHERS | KWAME ANNAN JN - KWAME ANNAN | 1.8 | ASS | Reshaping | CR-ASS-A-002 | Walterduam Ent. Ltd. | 2011-09-25 | 2011-12-15 | 2012-03-15 | 23235.4 |  |  |  |  | DFR/CR/AS/RESH/GOG/2/11 | GOG
|  | DADIESO - KAASANKWA | 2.5 |  |  | CR-ASS-A-030
|  | NGRESI - OTABILKROM | 5.8 |  |  | CR-ASS-A-025 | [10 empty] | COCOA
10.1
| JAKIA - TUMFOKOR | JAKIA - TUMFOKOR | 7 | ASS | Reshaping | CR-ASS-C-011 | Sweet City Ent. | 2011-09-25 | 2011-11-28 | 2012-02-28 | 16072 |  |  |  |  | DFR/CR/AS/RESH/GOG/3/11 | GOG
7
5 | DOSII - BETWEASE & OTHER | TUMFOKOR - BANKYASE JN | 4 | ASS | Reshaping | CR-ASS-C-011 | Jobewill Ltd. | 2011-09-25 |  |  | 21292 |  |  |  |  | DFR/CR/AS/RESH/GOG/4/11 | GOG
|  | DOSII - BETWEASE | 5 |  |  | CR-ASS-A-016
9
| AYAASE - KRUWA PH 1 | AYAASE - KRUWA | 9 | ASS | Reshaping | CR-ASS-I-018 | Anafo Const Works | 2011-09-25 | 2011-11-18 | 2012-02-18 | 21422 | 20609.26 | 100 | 9.0km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/5/11 | GOG
9
| AYAASE - KRUWA PH 2 | AYAASE - KRUWA | 8 | ASS | Reshaping | CR-ASS-I-018 | J.E.A. Aggrey & Sons Ltd. | 2011-09-25 | 2012-01-03 | 2012-04-03 | 18584 | 13028.27 | 100 | 6.1km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/6/11 | GOG
8
1 | NKUBEM - AMANBETE & OTHERS | NKUBEM - AMANBETE | 3.4 | ASS | Reshaping | CR-ASS-C-032 | Samwilco Const. Ltd. | 2011-09-25 | 2011-12-12 | 2012-04-12 | 33705.6 | 23412.84 | 100 | 14.4km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/7/11 | GOG
|  | NSUAKYIR - HOMAHOM | 4.2 |  |  | CR-ASS-C-034
|  | KWOAFOKROM - AKOYEM | 2.8 |  |  | CR-ASS-A-059
|  | ACHIASE - ONIPANKA | 4.3 |  |  | CR-ASS-A-026
14.7
5 | CHAPESS CONGA JN - GOMOA MAMPONG & OTHER | CHAPESS CONGA JN - GOMOA MAMPONG | 6.8 | GOM | Reshaping | CR-GOM-C-037 | Adeaq Co. Ltd. | 2011-09-25 | 2011-12-15 | 2012-03-15 | 36934 | 33507.56 | 100 | 15.9km of Grass Cutting and Reshaping completed |  | DFR/CR/GE/RESH/GOG/8/11 | GOG
|  | ESSIWUKWA - GOMOA NYANSAKYERE JN | 9.6 |  |  | CR-GOM-I-047
16.4
1 | KWEIKROM - OKUSIBIADZE & OTHERS | KWEIKROM - OKUSIBIADZE | 5.8 | AES | Reshaping | CR-AES-C-045 | E. Speedway Const. Ltd. | 2011-09-25 | 2011-12-05 | 2012-03-05 | 29196 | 26491.55 | 100 | 12.0km of Grass Cutting and Reshaping completed |  | DFR/CR/GE/RESH/GOG/9/11 | GOG
|  | FEYENORD JN - FEYENORD | 3.2 |  |  | CR-AES-C-052
|  | FETTEH KAKRABA - NKWANTANAN | 2.5 |  |  | CR-GOM-A-055
|  | AKRAMPA JN - AKRAMPA | 1.1 |  |  | CR-AES-C-048
12.6
1 | GOMOA ESHIEM - GOMOA APPIAKROM DEBISO & OTHERS | GOMOA ESHIEM - GOMOA APPIAKROM DEBISO | 5 | GOM | Reshaping | CR-GOM-I-022 | Ruthra Const. Ltd. | 2011-09-25 | 2012-01-05 | 2012-04-05 | 32763 | 24144.44 | 100 | 9.5km of Grass Cutting and Reshaping completed |  | DFR/CR/GW/RESH/GOG/10/11 | GOG
|  | ABEADZE JN - ABEADZE | 0.6 |  |  | CR-GOM-A-002
|  | GOMOA BROFO - AGYATEME JN | 4.5 |  |  | CR-GOM-A-032
|  | GOMOA AKROPONG JN - GOMOA AKROPONG | 4.5 |  |  | CR-GOM-C-034
14.6
| AGONA POT - AMOAMAN PH 1 | AGONA POT - AMOAMAN | 10 | UED | Reshaping | CR-UED-C-007 | Fasaan Ent. Ltd. | 2011-09-25 |  | 2012-04-16 | 25020 | 19572.9 | 100 | 9.5km of Grass Cutting and Reshaping completed |  | DFR/CR/UDW/RESH/GOG/11/11 | GOG
10
| AGONA POT - AMOAMAN PH 2 | AGONA POT - AMOAMAN | 9.3 | UED | Reshaping | CR-UED-C-007 | Yadovic Ltd. | 2011-09-25 | 2012-01-17 | 2012-04-17 | 23701.2 | 15706.76 | 100 | 7.4km of Grass Cutting and Reshaping completed |  | DFR/CR/UDW/RESH/GOG/12/11 | GOG
|  | DOMINASE-CHARLESKROM | 7.4 |  |  | CR-UED-I-002
7.4
5 | AMOAMAN - ASAMAN & OTHER | AMOAMAN - ASAMAN | 6.4 | UED | Reshaping | CR-UED-I-008 | King-Kay Co. Ltd. | 2011-09-25 | 2011-12-20 | 2012-03-20 | 24373 | 23323.76 | 100 | 9.2km of Grass Cutting and Reshaping completed |  | DFR/CR/UDW/RESH/GOG/13/11 | GOG
|  | NKRONUA ANAFO - NKRONUA ATIFI | 3.5 |  |  | CR-UED-I-067
9.9
| ZION CAMP JN - BONINSUMA | ZION CAMP JN - BONINSUMA | 10.6 | UED | Reshaping | CR-UED-A-056/55 | Gbagory Const. Ltd. | 2011-09-25 | 2012-02-01 | 2012-05-02 | 25361.6 | 24192 | 100 | 10.6km of Grass Cutting and Reshaping completed |  | DFR/CR/UDW/RESH/GOG/14/11 | GOG
10.6
5 | ZION № 2 - OBRAYEKO & OTHER | ZION № 2 - OBRAYEKO | 5 | UED | Reshaping | CR-UED-C-058 | Alt Const. Ltd. | 2011-09-25 |  |  | 21541.6 |  | 100 | 8.4km of Grass Cutting and Reshaping completed |  | DFR/CR/UDE/RESH/GOG/15/11 | GOG
|  | ZION CAMP - ZION № 2 | 3.4 |  |  | CR-UED-A-057
8.4
1 | KUNTENASI - AKURAKESE & OTHERS | KUNTENASI - AKURAKESE | 5.1 | ASI | Reshaping | CR-ASI-A-016 | Raj Co. Ltd. | 2011-09-27 | 2011-12-13 | 2012-03-27 | 33429.6 | 30004.13 | 100 | 14.40km of Grass Cutting and Reshaping completed | 4200.8 | DFR/CR/AOB/RESH/GOG/16/11 | GOG
|  | AWISAM JN - AWISAM | 1 |  |  | CR-ASI-A-021
|  | TOBOASE - AKROMAKWA | 4.3 |  |  | CR-ASI-A-012
|  | BARKO - OTROBA | 4 |  |  | Not Available | Super Technology Ent. | [9 empty] | COCOA
14.4
1 | TEGYAMOSO JN - TEGYAMOSO & OTHERS | KWAKUDUM JN - KWAKUDUM | 1.8 | UED | Reshaping | CR-UED-A-044 | Rochford Co. Ltd. | 2011-09-27 | 2011-12-29 | 2012-03-29 | 20427 |  |  |  |  | DFR/CR/UDE/RESH/GOG/17/11 | GOG
|  | TEGYAMOSO JN - TEGYAMOSO | 3.1 |  |  | CR-UED-A-037
|  | KRAMOKROM CAMP - NYAMEBEKYERE | 3 |  |  | CR-UED-A-047 | Super Technology Ent. | [9 empty] | COCOA
7.9
| ASIKUMA - AKWABOA Ph1 | ASIKUMA - AKWABOA | 9 | UED | Reshaping | CR-UED-I-030 | Dakal Const. Wks | 2011-09-25 |  |  | 20608 |  |  |  |  | DFR/CR/UDE/RESH/GOG/18/11 | GOG
9
| ASIKUMA - AKWABOA Ph 2 | ASIKUMA - AKWABOA | 8.1 | UED | Reshaping | CR-UED-I-030 | Alt Const. Ltd. | 2011-09-25 |  |  | 20060 |  | 100 | 8.1km of Grass Cutting and Reshaping completed |  | DFR/CR/UDE/RESH/GOG/19/11 | GOG
8.1
5 | ASIKUMA - AYANFURI & OTHER | ASIKUMA - AYANFURI | 11.45 | UED | Reshaping | CR-UED-C-013 | Shalicoma Ltd. | 2011-09-25 | 2011-12-22 | 2012-04-23 | 37645.8 |  |  |  |  | DFR/CR/UDE/RESH/GOG/20/11 | GOG
|  | AMISSAH - ONWE | 3.5 |  |  | CR-UED-A-024 | [10 empty] | COCOA
14.95
2 | ASMA CAMP - NYARDUAM JN | ASMA CAMP - NYARDUAM JN | 9.8 | UED | Reshaping | CR-UED-C-050 | Bestimmt CSA Ltd. | 2011-09-25 | 2012-04-06 | 2012-07-06 | 23760.8 | 22086.6 | 100 | 9.8km of Grass Cutting and Reshaping completed |  | DFR/CR/UDE/RESH/GOG/21/11 | GOG
9.8
2 | AWISEM - ASAMAN | AWISEM - ASAMAN | 6 | UDE | Reshaping | CR-UED-A-049 | Amplicon Ent. | 2011-09-25 | 2012-01-19 | 2012-04-19 | 15368 | 14874.05 | 100 | 5.5km of Grass Cutting and Reshaping completed |  | DFR/CR/UDE/RESH/GOG/22/11 | GOG
6
2 | DUNKWA - NKOTOMSO PH1 | DUNKWA - NKOTOMSO | 13 | UDE | Reshaping | CR-UED-C-001 | Approtech Impex Ltd. | 2011-09-25 | 2011-12-29 | 2012-03-29 | 30510 | 29002.43 | 100 | 13.0km of Grass Cutting and Reshaping completed |  | DFR/CR/UDE/RESH/GOG/23/11 | GOG
13
5 | AKONFUDI - ASUOKUMASO & OTHERS | AKONFUDI - ASUOKUMASO | 3.5 | ASN | Reshaping | CR-ASN-A-028 | Konasah Ent. Ltd. | 2011-09-25 |  |  | 30342 |  | 100 | 13.3km of Grass Cutting and Reshaping completed |  | DFR/CR/AN/RESH/GOG/24/11 | GOG
|  | AKONFUDI - ATWEREBONDA | 4 |  |  | CR-ASN-A-020
|  | BENUYE - ATAKWAA | 5.8 |  |  | CR-ASN-A-003 | [10 empty] | COCOA
13.3
5 | DWENAMA JN - DWENAMA TOGO & OTHER | DWENAMA JN - DWENAMA TOGO | 3 | ASN | Reshaping | CR-ASN-A-030 | Opakoh Ent. | 2011-09-25 | 2011-12-28 | 2012-04-28 | 29662 |  |  |  |  | DFR/CR/AN/RESH/GOG/25/11 | GOG
|  | JAPAN BRIDGE - NINGO SCH | 10 |  |  | CR-ASN-I-017 | [10 empty] | COCOA
13
2 | BRONYIBIMA - BERASE | BRONYIBIMA - BERASE | 12 | KEE | Reshaping | CR-KEE-C-007 | Asaff Co. Ltd. | 2011-09-25 | 2012-01-19 | 2012-04-19 | 26499 | 23488.88 | 100 | 11.0km of Grass Cutting and Reshaping completed |  | DFR/CR/KEEA/RESH/GOG/26/11 | GOG
12
5 | ODUMASE NKRANFOUM - JAPAN BRIDGE & OTHER | ODUMASE NKRANFOUM - JAPAN BRIDGE | 11.5 | ASN | Reshaping | CR-ASN-C-023 | Musabee Ent. | 2011-09-25 | 2011-11-08 | 2012-02-08 | 34256 | 34123.7 | 100 | 14.0km of Grass Cutting and Reshaping completed |  | DFR/CR/AN/RESH/GOG/27/11 | GOG
|  | BEREKU - NINKYINSO | 11 |  |  | CR-ASN-A-014
|  | KWESI ADU - WAWASE | 3 |  |  | CR-ASN-C-024
14
5 | DOKODOKO - ASHIRE ATIEKU & OTHERS | DOKODOKO - ASHIRE ATIEKU | 5.5 | THLD | Reshaping | CR-LDE-I-022 | Nataco Beach Resort & Co. Ltd. | 2011-09-25 | 2011-12-20 | 2012-04-20 | 34620 |  |  |  |  | DFR/CR/THLD/RESH/GOG/28/11 | GOG
|  | ATIEKU - OSENAGYA | 7.5 |  |  | CR-LDE-C-027
|  | NYINASE - ADUGYAA | 2 |  |  | CR-LDE-A-021 | [10 empty] | COCOA
15
5 | NUAMAKROM - KENKUASE & OTHER | NUAMAKROM - KENKUASE | 5.6 | THLD | Reshaping | CR-LDE-A-004 | Gudmann Int. Ltd. | 2011-09-25 | 2012-01-11 | 2012-04-11 | 27487 |  |  |  |  | DFR/CR/THLD/RESH/GOG/29/11 | GOG
|  | KENKUASE JN - KENKUASE | 5.5 |  |  | CR-LDE-A-047 | [10 empty] | COCOA
11.1
2 | AKROMAIM JN - NKWANKYEMASO | AKROMAIM JN - NKWANKYEMASO | 6.8 | THLD | Reshaping | CR-LDE-C-005 | Nataco Beach Resort & Co. Ltd. | 2011-09-25 | 2012-02-17 | 2012-05-17 | 15456.4 | 15434.26 | 100 | 7.1km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/30/11 | GOG
6.8
5 | JUKWA - ACHIASE & OTHERS | JUKWA - ACHIASE | 4.2 | THLD | Reshaping | CR-LDE-A-071 | Jonsab Ent. Ltd. | 2011-09-25 | 2012-01-02 | 2012-05-02 | 31210.4 | 24861.16 | 100 | 11.2km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/31/11 | GOG
|  | JUKWA - AMANASE | 3.3 |  |  | CR-LDE-A-067
|  | JUKWA - WATRESO | 4 |  |  | CR-LDE-A-072
|  | NYAMEANI JN - NYAMEANI | 1.8 |  |  | CR-LDE-A-073 | [10 empty] | COCOA
13.3
5 | WAWASE - ATWEREBOANDA & OTHER | WAWASE - ATWEREBOANDA | 6.5 | THLD | Reshaping | CR-LDE-C-053 | Walterduam Ent. Ltd. | 2011-09-25 | 2011-12-15 | 2012-03-15 | 27504 | 16756.23 | 100 | 9.75km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/32/11 | GOG
|  | WAWASE - AYEBISHWE | 5.5 |  |  | CR-LDE-C-054 | [10 empty] | COCOA
12
| DANYASE CAMP - MANFI PRA RIVER | DANYASE CAMP - MANFI PRA RIVER | 6.2 | THLD | Reshaping | CR-LDE-A-012 | Line-Ka Ent. | 2011-09-25 | 2011-12-19 | 2012-03-19 | 14157.1 | 9003.7 | 100 | 5.5km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/33/11 | GOG
6.2
5 | ABRAFO - GYEWARE & OTHERS | ABRAFO - GYEWARE | 4.3 | THLD | Reshaping | CR-LDE-C-065 | Ark Const Works Ltd. | 2011-09-25 | 2011-12-05 | 2012-03-05 | 27786.6 | 25706.64 | 100 | 11.0km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/34/11 | GOG
|  | EDZIYAW - AGRIC BUNGALOW | 2.6 |  |  | CR-LDE-C-068
|  | ABRAFO - BEKAWOPA | 4.9 |  |  | CR-LDE-C-066 | [10 empty] | COCOA
11.8
2 | PRASO № 1 - NTIAMOAH | PRASO № 1 - NTIAMOAH | 13 | THLD | Reshaping | CR-LDE-A-044 | Caks Ltd. | 2011-09-25 | 2011-12-19 | 2012-04-19 | 29906 | 27390.2 | 100 | 13.0km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/35/11 | GOG
13
| OTUANO CAMP - ABADWESE | OTUANO CAMP - ABADWESE | 6 | THLD | Reshaping | CR-LDE-C-046 | Buabeng Adu Contract Wks | 2011-09-25 | 2011-12-19 | 2012-03-19 | 14153 | 14069.4 | 100 | 6.3km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/36/11 | GOG
6
5 | EGYIKUMA - AKWEIKROM & OTHER | EGYIKUMA - AKWEIKROM | 6.4 | THLD | Reshaping | CR-LDE-A-007 | Sung Nuo Co. Ltd. | 2011-09-25 |  |  | 24688.4 |  | 100 | 6.75km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/37/11 | GOG
|  | AKURAKESE JN - ASEREKWEKU | 4.4 |  |  | CR-LDE-A-042 | [10 empty] | COCOA
10.8
| NUAMAKROM - MINTAH | NUAMAKROM - MINTAH | 6.7 | THLD | Reshaping | CR-LDE-C-003 | Cob-Tay Const. Wks. | 2011-09-25 | 2011-11-25 | 2012-02-25 | 16305 | 16203.31 | 100 | 6.7km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/38/11 | GOG
6.7
1 | MESUNKWA - FOTWEKROM & OTHERS | MESUNKWA - FOTWEKROM | 2.7 | AAK | Reshaping | CR-AAK-A-005 | A.B. & K Ltd. | 2011-09-27 | 2012-03-28 | 2012-07-27 | 35964 |  |  |  |  | DFR/CR/AAK/RESH/GOG/39/11 | GOG
|  | SRAFA JN - ASUANSI | 5.7 |  |  | CR-AAK-A-012
|  | ABURA DUNKWA - APENKWAKROM | 6.7 |  |  | CR-AAK-A-001
|  | APENKWAKROM - NSUNYAMEYE | 1.5 |  |  | CR-AAK-A-002
16.6
2 | AYENSUDO - DWABOR | AYENSUDO - DWABOR | 11 | KEE | Reshaping | CR-KEE-C-020 | Walker Ent. Ltd. | 2011-09-25 | 2011-11-23 | 2012-02-23 | 25274 | 24669.37 | 100 | 11.0km of Grass Cutting and Reshaping completed |  | DFR/CR/KEEA/RESH/GOG/40/11 | GOG
11
1 | GYEMPOHKROM JN - GYEMPOHKROM & OTHERS | GYEMPOHKROM JN - GYEMPOHKROM | 5.3 | UED | Reshaping | CR-UED-A-064 | Seidusco Ent. | 2011-09-27 | 2011-12-08 | 2012-04-08 | 43053 | 37714.68 | 100 | 15.1km of Grass Cutting and Reshaping completed |  | DFR/CR/UDE/RESH/GOG/41/11 | GOG
|  | SUBRISO JN - SUBRISO | 1.5 |  |  | CR-UED-A-034
|  | BUABIN - SOBROSO | 1.5 |  |  | CR-UED-A-027
|  | MBRADAN - NKWANTA | 0.8 |  |  | CR-UED-A-029
|  | BUABIN - KONTOKROM | 3 |  |  | CR-UED-A-025
|  | ZION CAMP - ZION № 2 | 3.4 |  |  | Not Available
|  | DENKYIRA FOSO - ONE POUND | 5.2 |  |  | CR-UED-A-052 | Super Technology Ent. | [9 empty] | COCOA
20.7
2 | DUNKWA - NKOTOMSO PH 2 | DUNKWA - NKOTOMSO | 12.2 | UED | Reshaping | CR-UED-C-001 | Jasima Co. Ltd. | 2011-09-27 | 2012-01-25 | 2012-05-25 | 28704 | 28235.13 | 100 | 12.0km of Grass Cutting and Reshaping completed |  | DFR/CR/UDE/RESH/GOG/42/11 | GOG
12.2
3 | MOSEASO - SONYAMEKODU & Others | MOSEASO - SONYAMEKODU | 5.6 | THLD | Reshaping | CR-LDE-A-030 | Graduate Ventures Ltd. | 2011-09-27 | 2011-12-01 | 2012-04-27 | 41702 | 40030.87 | 100 | 17.20km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/43/11 | GOG
|  | PRASO - NYAMEBEKYERE | 4.2 |  |  | Not Available
|  | EBEM - MBAANIAYE | 7.2 |  |  | CR-LDE-A-067
17
4 | NSENE JN - NSENE & Others | NSENE JN - NSENE | 2.4 | ASS | Reshaping | CR-ASS-C-019 | Habsal Co. Ltd. | 2011-09-27 | 2012-01-06 | 2012-05-06 | 33760.8 | 28737.78 | 100 | 14.20km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/44/11 | GOG
|  | ASSIN KRUWA - KROFOFORMU | 5 |  |  | CR-ASS-A-057
|  | NKWANTA - BONKOTU | 1.7 |  |  | CR-ASS-A-058
|  | DAMSEKROM JN - DAMSEKROM | 1 |  |  | CR-ASS-C-021
|  | FRAMASE JN - DAMSEKROM JN | 4.5 |  |  | CR-ASS-I-018
14.6
5 | ABOTAREYE - DIADOKONO & OTHER | ABOTAREYE - DIADOKONO | 6 | ASN | Reshaping | CR-ASN-A-052 | Sedben Investment | 2011-09-27 | 2011-11-20 | 2012-03-20 | 33052 | 33042.61 | 100 | 12.6km of Grass Cutting and Reshaping completed |  | DFR/CR/AN/RESH/GOG/45/11 | GOG
|  | AKYIANO - ARMAH CAMP | 7 |  |  | CR-ASN-A-037 | [10 empty] | COCOA
13
7 | TREPOSO - ADABOE & Others | TREPOSO - ADABOE | 5 | UED | Reshaping | CR-UED-A-005 | Konasah Ent. Ltd. | 2011-09-27 | 2011-12-29 | 2012-04-29 | 28460 | 27926.46 | 100 | 11.2km of Grass Cutting and Reshaping completed |  | DFR/CR/UDW/RESH/GOG/46/11 | GOG
|  | WAMPEM JN - WAMPEM | 3.4 |  |  | Not Available
|  | FOBINSO JN - FOBINSO | 2.8 |  |  | CR-UED-A-021 | [10 empty] | COCOA
11.2
| Apenkwakrom - Obokrom Jn | Apenkwakrom - Obokrom Jn | 3.7 | AAK | Reshaping | CR-AAK-C-003 | Big Ben Eng. Ltd. | 2011-09-27 | 2011-12-21 | 2012-04-23 | 34594.4 |  |  |  |  | DFR/CR/AAK/RESH/GOG/47/11 | GOG
|  | Asuansi - Obokrom | 2.7 |  |  | CR-AAK-A-041
|  | Odumano - Akropong | 5.3 |  |  | CR-MFA-A-030
|  | Akropong - Kwaakron | 3.6 |  |  | Not Available
15.3
| Asomdwee - Okyeriku | Asomdwee - Okyeriku | 3.2 | AAK | Reshaping | CR-AAK-C-056 | Cest Bonne Const. Ltd. | 2011-09-27 | 2011-11-01 | 2012-03-01 | 30693.4 | 26423.3 | 100 | 12.10km of Grass Cutting and Reshaping completed |  | DFR/CR/AAK/RESH/GOG/48/11 | GOG
|  | Asuansi - Okyeriku | 3.9 |  |  | CR-AAK-C-043
|  | Framase - Kruwaa | 7 |  |  | Not Available
14.1
| Acquahkrom - Amissahkrom | Acquahkrom - Amissahkrom | 14.1 | MFA | Reshaping | CR-MFA-C-021 | Bumecon Inv. Ltd. | 2011-09-27 | 2012-03-21 | 2012-07-21 | 36014 | 35930.95 | 100 | 12.0km of Grass Cutting and Reshaping completed |  | DFR/CR/MFA/RESH/GOG/49/11 | GOG
14.1
| Kwame Alert Jn - Kwame Alert - Amuza | Kwame Alert Jn - Kwame Alert - Amuza | 4 | THLD | Spot Improvement | CR-LDE-A-050 | Kobota Ent. | 2011-09-27 | 2011-12-01 | 2012-04-01 | 32329.2 | 31827 | 100 | 1№ 1800X1800mm completed. |  | DFR/CR/THLD/RESH/GOG/50/11 | #REF!
4
8 | AMANFUPONG - APERADE & Other | AMANFUPONG - APERADE | 12 | ASI | Reshaping | Not Available | K-Lia Ent. Ltd. | 2011-09-27 |  |  | 32278.8 |  |  |  |  | DFR/CR/AOB/RESH/GOG/51/11 | GOG
|  | AMANFUPONG - NYAMEBEKYERE | 2.2 |  |  | CR-ASI-A-029 | [10 empty] | COCOA
14.2
9 | ESSUSU - ABOANO & Other | ESSUSU - ABOANO | 7.3 | AGO | Reshaping | CR-AGO-C-026 | K & J Ventures | 2011-09-27 | 2012-01-25 | 2012-05-25 | 33634 |  |  |  |  | DFR/CR/AE/RESH/GOG/52/11 | GOG
|  | KENYANKOR - AKOKOASA JN | 7.4 |  |  | CR-AGO-C-008 | [10 empty] | COCOA
14.7
10 | FOSUANSA - AMANOR & Other | FOSUANSA - AMANOR | 6 | ASI | Reshaping | CR-ASI-A-008 | Kobnash Investment | 2011-09-27 | 2012-01-18 | 2012-05-18 | 24468 |  |  |  |  | DFR/CR/AOB/RESH/GOG/53/11 | GOG
|  | MAHOGO - OFABIR | 5 |  |  | CR-ASI-A-026 | [10 empty] | COCOA
11
12 | KENYANKOR - AKWAKWAA & Others | KENYANKOR - AKWAKWAA | 8.5 | AGO | Reshaping | CR-AGO-C-057 | Quakor Ltd. | 2011-09-27 | 2012-05-07 | 2012-09-07 | 30020 |  |  |  |  | DFR/CR/AE/RESH/GOG/54/11 | GOG
|  | KENYANKOR - KOBINA ATTA | 1.8 |  |  | CR-AGO-C-058
|  | ABOANO JN - POBIKUMA - NYANKOKWA | 3 |  |  | CR-AES-I-020 | [10 empty] | COCOA
13.3
Note on D5: CR3:

## ROUTINE 2012
DEPARTMENT OF FEEDER ROADS
CENTRAL REGION
MONTHLY PROGRESS REPORT FOR JUNE 2014
NO. | PROJECT NAME |  | ROAD LENGTH (KM) | PROJECT LOCATION (DISTRICT) | ACTIVITY | ROAD NUMBER | CONTRACTOR | WORK PERIOD |  |  | CONTRACT SUM (GH¢) | TOTAL AMOUNT CERTIFIED | % COMPLETED | LENGTH COMPLETED | REMARKS | CONTRACT NUMBER | FUNDING & SOURCES | CERT. NO
[8 empty] | AWARD | DATE OF | DATE OF
[8 empty] | DATE | COMM. | COMP.
ROAD FUND
1 | ATEKYEM - BESEASE JN & OTHER | ATEKYEM - BESEASE JN | 8.25 | KEEA | Reshaping | CR-KEE-C-037 | Olicks Ltd. | 2012-12-21 | 2013-03-13 | 2013-06-13 | 24282 |  |  |  |  | DFR/CR/KEEA/RESH/GOG/1/12 | GOG
|  | ATEKYEM - MPRAKOKROM | 2 |  |  | CR-KEE-A-039
10.25
2 | KOMENDA SEFWI - KROFOKROM & OTHERS | KOMENDA SEFWI - KROFOKROM | 6.6 | KEEA | Reshaping | CR-KEE-C-034 | Cliffstons Co. Ltd. | 2012-12-21 |  |  | 41346.4 |  | 100 | 17.10km of Grass Cutting and Reshaping completed |  | DFR/CR/KEEA/RESH/GOG/2/12 | GOG
|  | ANWIOM JN - BEPOSO | 6.6 |  |  | CR-KEE-C-044
|  | DOMENASE - DUAKYIMASE | 4 |  |  | CR-KEE-A-033 | [10 empty] | COCOA
17.2
3 | KISSI - ATEKYEM & OTHER | KISSI - ATEKYEM | 10 | KEEA | Reshaping | CR-KEE-C-036 | Wam Hills Ent. | 2012-12-21 | 2013-03-08 | 2013-06-08 | 36920 | 32055.55 | 100 | 15.2km of Grass Cutting and Reshaping completed |  | DFR/CR/KEEA/RESH/GOG/3/12 | GOG
|  | EBUKROM JN-HEMANG JN | 5.2 |  |  | Not Available
15.2
4 | ABREM AGONA - ADAMA & OTHERS | ABREM AGONA - ADAMA | 9.3 | KEEA | Reshaping | CR-KEE-I-017 | Raksa Investment Ltd. | 2012-12-21 |  | 2013-09-16 | 41926 | 44975.21 | 100 | 23.60km of Grass Cutting and Reshaping completed |  | DFR/CR/KEEA/RESH/GOG/4/12 | GOG
|  | AKWAKROM JN - AKWAKROM | 4.1 |  |  | CR-KEE-A-021
|  | NTONTONSO JN - NTONTONSO | 2.6 |  |  | CR-KEE-A-018
|  | WAREBEBA JN - WAREBEBA | 1.5 |  |  | CR-KEE-A-023
17.5
5 | ANYINASE - DUTCH KOMENDA & OTHERS | ANYINASE - DUTCH KOMENDA | 5.2 | KEEA | Reshaping | CR-KEE-A-025 | Acod Const. | 2012-12-21 | 2013-04-30 | 2013-07-30 | 31080 |  | 100 | 13.0km of Grass Cutting and Reshaping completed |  | DFR/CR/KEEA/RESH/GOG/5/12 | GOG
|  | DOMPOASE - KOKWADO | 1.5 |  |  | CR-KEE-A-012
|  | ANLO JN - ANLO | 0.5 |  |  | CR-KEE-A-026
|  | DWENASE - JUKWA | 4 |  |  | CR-KEE-I-016
|  | ANTADO JN - ANTADO | 0.8 |  |  | CR-KEE-A-035
|  | ANLO BEACH JN - ANLO BEACH | 1 |  |  | CR-KEE-A-027
13
6 | EFUTU JN - ABREM AGONA & OTHERS | EFUTU JN - ABREM AGONA | 14.7 | KEEA | Grasscutting | CR-KEE-I-009 | Osei Appeani Co. Ltd. | 2012-12-21 | 2013-02-20 | 2013-05-20 | 11871 | 17184.4 | 100 | 34.10km of Grass Cutting completed | Variation Order approved on 07/05/2013 | DFR/CR/KEEA/RESH/GOG/6/12 | GOG
|  | AYENSUDO - BRENU-AKYINIM | 5.1 |  |  | CR-KEE-A-019
|  | ATAABADZE JN - ABREM AGONA | 11.7 |  |  | CR-KEE-I-015
|  | KOMENDA JN - KOMENDA | 4 |  |  | CR-KEE-A-028
35.5
7 | NTRANOA JN - SSNIT & OTHERS | NTRANOA JN - SSNIT | 6 | KEEA | Reshaping | CR-KEE-C-004 | Merzoe Ventures | 2012-12-21 |  |  | 30082 |  | 100 | 6.2km of Grass Cutting and Reshaping completed |  | DFR/CR/KEEA/RESH/GOG/7/12 | GOG
|  | ANKAFUL PRISON - SIMIW | 3 |  |  | CR-KEE-A-002
|  | ABEE JN - ABEE | 0.5 |  |  | CR-KEE-A-003
|  | AMOANDA JN - AMOANDA | 2.2 |  |  | CR-KEE-A-005
|  | MINISTRY OF AGRIC JN - BUNGALOW | 0.6 |  |  | CR-KEE-A-006
12.3
8 | GYNABODIE JN - NYANKOMASE | GYNABODIE JN - NYANKOMASE | 19.2 | ASS | Reshaping | CR-ASS-C-011 | Zigma Gh Ltd. | 2012-12-21 |  | 2013-07-26 | 47624 | 39124.94 | 100 | 19.20km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/8/12 | GOG
19.2
9 | ONGUA - SARGENTKROM | ONGUA - SARGENTKROM | 14.5 | ASS | Reshaping | CR-ASS-A-039 | Daess Const. Ltd. | 2012-12-21 |  |  | 35217 | 30046.9 | 100 | 14.5km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/9/12 | GOG | 1
14.5
10 | KYINSO - GYINABODIE & OTHER | KYINSO - GYINABODIE | 14 | ASS | Reshaping | CR-ASS-A-008 | A.A.D. Gh Ltd. | 2012-12-21 |  |  | 49698 |  |  |  |  | DFR/CR/AS/RESH/GOG/10/12 | GOG
|  | TUAKWA JN - AGYEMPOMA | 7.6 |  |  | CR-ASS-A-013
21.6
11 | ASSIN AKROFROM - ASIBIREM & OTHERS | ASSIN AKROFROM - ASIBIREM | 13.3 | ASS | Reshaping | CR-ASS-I-031 | Carvalie Ent. | 2012-12-21 | 2013-02-28 | 2013-06-28 | 49916.6 | 44150.08 | 100 | 21.5km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/11/12 | GOG
|  | ANDOE JN - LARTEH AMANBETE | 3.3 |  |  | CR-ASS-C-029
|  | FANTI AMANBETI JN - FANTI AMANBETI | 3.3 |  |  | CR-ASI-A-007
|  | LARTEH AMANBETE - ANDOE BUSH | 1.6 |  |  | CR-ASS-C-033
21.5
12 | ADUBIASE - ANDOE PH I | ADUBIASE - ANDOE | 14 | ASS | Reshaping | CR-ASS-C-001 | Brokers Ventures | 2012-12-21 | 2013-02-04 | 2013-06-04 | 34684 | 31238 | 100 | 14.0km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/12/12 | GOG
14
13 | ADUBIASE - ANDOE PH II | ADUBIASE - ANDOE | 14 | ASS | Reshaping | CR-ASS-C-001 | M.A. Benle & Sons Ltd. | 2012-12-21 |  |  | 35068 | 32200.55 | 100 | 14.0km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/13/12 | GOG
14
14 | BENUYE JN - AWAISU WAWASE & OTHERS | BENUYE JN - AWAISU WAWASE | 9 | ASN | Reshaping | CR-ASN-C-004 | Tonymax Const. Ltd. | 2012-12-21 |  |  | 39189 | 25051.81 | 100 | 15.40km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/14/12 | GOG
|  | SEKANBODUA JN - SEKANBODUA | 2.4 |  |  | CR-ASN-A-036
|  | GANGAN - ANKAA | 4 |  |  | CR-ASN-A-008 | Super Technology Ent. | [9 empty] | COCOA
15.4
15 | ATONSU - NYAMYENAM & OTHERS | ATONSU - NYAMYENAM | 10 | ASN | Reshaping | CR-ASN-A-041 | Chrispoint Ltd. | 2012-12-21 | 2013-04-30 | 2013-08-30 | 47051 | 34427.18 | 100 | 19.0km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/15/12 | GOG | 1
|  | ASSIN FOSU - ANKAASE BUSH | 4.5 |  |  | CR-ASN-A-042
|  | ASSIN FOSU - ODUMASI | 4 |  |  | CR-ASN-A-040 | Super Technology Ent. | [9 empty] | COCOA
18.5
16 | BUNGALOW - DONKORKROM | BUNGALOW - DONKORKROM | 11 | ASN | Reshaping | CR-ASN-A-012 | King-Kay Co. Ltd. | 2012-12-21 |  |  | 28480 | 19964.96 | 100 | 9.0km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/16/12 | GOG
11
17 | ASSIN ASIBIRIM - ODUMASE & OTHER | ASSIN ASIBIRIM - ODUMASE | 11 | ASN | Reshaping | CR-ASN-C-026 | Groca Co. Ltd. | 2012-12-21 | 2013-03-04 | 2013-07-04 | 34273 | 34272.59 | 100 | 13.5km of Grass Cutting and Reshaping completed |  | DFR/CR/AS/RESH/GOG/17/12 | GOG
|  | ASSIN ASIBIRIM - OBIRIKWAKU | 2.25 |  |  | CR-ASN-A-021 | [10 empty] | COCOA
13.25
18 | CONST. OF SPEED RAMPS ON AWUTU TOWN ROADS PH I | CONST. OF SPEED RAMPS ON AWUTU TOWN ROADS PH I | 0.73 | AWS | Spot Improvement | Not Available | Winstar Ltd. | 2012-12-21 | 2013-04-26 | 2013-10-26 | 49800 |  | 90 | 5№ Speed humps |  | DFR/CR/AWS/RESH/GOG/18/12 | GOG
0.73
19 | CONST. OF SPEED RAMPS ON AWUTU TOWN ROADS PH II | CONST. OF SPEED RAMPS ON AWUTU TOWN ROADS PH II | 0.81 | AWS | Spot Improvement | Not Available | Winstar Ltd. | 2012-12-21 | 2013-04-26 | 2013-10-26 | 49800 |  | 100 | 5№ Speed humps |  | DFR/CR/AWS/RESH/GOG/19/12 | GOG
0.81
20 | CONST. OF SPEED RAMPS ON SENYA TOWN ROADS PH I | CONST. OF SPEED RAMPS ON SENYA TOWN ROADS PH I | 1.25 | AWS | Spot Improvement | Not Available | O.D.B. Const. Ltd. | 2012-12-21 | 2013-04-26 | 2013-10-26 | 49320 |  | 90 | 5№ Speed humps |  | DFR/CR/AWS/RESH/GOG/20/12 | GOG
1.25
21 | CONST. OF SPEED RAMPS ON SENYA TOWN ROADS PH II | CONST. OF SPEED RAMPS ON SENYA TOWN ROADS PH II | 0.6 | AWS | Spot Improvement | Not Available | O.D.B. Const. Ltd. | 2012-12-21 | 2013-04-26 | 2013-10-26 | 49320 |  | 90 | 5№ Speed humps |  | DFR/CR/AWS/RESH/GOG/20/12 | GOG
0.6
22 | CONST. OF SPEED RAMPS ON SENYA TOWN ROADS PH III | CONST. OF SPEED RAMPS ON SENYA TOWN ROADS PH III | 0.6 | AWS | Spot Improvement | Not Available | Veb-bu Ent. | 2012-12-21 | 2013-04-26 | 2013-10-26 | 49320 |  | 100 | 5№ Speed humps |  | DFR/CR/AWS/RESH/GOG/22/12 | GOG
0.6
23 | ATEITU - WINNEBA & OTHERS | ATEITU - WINNEBA | 3.87 | EF | Reshaping | CR-AES-C-050 | Sweet City Ent. | 2012-12-21 |  | 2013-08-18 | 28412 | 24060.76 | 100 | 11.42km of Grass Cutting and Reshaping completed |  | DFR/CR/EF/RESH/GOG/23/12 | GOG
|  | AGYATEME JN - AGYATEME | 2.2 |  |  | CR-AES-A-037
|  | NSUAKYIR - KAKRABA | 1.6 |  |  | CR-AES-A-038
|  | GYATEKROM - OSUBOMPANIN | 3.75 |  |  | CR-AES-C-049 | [10 empty] | COCOA
11.42
24 | AHINTIA - KASOA & OTHERS | AHINTIA - KASOA | 10 | AWS | Reshaping | CR-AES-C-035 | Seidusco Ent. | 2012-12-21 |  | 2013-07-18 | 49548 | 34798.86 | 100 | 24.90km of Grass Cutting and Reshaping completed |  | DFR/CR/AWS/RESH/GOG/24/12 | GOG
|  | OSIMPO - AKRAMAN | 4 |  |  | CR-AES-I-031
|  | MFADWEN JN - BONTRASE | 5.1 |  |  | CR-AES-C-025
|  | OBUASE - BENTUM | 2 |  |  | CR-ASN-I-017 | [10 empty] | COCOA
21.1
25 | AKUBIFA JN - GYEIKRODUA & OTHERS | AKUBIFA JN - GYEIKRODUA | 6.8 | AWS | Reshaping | CR-AES-C-026 | Royal Star Co. Ltd. | 2012-12-21 |  |  | 23284 |  | 100 | 10.40km of Grass Cutting and Reshaping completed |  | DFR/CR/AWS/RESH/GOG/25/12 | GOG
|  | GYEIKRODUA - O'LOTOM | 3 |  |  | CR-AES-C-027
|  | GYAN NKWANTA - GYAN | 0.7 |  |  | CR-AES-A-028 | [10 empty] | COCOA
10.5
26 | FIANKO - OFAADA & OTHERS | FIANKO - OFAADA | 7 | AWS | Reshaping | CR-AES-C-006 | Leads Co. Ltd. | 2012-12-21 |  | 2013-06-24 | 43901 | 33338.95 | 100 | 18.12km of Grass Cutting and Reshaping completed |  | DFR/CR/AWS/RESH/GOG/26/12 | GOG
|  | MMOFRAKROM JN - MMOFRAKROM | 1.3 |  |  | CR-AES-A-010
|  | DANKWA JN - DANKWA | 1.2 |  |  | CR-AES-A-011
|  | AKOMFUAKURA - OFAADA | 2 |  |  | CR-AES-C-009
|  | OKWABENA - OFASO | 2.4 |  |  | CR-AES-C-012
|  | AKOMFUAKURA - OFASO JN | 2.9 |  |  | CR-AES-C-058
|  | TOPIASE JN - ABONKWANTA | 2.6 |  |  | CR-AES-I-007
19.4
27 | KROFU JN - EWOYAA JN & OTHERS | KROFU JN - EWOYAA JN | 10.1 | MFA | Reshaping | CR-MFA-C-046 | B. A. Worlanyo Ent. | 2012-12-21 | 2013-03-28 | 2013-06-28 | 28818 |  | 70 | 8.40km of Grass Cutting and Reshaping completed |  | DFR/CR/MFA/RESH/GOG/27/12 | GOG
|  | ANTAADZE JN - ANTAADZE | 1 |  |  | CR-MFA-C-047
|  | KROFU - KRAMPAKROM JN | 1.7 |  |  | CR-MFA-C-049 | [10 empty] | COCOA
12.8
28 | NSANFO JN - NKRAMOFOKROM & OTHERS | NSANFO JN - NKRAMOFOKROM | 10.6 | MFA | Reshaping | CR-MFA-C-055 | Unkar Ltd. | 2012-12-21 |  |  | 46659 |  |  |  |  | DFR/CR/MFA/RESH/GOG/28/12 | GOG
|  | NSANFO - NSAADZE JN | 4.4 |  |  | CR-MFA-C-057
|  | KORMANTSE - OTSIR | 3.5 |  |  | CR-MFA-A-054
|  | OGUANAMUA JN - AKOA | 2 |  |  | CR-MFA-A-056 | [10 empty] | COCOA
20.5
29 | ABOR JN - ENYAN APAA & OTHER | ABOR JN - ENYAN APAA | 6 | MFA | Reshaping | CR-MFA-I-017 | P-Clicks Services | 2012-12-21 | 2013-05-17 | 2013-08-16 | 25560 | 21181.5 | 100 | 9.0km of Grass Cutting and Reshaping completed |  | DFR/CR/MF/RESH/GOG/29/12 | GOG | 1
|  | AMPREFI JN - BEWURA | 5.4 |  |  | CR-MFA-I-028 | [10 empty] | COCOA
11.4
30 | MPRENKYI JN - BEWURA | MPRENKYI JN - BEWURA | 13 | MFA | Reshaping | CR-MFA-I-027 | Kobnash Investment | 2012-12-21 |  |  | 29074 |  | 100 | 13.0km of Grass Cutting and Reshaping completed |  | DFR/CR/MF/RESH/GOG/30/12 | GOG
13
31 | ANOMABO - BANDO & OTHERS | ANOMABO - BANDO | 12 | MFA | Reshaping | CR-MFA-I-036 | Sanekambala Co. Ltd. | 2012-12-21 | 2013-02-07 | 2013-05-07 | 34340 | 32621.3 | 100 | 17.8km of Grass Cutting and Reshaping completed |  | DFR/CR/MF/RESH/GOG/31/12 | GOG
|  | OGOEKROM - OGOEKROM JN | 0.4 |  |  | CR-MFA-C-033
|  | OBOADZE - KANKABOM | 1 |  |  | CR-MFA-C-034
|  | ANOMANSA JN - OGOEKROM | 2.2 |  |  | CR-MFA-C-035 | [10 empty] | COCOA
15.6
32 | ADANSI - IMMUNA & OTHERS | ADANSI - IMMUNA | 11 | MFA | Reshaping | CR-MFA-C-074 | Roovan Co. Ltd. | 2012-12-21 |  |  | 49827.2 |  |  |  |  | DFR/CR/MF/RESH/GOG/32/12 | GOG
|  | EGYANKWA - IMMUNA | 6 |  |  | CR-MFA-C-005
|  | OTUAM - SRAFA KOKODO | 4.7 |  |  | CR-MFA-C-073 | [10 empty] | COCOA
21.7
33 | BIRIWA - ASAFORA JN & OTHERS | BIRIWA - ASAFORA JN | 5.6 | MFA | Reshaping | CR-MFA-C-064 | Kobota Ent. | 2012-12-21 |  |  | 32355 |  | 50 | 7.0km of Grass Cutting and Reshaping completed |  | DFR/CR/MF/RESH/GOG/33/12 | GOG
|  | WAAKROM JN - WAAKROM | 1.5 |  |  | CR-MFA-A-059
|  | AKATAKYIWA JN - AKATAKYIWA | 0.8 |  |  | CR-MFA-A-060
|  | EGYIREFA JN - EGYIREFA | 2.85 |  |  | CR-MFA-A-062
|  | AKOANSO - EKROFUL | 3.5 |  |  | CR-MFA-A-063 | [10 empty] | COCOA
14.25
34 | BAIFIKROM - DOMINASE & OTHERS | BAIFIKROM - DOMINASE | 12 | MFA | Reshaping | CR-MFA-C-025 | Minak Investment Co. Ltd. | 2012-12-21 | 2013-03-29 | 2013-06-29 | 40200 | 38857 | 100 | 18.0km of Grass Cutting and Reshaping completed |  | DFR/CR/MF/RESH/GOG/34/12 | GOG
|  | ESHIROW JN - ESHIROW JN | 1.9 |  |  | CR-MFA-A-026
|  | DUADZE - KWESILANSAH | 4 |  |  | CR-MFA-C-075 | [10 empty] | COCOA
17.9
35 | EKUMFI DUNKWA - ATWA JN & OTHERS | EKUMFI DUNKWA - ATWA JN | 10 | MFA | Reshaping | CR-MFA-C-013 | Kaneamayewo Ent. | 2012-12-21 |  |  | 26553 |  |  |  |  | DFR/CR/MF/RESH/GOG/35/12 | GOG
|  | GYINANKOMA JN - GYINANKOMA | 1.1 |  |  | CR-MFA-A-008
|  | GYINANKOMA - ADUASA KOKODO | 0.65 |  |  | CR-MFA-C-010 | [10 empty] | COCOA
11.75
36 | ABEADZEKYEAKOR - KWAAKROM & OTHERS | ABEADZEKYEAKOR - KWAAKROM | 9 | MFA | Reshaping | CR-MFA-I-029 | Willjoan Ent. | 2012-12-21 | 2013-04-03 | 2013-08-03 | 27192 | 21099.92 | 100 | 9.5km of Grass Cutting and Reshaping completed |  | DFR/CR/MF/RESH/GOG/36/12 | GOG
|  | MAMPONG - ESAIKROM | 2.5 |  |  | CR-MFA-A-038
|  | ENYINABRIM JN - ENYINABRIM | 0.5 |  |  | CR-MFA-A-039 | [10 empty] | COCOA
12
37 | BROFREASE JN - KWETUA & OTHERS | BROFREASE JN - KWETUA | 4.8 | AE | Reshaping | CR-AGO-C-035 | Cusby & Cusby Ltd. | 2012-12-21 | 2013-04-09 | 2013-06-03 | 40735 |  | 80 | 11.0km of Grass Cutting and Reshaping completed |  | DFR/CR/AE/RESH/GOG/37/12 | GOG
|  | DUOTO - OBREPO | 2 |  |  | CR-AGO-A-027
|  | DUABONE - PAASO | 1 |  |  | CR-AGO-C-036
|  | NKRANKROM JN - NKRANKROM | 2 |  |  | CR-AGO-A-038
|  | KWESIKUM - DUABONE | 3.1 |  |  | CR-AGO-C-029
|  | DUABONE - KWAME SAM JN | 3 |  |  | CR-AGO-C-037
|  | KOFIKUM - ABAMKROM | 3.03 |  |  | CR-AGO-I-056
16.93
38 | ASAFO - KWESITWIKWAA & OTHERS | ASAFO - KWESITWIKWAA | 6 | AE | Reshaping | CR-AGO-I-015 | Cusby & Cusby Ltd. | 2012-12-21 | 2013-04-09 | 2013-06-03 | 29436 |  | 80 | 6.0km of Grass Cutting and Reshaping completed |  | DFR/CR/AE/RESH/GOG/39/12 | GOG
|  | BRAHABEKUMI JN - BRAHABEKUMI | 1.25 |  |  | CR-AGO-A-002
|  | OTABILKWA JN - OTABILKWA | 1.2 |  |  | CR-AGO-A-003
|  | OBOSOMASE - ASANKWA | 3 |  |  | CR-AGO-A-025
|  | NANTIFA - KOKOADO | 3 |  |  | CR-AGO-C-016
11.45
39 | NSABAA - NYARKROM & OTHERS | NSABAA - NYARKROM | 5.6 | AE | Reshaping | CR-AGO-C-006 | Kaleb Access Ltd. | 2012-12-21 | 2013-05-09 | 2013-09-09 | 35526 |  |  |  |  | DFR/CR/AE/RESH/GOG/39/12 | GOG
|  | NINTA - OFOASE | 2.6 |  |  | Not Available
|  | NINTA - NAMPONG | 2.6 |  |  | CR-AGO-C-029
|  | KWESIKUM - DUABONE | 3 |  |  | CR-AGO-C-029
13.8
40 | AMANFOR - NAMAWORA & OTHERS | AMANFOR - NAMAWORA | 8.4 | AE | Reshaping | CR-AGO-C-010/11/12 | Offshore Eng. Ltd. | 2012-12-21 |  |  | 49598.4 |  | 100 | 20.0km of Grass Cutting and Reshaping completed |  | DFR/CR/AE/RESH/GOG/40/12 | GOG
|  | BOSOMPA - NKWANTANANDO | 3 |  |  | Not Available
|  | BOBIKUMA - KUNTUNASE | 10.4 |  |  | CR-AGO-I-050 | Super Technology Ent. | [9 empty] | COCOA
21.8
41 | NYINASIN - TSETSEKASUM & OTHERS | NYINASIN - TSETSEKASUM | 6 | CC | Reshaping | CR-CCP-I-006 | Abdul Rahman & Sons Ltd. | 2012-12-21 | 2013-03-07 | 2013-07-07 | 42523.6 | 29931.13 | 100 | 15.9km of Grass Cutting and Reshaping completed |  | DFR/CR/CC/RESH/GOG/41/12 | GOG
|  | EFUTU - SRODOFO | 3.9 |  |  | CR-AAK-I-014
|  | ANKAFUL SCHOOL - EBU | 5 |  |  | CR-CCP-A-002
|  | KOKOWADO JN - NKOKOSA | 3.2 |  |  | CR-CCP-A-008
18.1
42 | TUAKWA JN - BETSINGUA & OTHERS | TUAKWA JN - BETSINGUA | 8 | AAK | Reshaping | CR-AAK-C-046 | Rocky Stream Co. Ltd. | 2012-12-21 | 2013-03-04 | 2013-07-04 | 49166 | 49102.34 | 100 | 21.4km of Grass Cutting and Reshaping completed |  | DFR/CR/AAK/RESH/GOG/42/12 | GOG
|  | TUAKWA - ODONKWA | 1 |  |  | CR-AAK-A-047
|  | BANDO - ABURA ABOASE | 3 |  |  | CR-AAK-C-048
|  | OBOHEN - EKROFUL | 1.4 |  |  | CR-AAK-C-049
|  | GYABANKROM - KWAMANKESE | 2 |  |  | CR-AAK-C-050
|  | KWAMANKESE - OBORKOR NKWANTA | 4 |  |  | CR-AAK-C-051
|  | KANKANASE JN - OLD ODONASE | 2 |  |  | CR-AAK-C-052
21.4
43 | ABAKRAMPA JN - OKYIREKU | ABAKRAMPA JN - OKYIREKU | 20.5 | AAK | Reshaping | CR-AAK-C-025 | P. F. K. Const. Wks. | 2012-12-21 |  |  | 45736 |  | 80 | 16.4km of Grass Cutting and Reshaping completed |  | DFR/CR/AAK/RESH/GOG/43/12 | GOG
20.5
44 | ABURA DENKYIRA - ABAKRAMPA & OTHERS | ABURA DENKYIRA - ABAKRAMPA | 6 | AAK | Reshaping | CR-AAK-C-027 | Akakyere Ventures | 2012-12-21 |  |  | 27554.2 |  | 100 | 12.1km of Grass Cutting and Reshaping completed |  | DFR/CR/AAK/RESH/GOG/44/12 | GOG
|  | PRA EWUSI - EKROFUL | 1.1 |  |  | CR-AAK-A-028
|  | TAYEDO - EKROFUL | 0.7 |  |  | CR-AAK-A-029
|  | NKRAMOFOKROM - AMOANDA | 0.9 |  |  | CR-AAK-A-030
|  | BATANYA - ABAKRAMPA | 3.4 |  |  | CR-AAK-A-031 | [10 empty] | COCOA
12.1
45 | ABAKRAMPA - ACHIASE JN & OTHERS | ABAKRAMPA - ACHIASE JN | 14.4 | AAK | Reshaping | CR-AAK-I-032 | Lilgeo Ent. Ltd. | 2012-12-21 | 2013-03-20 | 2013-07-20 | 40776 | 40776 | 100 | 18.5km of Grass Cutting and Reshaping completed |  | DFR/CR/AAK/RESH/GOG/45/12 | GOG | 1
|  | PAPAGYA - TSETSEKASUM | 3.4 |  |  | CR-AAK-A-035
|  | ASAMAN JN - ASAMAN | 0.4 |  |  | CR-AAK-A-036 | [10 empty] | COCOA
18.2
46 | ASEBU - BIRIMSO WATER WORKS & OTHERS | ASEBU - BIRIMSO WATER WORKS | 10.7 | AAK | Reshaping | CR-AAK-I-020 | Asim Links Investment Ltd. | 2012-12-21 |  |  | 27456 |  | 90 | 11.0km of Grass Cutting and Reshaping completed |  | DFR/CR/AAK/RESH/GOG/46/12 | GOG
|  | NFRAMANDWE JN - NFRAMANDWE | 0.2 |  |  | CR-AAK-A-021
|  | OLD EBU JN - BREBEA | 1.3 |  |  | CR-AAK-A-022
12.2
47 | EGUASE - ASEBU EKROFUL JN& OTHERS | EGUASE - ASEBU EKROFUL JN | 8.7 | AAK | Reshaping | CR-AAK-C-017 | Adeaq Co. Ltd. | 2012-12-21 | 2013-04-11 | 2013-08-11 | 34278.8 |  |  |  |  | DFR/CR/AAK/RESH/GOG/47/12 | GOG
|  | MENSAH JN - MENSAH | 2.25 |  |  | CR-AAK-A-018
|  | ABUENU JN - ABUENU | 3.7 |  |  | CR-AAK-A-024
14.65
48 | BOBIKUMA - NYARKROM | BOBIKUMA - NYARKROM | 11.5 | AW | Reshaping | CR-AGO-C-049 | Sardauna Ltd. | 2012-12-21 |  |  | 26042 |  |  |  |  | DFR/CR/AAK/RESH/GOG/48/12 | GOG
11.5
49 | MANDO - ENYAN APAA & OTHERS | MANDO - ENYAN APAA | 11 | AJU | Reshaping | CR-AJU-C-012 | Ruzilet Gh Co. Ltd. | 2012-12-21 | 2013-03-11 | 2013-07-11 | 49261 |  | 95 | 20.0km of Grass Cutting and Reshaping completed |  | DFR/CR/AJU/RESH/GOG/49/12 | GOG
|  | OBONTSER - OBONTSER ENYAN | 3.9 |  |  | CR-AJU-A-013
|  | ESIAMAN - ASASAN | 3 |  |  | CR-AJU-C-007
|  | ADUASA KOKODO - OBONTSER ENYAN | 1.6 |  |  | CR-AJU-C-030
|  | NSAWADZE - OBONTSER JN | 1.6 |  |  | CR-AJU-C-031 | [10 empty] | COCOA
21.1
50 | AMPIA - ABEADZE & OTHERS | AMPIA - ABEADZE | 5 | AJU | Reshaping | CR-AJU-I-034 | Alaro Eng. Ltd. | 2012-12-21 | 2013-04-18 | 2013-08-18 | 35067.8 |  |  |  |  | DFR/CR/AJU/RESH/GOG/50/12 | GOG
|  | ABROFO - ATAKORASE | 4 |  |  | CR-AJU-A-009
|  | MANDO JN - ATAKORASE JN | 2 |  |  | CR-AJU-C-010
|  | MANDO - OPPONSO KYEBI | 3.4 |  |  | CR-AJU-I-011 | [10 empty] | COCOA
14.4
51 | MANTE (AMANOR) - OTABILKWA & OTHERS | MANTE (AMANOR) - OTABILKWA | 5 | ASI | Reshaping | CR-ASI-A-009 | Global-Ten Ltd. | 2012-12-21 |  |  | 36012.2 |  |  |  |  | DFR/CR/ASI/RESH/GOG/51/12 | GOG
|  | OTABILKWA - OBOSOMFO | 2 |  |  | CR-ASI-A-002
|  | ANKOMAKWAA JN - BISEASE | 3 |  |  | CR-ASI-A-013
|  | YEKUKWA - AKAWUSU | 4.7 |  |  | CR-ASI-A-031 | [10 empty] | COCOA
14.7
52 | JAMRA - KROBO YAW | JAMRA - KROBO YAW | 13 | ASI | Reshaping | CR-ASI-A-010 | Visitors Const. Ltd. | 2012-12-21 |  |  | 29295 |  |  |  |  | DFR/CR/ASI/RESH/GOG/52/12 | GOG
13
53 | BEPOTEN JN - BEPOTEN & OTHERS | BEPOTEN JN - BEPOTEN | 8 | THLD | Reshaping | CR-LDE-A-062 | Karins Gh Ltd. | 2012-12-21 |  |  | 34554 |  |  |  |  | DFR/CR/THLD/RESH/GOG/53/12 | GOG
|  | ANKAAKO - AKATAKYIWA | 5.2 |  |  | CR-LDE-I-056 | [10 empty] | COCOA
13.2
54 | NYINASE - BROFOYEDUR & OTHERS | NYINASE - BROFOYEDUR | 4.7 | THLD | Reshaping | CR-LDE-A-017 | Ebko-V Ltd. | 2012-12-21 | 2013-03-07 | 2013-07-07 | 35873 | 22076.17 | 100 | 9.1km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/54/12 | GOG
|  | OLD DAMANG JN - OLD DAMANG | 2 |  |  | CR-LDE-A-018
|  | ABODOM - HEMANSE | 4.2 |  |  | CR-LDE-A-020
|  | ABODOM JN - ABODOM | 3 |  |  | CR-LDE-A-019 | [10 empty] | COCOA
13.9
55 | DARMANG - MOSEASO & OTHER | DARMANG - MOSEASO | 12 | THLD | Reshaping | CR-LDE-C-016 | Koo Baiden Co. Ltd. | 2012-12-21 |  |  | 35926 |  |  |  |  | DFR/CR/THLD/RESH/GOG/55/12 | GOG
|  | DARMANG - KOJOKROM | 4 |  |  | CR-LDE-A-014 | [10 empty] | COCOA
16
56 | MINTASO - ADADEKOFI & OTHERS | MINTASO - ADADEKOFI | 9.7 | THLD | Reshaping | CR-LDE-I-032 | Hafissco Gh Ltd. | 2012-12-21 |  | 2013-07-07 | 49756.7 | 35105 | 71.86 | 12.80km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/56/12 | GOG
|  | KOTOKYE(TWIFU JUABENG) - ATIASO | 4 |  |  | CR-LDE-A-033
|  | KOTOKYE(TWIFU JUABENG) - SALT FACTORY | 1.3 |  |  | CR-LDE-A-034
|  | ATTORKROM JN - ATTORKROM | 2.2 |  |  | CR-LDE-A-036
|  | KYIRENKUM - BONINSUMA | 2.4 |  |  | CR-LDE-C-035 | [10 empty] | COCOA
19.6
57 | PERWUDIE - GYAWARE & OTHERS | PERWUDIE - GYAWARE | 3 | THLD | Reshaping | CR-LDE-A-031 | Acquah & Sons Ltd. | 2012-12-21 |  |  | 26425 |  |  |  |  | DFR/CR/THLD/RESH/GOG/57/12 | 0
|  | ATRENSU NO.1 - ATRENSU NO.2 | 2.5 |  |  | CR-LDE-A-038
|  | TUAKWA JN - ATRENSU NO.2 | 6 |  |  | CR-LDE-C-039 | [10 empty] | COCOA
11.5
58 | NKWANKYEMANSO - NUANUA & OTHER | NKWANKYEMANSO - NUANUA | 15 | THLD | Reshaping | CR-LDE-I-001 | B-Molie Ent. Ltd. | 2012-12-21 |  |  | 46905 | 44587.32 | 100 | 17.5km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/58/12 | GOG
|  | ADJETEYKROM JN - ADJETEYKROM | 2.5 |  |  | CR-LDE-A-002 | [10 empty] | COCOA
17.5
59 | GYANKOBO - NSUTEM & OTHER | GYANKOBO - NSUTEM | 17 | THLD | Reshaping | CR-LDE-I-052 | Silversteps Co. Ltd. | 2012-12-21 | 2013-03-07 | 2013-07-07 | 48956 | 44635.17 | 100 | 19.2km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/59/12 | GOG
|  | ANTWIKWAA JN - ANTWIKWAA | 2 |  |  | CR-LDE-A-057 | [10 empty] | COCOA
19
60 | HEMANG-PAASO - ABAKA NKWANTA & OTHERS | HEMANG-PAASO - ABAKA NKWANTA | 15 | THLD | Reshaping | CR-LDE-C-058 | Imohin Const. | 2012-12-21 |  | 2013-08-09 | 48493 | 38143.87 | 100 | 18.5km of Grass Cutting and Reshaping completed |  | DFR/CR/THLD/RESH/GOG/60/12 | GOG
|  | BETIMOR - NYAMEYEDOM | 6.7 |  |  | CR-LDE-A-049 | [10 empty] | COCOA
21.7
61 | EFUM - GYAWARE & OTHERS | EFUM - GYAWARE | 7 | THLD | Reshaping |  | Landlock Gh Natural Paving Ltd. | 2012-12-21 |  |  | 42793 |  |  |  |  | DFR/CR/THLD/RESH/GOG/61/12 | GOG
|  | LAST STOP - APONSAHSO | 3.5
|  | BREMANG - ANTIFILICIA | 2.5
|  | KWAMOANO - ATWEREBONANDA | 3.5 | [13 empty] | COCOA
16.5
62 | OGUAA - GOMOA TARKWA | OGUAA - GOMOA TARKWA | 15.5 | GW | Reshaping | CR-GOM-I-021 | Jonokie Ltd. | 2012-12-21 |  | 2013-09-16 | 36866 | 34886.72 | 100 | 15.50km of Grass Cutting and Reshaping completed |  | DFR/CR/GW/RESH/GOG/62/12 | GOG
15.5
63 | GOMOA BROFO - GOMOA AKROPONG & OTHERS | GOMOA BROFO - GOMOA AKROPONG | 4 | GW | Reshaping | CR-GOM-A-032 | Saint Gallen Ent. | 2012-12-21 |  |  | 36680 |  | 100 | 15.50km of Grass Cutting and Reshaping completed |  | DFR/CR/GW/RESH/GOG/63/12 | GOG
|  | GOMOA AKYEASE - GOMOA MANKESSIM | 3 |  |  | CR-GOM-C-033
|  | GOMOA AKROPONG - AKROPONG JN | 4.5 |  |  | CR-GOM-C-034
|  | APPIAKROM DEBISO JN - ESHIEM | 4 |  |  | CR-GOM-I-022 | [10 empty] | COCOA
15.5
64 | GOMOA MANSO NO.2 JN - OGUAA JN | GOMOA MANSO NO.2 JN - OGUAA JN | 13 | GW | Reshaping | CR-GOM-C-020 | Saint Gallen Ent. | 2012-12-21 |  |  | 29159 | 27948.75 | 100 | 13.00km of Grass Cutting and Reshaping completed |  | DFR/CR/GW/RESH/GOG/64/12 | GOG
13
65 | SIMBROFO JN - DENKYIRA & OTHERS | SIMBROFO JN - DENKYIRA | 11 | GW | Reshaping | CR-GOM-C-007 | Raksa Investment Ltd. | 2012-12-21 |  |  | 48970 |  | 100 | 24.0km of Grass Cutting and Reshaping completed |  | DFR/CR/GW/RESH/GOG/65/12 | GOG
|  | OGUAN JN - NDUEM | 9.2 |  |  | CR-GOM-C-006
|  | OGUAN JN - AJUMAKO | 4.5 |  |  | CR-GOM-C-014 | [10 empty] | COCOA
24.7
66 | OGUAA JN - ABEADZE & OTHERS | OGUAA JN - ABEADZE | 8 | GW | Reshaping | CR-GOM-I-021 | AWC Services | 2012-12-21 |  |  | 42900 |  | 100 | 18km of Grass Cutting and Reshaping completed |  | DFR/CR/GW/RESH/GOG/66/12 | GOG
|  | GOMOA TARKWA - ABEADZE | 7.5 |  |  | CR-GOM-I-021
|  | GOMOA AKYEASE - GOMOA MANKESSIM | 3.5 |  |  | CR-GOM-C-033 | [10 empty] | COCOA
19
67 | APAM - BROFOYEDUR JN & OTHERS | APAM - BROFOYEDUR JN | 11.8 | GW | Reshaping | CR-GOM-C-018 | Antonopos Ltd. | 2012-12-21 |  |  | 37804.8 |  | 100 | 15.0km of Grass Cutting and Reshaping completed |  | DFR/CR/GW/RESH/GOG/67/12 | GOG
|  | GOMOA ABOTSIA JN - GOMOA ABOTSIA | 0.8 |  |  | CR-GOM-A-017
|  | GOMOA ASEMPANYIN JN - ASEMPANYIN | 1 |  |  | CR-GOM-A-036
|  | BROFOYEDUR - GOMOA ASSIN | 2.2 |  |  | CR-GOM-C-016 | [10 empty] | COCOA
15.8
68 | NDUEM - LOME & OTHERS | NDUEM - LOME | 13.5 | GW | Reshaping | CR-GOM-C-005 | Pekofos Ltd. | 2012-12-21 |  |  | 49647 |  |  |  |  | DFR/CR/GE/RESH/GOG/68/12 | GOG
|  | ACHIASE - DAHOME | 3.8 |  |  | CR-GOM-C-028
|  | EKWAMKROM - MANSO | 3.3 |  |  | CR-GOM-C-041 | [10 empty] | COCOA
20.6
69 | CONST. OF 2/1800X1800mm on PAASO - NYAMEBEKYERE | PAASO - NYAMEBEKYERE | 3.5 | THLD | Spot Improvement | CR-LDE-C-053 | Insaan Gh Ltd. | 2012-12-21 | 2013-03-27 | 2013-07-27 | 47591.64 | 41924 | 90 | 1№ 2/1800mm x1800mm completed. |  | DFR/CR/THLD/RESH/GOG/69/12 | GOG | 1
3.5
Note on D5: CR3: